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TENDER NOTICE

OPEN NATIONAL INVITATION TO TENDER,EMERGENCY PROCEDURE
N° 02/ONIT/NWO6/DTB/2024 OF ____/___/2024
FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION
Financing: MINTP Public Investment Budget of 2024
1. Subject of the invitation to tender: 
Within the framework of 2024 Investment Budget, the Senior Divisional Officer for the MOMO Division, Contracting Authority hereby launches an Open National Invitation to Tender FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION.
2. Nature of work:

Work to be done consists of 

· Serie 000: SITE INSTALLATION  

· Serie 100: cleaning & levelling 

· Serie 300: drianage 

· Serie 400: engineering structures 

· Serie 500: signalsation & security equipment
· Serie 600: others 
3. Execution deadline  



The maximum duration provided by the Contracting Authority for the execution of the works forming the subject of this invitation to tender is six (06) calendar months

4. Lots: 

The work is in a unique lot as follows FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION 
5. Estimated cost

The estimated cost after preliminary studies is 127,221,863 (one hundred and twenty seven Million two hundred and twenty one thousand eight hundred and sixty three) CFA Francs.

6. Participation and origin


Participation to this invitation to tender is open to Cameroonian enterprises that are in compliance with the fiscal laws.

7. Financing

Works which form the subject of this invitation to tender are financed by the 2024 Public Investment Budget of the Ministry of Public Works. Budget head N° 36 125 03 58363300093 523411
Bid bond

Each bidder must include in his administrative documents, a bid bond issued by a first-rate banking establishment approved by the Ministry in charge of finance and whose list is found in document No. 12 of the Tender File, of an amount of 2,544,437 CFA (two million five hundred and forty four thousand four hundred and thirty seven Francs CFA, valid for thirty (30) days beyond the date of validity of bids. As per article 90 (9) of the Public contract Code (Decree No. 2018/366 OF 20 June 2018), certified cheques or bank cheques are acceptable in the place of bid bond.
8. Consultation of Tender File:

The file may be consulted during working hours at the Private Secretariat of the Senior Divisional Officer, Momo-Mbengwi, Telephone N0 (237) ________________, as soon as this tender notice is published.

9.   Acquisition of tender file:




The file may be obtained from the Private Secretariat of the Senior Divisional Officer, Momo-MBENGWI Telephone (237) ________________ as soon as this tender notice is published against payment of a non refundable sum of 120, 000 (one hundred and twenty thousand) CFA francs, payable at Public Treasury, representing the cost of purchasing the tender file. 

10. Submission of bids:

Each offer drafted in English or French in 07 (seven) copies including 01 (one) original and 06 (six) copies should reach the MOMODivisional Tender’s board secretariat   not later than ____/___/2024  at 10 AM local time and should carry the inscription:
TO THE DELEGATED PROJECT OWNER (CONTRACTING AUTHORITY)

<< OPEN NATIONAL INVITATION TO TENDER, EMERGENCY PROCEDURE
N° 02/ONIT/NWO6/DTB/2024 OF ____/___/2024
FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION>>. 
   “To be opened only during the bid-opening session”

11. Admissibility of bids

        Under penalty of being rejected, only originals or true copies certified by the issuing service or administrative authorities (Senior Divisional Officer, Divisional Officers) must imperatively be produced in accordance with the Special Regulations of the invitation to tender. 

They must obligatorily be not older than three (3) months preceding the date of LAUNCHING OF THE TENDERS or may be established after the signature of the tender notice

 Any bid not in compliance with the prescriptions of the Tender File shall be declared inadmissible. This refers especially to the absence of a bid bond issued by a first-rate bank approved by the Minister in charge of Finance. .

12. Opening of bids:

The bids shall be opened in a single phase. The opening of the administrative documents, the Technical and Financial offers will take place on the -----/---/2024  at 11 AM local time, at the Conference Hall of office designated by the Contracting Authority , by the MOMODivisional  Tenders Board. Only bidders may attend or be represented by duly mandated persons of their choice.
13.  Evaluation criteria
The bids shall be evaluated according to the main criteria as follows:
A. Eliminatory criteria

· Outright elimination during the opening session of the bids

1. Absence bid bond(from bank only) in the administrative file; 

2. No purchase receipt Momo Divisional Tresury

3. No reference ≥ 50,000,000frs in this domian(Momo Division)
4. Deadline for delivery higher than prescribed; 

5. False declaration or falsified documents; 

6. A bid with the external envelope carrying a sign or mark leading to the identification of the bidder; 

7. Incomplete financial file; 

8. Change of quantity or unit; 

9. Suspended by MINMAP or ARMP in 2024. 

During the opening session of the bids if a document of the administrative bid is absent or noncompliant, the bidder will be given fourty eight (48) hours to produce or replace said document else will be eliminated during the evaluation of the bids. No such document will be accepted after this deadline.
B. Essential criteria

1. General presentation of the tender files;
2.  Financial capacity; 

3. References of the company in  similar achievements;

4. Quality of the personnel;  

5. Technical organization of the works;

6. Safety measures on the site;
7. Logistics;

8. Attestation and report of site visit;
9. Special Technical Clauses initialed in all the pages;

10. Special Administrative Clauses completed and initialed in all the pages.

These essential criteria are subject to lower limits, the details of which are spelled out in the Special Regulations of the invitation to tender

14. Award

This evaluation will be done in a purely binary method with a positive (yes) or negative (no) with an acceptable minimum of 75% of the essential criteria taken into account.

The contract will be awarded to the bidder who would have proposed the offer with the lowest reasonable amount, in conformity with the regulations of the Tender Documents and having satisfied to 100% of the eliminatory criteria and at least 75%of the essential criteria.

 Pursuant to justification by bidder, unconvincing abnormally low costing will not be accepted spelled out in the Special Regulations of the invitation to tender of this consultation.  
15. Validity of bids
Bidders will remain committed to their offers for sixty (60) days from the deadline set for the submission of tenders.
16. Complementary information
Complementary technical information may be obtained during working hours at the Divisional Delegation of Public Works Momo. 
                                                                              Done at MBENGWI on the,_______________

    CONTRACTING AUTHORITY

(THE SENIOR DIVISIONAL OFFICER)
Copies:

· ARMP 

· Project Owner 

· Chairperson of MDTB
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AVIS D’APPEL D'OFFRES 

AVIS D’APPEL D’OFFRES NATIONAL OUVERT,PROCEDURE URGENCE 
N° 02/AONO/NW06/ DTB/2024 OF ____/___/2024
POUR LES TRAVAUX DE CONSTRUCTION DE PONT 18M A RIVERIE MUNAM AU PK 0+150 SUR LA ROUTE MUNAM – GUFOM, DEPARTEMENT DE MOMO, REGION DU NORD-OUEST. 
Financement : BUDGET D’INVESTISSEMENT PUBLIC (BIP MINTP)  - EXERCICE 2024
1. Objet de l'Appel d'Offres
Dans le cadre de l’exercice budgétaire 2024, LE Préfet de la Département de MOMO Autorité Contractante lance un Appel d’Offres National Ouvert pour les travaux TRAVAUX DE CONSTRUCTION DE PONT 18M A RIVERIE MUNAM AU PK 0+150 SUR LA ROUTE MUNAM – GUFOM, DEPARTEMENT DE MOMO, REGION DU NORD-OUEST.
2. Consistance des travaux
Les travaux comprennent notamment : 
· Travaux préparatoires

· Terrassement

· Fondations

· Maçonneries en élévations

· Charpente-couverture

· Menuiserie métallique et bois.
· Plomberie et installation sanitaire,
· Electricité

· Peinture

· Travaux extérieurs / drainage 
3. Délais d’exécution
Le délai maximum prévu le Maître d’Ouvrage Délégué pour la réalisation des travaux objet du présent appel d’offres est de six (06) mois calendaires et court ā compter de la date de notification de l’ordre de service de démarrage des travaux.
4. Lotissement: 

Les travaux objet de cet appel d’offres sont en un lot unique et concernent Le TRAVAUX DE CONSTRUCTION DE PONT 18M A RIVERIE MUNAM AU PK 0+150 SUR LA ROUTE MUNAM – GUFOM, DEPARTEMENT DE MOMO, REGION DU NORD-OUEST. 

Coût prévisionnel

Le coût prévisionnel de l’opération à l’issue des études préalables est de 127,221,863 de Francs CFA
5. Participation et origine

La participation à cette consultation est ouverte aux entreprises de droit camerounais ayant une expérience avérée dans le domaine concerné et ayant réalisées des opérations similaires et qui sont en règle sur le plan fiscal.
6. Financement
Les travaux objet du présent appel d'offres sont financés par le Budget d’Investissement Publics du Ministère de l’Agriculture et du Développement Rural de l’exercice 2024  sur  la ligne ligne d’imputation budgétaire N° 36 125 03 58363300093 523411
 Cautionnement de soumission
Chaque soumissionnaire doit joindre à ses pièces administratives, une caution de soumission établie par une banque de premier ordre agréée par le Ministère chargé des finances et dont la liste figure dans la pièce12 du DAO, d’un montant de 2,544,437 FCFA et valable pendant trente (30) jours au-delà de la date de validité des offres. Conformement ā article 90 (9) du code des Marchés Publics (Decree No. 2018/366 du 20 June 2018), des chèques certifiés et cheques-banques sont admis ā la place du cautionnement de soumission.

7. Consultation du Dossier d'Appel d'Offres
Le Dossier d’Appel d’Offres peut être consulté et obtenu aux heures ouvrables au secrétariat de la Préfecture de MBENGWI  Telephone N0 (237) _____________________
, dès publication du présent avis. 

8. Acquisition du Dossier d'Appel d'Offres
Le dossier d'Appel d'Offres peut être obtenu aux heures ouvrables au Secrétariat de la Préfecture de MBENGWI Tél. : N0 (237) ________________, dès publication du présent avis, sous présentation d’une quittance de versement au Trésor Public de la somme non remboursable de cent vingt mille (120,000) F CFA de frais d’acquisition du Dossier 
9. Remise des offres
Chaque offre rédigée en français ou en anglais en sept (07) exemplaires dont un (01) original et (06) copies marquées comme telles, devra parvenir contre récépissé à la Secrétariat de la Préfecture de MBENGWI sis à MBENGWI au plus tard   le ___/____/2024 à 10 heures locale et devra  porter la mention suivante :

A MONSIEUR LE MAITRE D’OUVRAGE DELEGUE (AUTORITE CONTRACTANTE)
N° ____/AONO/NW06/DTB/2024 OF ____/___/2024
Pour le TRAVAUX DE CONSTRUCTION DE PONT 18M A RIVERIE MUNAM AU PK 0+150 SUR LA ROUTE MUNAM – GUFOM, DEPARTEMENT DE MOMO, REGION DU NORD-OUEST. 
«A N’OUVRIR QU’EN SEANCE DE DEPOUILLEMENT»

10. Recevabilité des offres
Sous peine de rejet, les pièces du dossier administratif requises doivent être produites en originaux ou en copies certifiées conformes par le service émetteur ou une autorité administrative (Préfet, Sous-préfet,), conformément aux stipulations du Règlement Particulier de l’Appel d’Offres.
La date limite de validité des pièces administratives susvisées doit être postérieure à celle de lancement de la consultation (date de signature de l’Avis d’Appel d’Offres).
Toute offre incomplète conformément aux prescriptions du Dossier d'Appel d'Offres sera déclarée irrecevable. L'absence de la caution de soumission délivrée par une banque de premier ordre agréée par le Ministère chargé des Finances entrainera un rejet séance tenante de l’ouverture des plis.

11. Ouverture des plis
L’ouverture des plis se fera en un seul temps. L’ouverture des pièces administratives et des offres techniques et financières aura lieu le ___/___/ 2024 à 11 heures précises, dans la salle de conférences de la Préfecture de MBENGWI, par la Commission Départemental de Passation de Marchés de la Département de MOMOsiégeant en présence des soumissionnaires ou de leurs représentants dûment mandatés et ayant une parfaite connaissance de leurs offres.

12. Critères d’évaluation
Les offres seront évaluées selon les principaux critères suivants :
A - Critères éliminatoires
Il s'agit notamment:
PENDANT LA SEANCE D’OUVERTURE DES OFFRES

1. Absence de caution de soumission(from bank only);
2. Absence d’une quittance de versement au Trésor Public Momo
3. Non Reference de l’entreprise dans les travaux similaires au montant ≥ 50,000,000FCFA a departementale de la Momo;
4. Délai d’exécution supérieur à celui prescrit (supérieur à trois mois) ;
5. Fausses déclarations ou pièces falsifiées;
6. Offre dont l’enveloppe extérieure  porte des mentions  permettant de reconnaître le Soumissionnaire;
7. Offres financière incomplète,
8. Le changement d’une unité ou d’une quantité du DAO dans l’offre financière ;
9. Suspendue par MINMAP or ARMP ;
N.B. En cas d’absence ou de non-conformité d’une pièce du dossier administratif lors de l’ouverture des plis, un délai de quarante-huit (48) heures est accordé aux soumissionnaires concernés pour remplacer la pièce en question. Passé ce délai, la pièce ne sera plus acceptée et l’offre ne sera éliminée que lors de l’évaluation des of en sous-commission d’analyse. 
B - Critères essentiels
Les critères relatifs à la qualification des candidats porteront à titre indicatif sur:

1. Présentation générale de l’offre ;

2.  Capacité financière; 

3. References de l’entreprise dans les travaux similaires;

4. Qualité des ressources humaines;  

5. Methodologie d’execution des travaux;

6. Mesures de securité envisagées pour l’éxecution des travaux;

7. Moyens materiels de l’entreprise;

8. Attestation et rapport de visite du site;

9. Cahier des Clauses Techniques Particulières paraphé ā chaque page et signé ā la derniere page;

10. Cahier des Clauses Administratives Particulières paraphé ā chaque page signé ā la derniere page;

Les critères essentiels sont soumis à des minima dont le détail est donné dans le Règlement Particulier de l’Appel d’Offres (RPAO).

13. Attribution
Cette évaluation se fera de manière purement binaire dont des positifs (oui) ou négatfs (non) et dont le minimum des « oui » acceptable est d’au moins 75% de l’ensemble des critères essentiels pris en compte.

Le marché sera attribué au soumissionnaire qui aura proposé l’offre la moins disante, conforme pour l’essentiel aux prescriptions du Dossier d’Appel d’Offres, ayant satisfait à 100% des critères éliminatoires et au moins 75% des critères essentiels.
14. Durée de validité des offres
Les soumissionnaires restent engagés par leur offre pendant 60 jours à partir de la date limite fixée pour la remise des offres.
15. Renseignements complémentaires
Les renseignements complémentaires d’ordre technique peuvent être obtenus auprès de la DDMINTP Momo
                                                                             Fait à  MBENGWI,  le_________________

                                                                                                                             AUTORITE CONTRACTANTE

Copies                                                                                                                           (Préfet de Momo)
· ARMP;
· Maître d’Ouvrage 
· Présidents CDPM/KM;
· Affichage.
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GENERAL RULES OF THE INVITATION TO TENDER

A. General

Article 1: Scope of the tender

1.1 The Contracting Authority as defined in the Special Regulations of the invitation to tender hereby launches an invitation to tender for the construction of the works described in the Tender File and briefly described in the Special Regulations.

1.2 The bidder retained or the preferred bidder must complete the works within the time- limit indicated in the Special Regulations and which time-limit runs from the date of notification of the Administrative Order.

1.2 In this Tender File, the term “day” means a calendar day.

Article 2: Financing

The source of financing of the works forming the subject of this invitation to tender shall be specified in the Special Regulations.

Article 3: Fraud and corruption

3.1 The Contracting Authority requires of bidders and contractors the strict respect of rules of professional ethics during the award and execution of public contracts. By virtue of this principle:
a)  The following definitions shall be admitted:

i) Shall be guilty of “corruption” whoever offers, gives, requests or accepts any advantage in view of influencing the action of a public official during the award or execution of a contract;

ii)   Is involved in “fraudulent manoeuvres” whoever deforms or distorts facts in order to influence the award or execution of a contract;

iii)   “Collusive practices” shall mean any form of agreement between two or among several bidders (whether the Contracting Authority is aware or not) aimed at artificially maintaining the prices of bids at levels not corresponding to those resulting from competition;

iv)   “Coercive practices” shall mean any form of harm against persons or their property or threats against them in order to influence their action during the award or execution of a contract.

b) Any proposed award shall be rejected if it is proved that the proposed preferred bidder is directly or through an intermediary, guilty of corruption or is involved in fraudulent manoeuvres, collusive or coercive practices for the award of this contract. 

3.2     The Minister Delegate at the Presidency in charge of public contracts may, as a precaution, take a decision of exclusion from bidding for a period not exceeding two(2) years against any bidder found guilty of influence peddling, of conflicts of interest, insider trading, fraud, corruption or production of non-genuine documents in the bid, without prejudice to criminal proceedings that may be brought against him
Article 4: Candidates allowed to compete

    4.1 If the invitation to tender is restricted, consultation is addressed to all candidates retained after a pre-qualification procedure.

    4.2 Generally, the invitation to tender is addressed to all entrepreneurs, subject to the following provisions:

(a) a bidder (including all members of a group of enterprises and all sub-contractors to the bidder), in accordance with the funding agreement.

(b) a bidder (including all members of a group of enterprises and all sub-contractors to the bidder) must not be in a situation of conflict of interest, subject to disqualification. A bidder shall be judged to be in a situation of conflict of interest if he:

i) is or was associated in the past with an enterprise (or a subsidiary of this enterprise) which provided consultancy services for the conception, preparation of specifications and other documents used within the scope of contracts awarded for this invitation to tender; or 

ii) presents more than one bid within the context of invitation to tender, except authorised variants according to article 17, where need be; meanwhile, this does not prevent the participation of sub-contractors in more than one bid.

iii) The Contracting Authority or Project Owner has financial interests in the capital in a way as to compromise the transparency of the procedures of award of public contracts.

         (c)   The bidder must not have been excluded from bidding for public contracts.

         (d)  A Cameroonian public enterprise may participate in the consultation if it can demonstrate that it is (i) legally and financially autonomous, (ii) managed according to commercial laws and (iii) not under the direct supervisory authority of the Contracting Authority or Project Owner. 

Article 5: Building materials, materials, supplies, equipment and authorised services

5.1 Building materials, the contractor’s materials, supplies, equipment and services forming the subject of this contract must originate from countries meeting the criteria of origin defined in the Special Regulations of the invitation to tender and all expenditure done within the context of the contract shall be limited to the said building materials, materials, supplies, equipment and services.

5.2  Within the meaning of this 5.1 above, the term “originate” shall designate the place where the goods are extracted, cultivated, produced, manufactured  and from where the services originate.
Article 6: Qualification of bidder

    6.1   As an integral part of their bid, bidders must:

(a) submit a power of attorney making the signatory of the bid bound by the bid; and

        (b)  provide all information (complete or update information included in their request for pre-qualification which may have changed in the case where the candidates took part in pre-qualification) requested of bidders in the Special Regulations of the invitation to tender, in order to establish their qualification to execute the contract.

Where necessary, bidders should provide information relating to the following points:

            (i)  The production of certified balance sheets and recent turnovers;

         (ii)  Access to a line of credit or availability of other financial resources;

         (iii)  Orders acquired and contracts awarded;

(iv)  Pending litigations; 

         (v)  Availability of indispensable equipment.

     6.2   Bids presented by two or more associated undertakings (joint-contracting) must satisfy the following conditions:

(a) The bid must include all the information listed in article 6(1) above. The Special Regulations must indicate the information to be furnished by the group and that to be furnished by each member of the group;

(b) The bid and the contract must be signed in a way that is binding on all members of the group;

(c) The nature of the group (joint or several) must be specified  in the Special Regulations and justified with the production of a joint venture agreement in due form;

(d) The member of the group designated as the representative will represent all the undertakings vis à vis the Project Owner and Contracting Authority with regard to the execution of the Contract;

(e)  In case of joint co-contracting, the co-contractors shall share the sums which are paid by the Project Owner into a single account. On the other hand, each undertaking is paid into its own account by the Project Owner where it is joint co-contracting.

     6.3 Bidders must equally present sufficiently detailed proposals to demonstrate that they comply with the technical specifications and execution time-limits set in the Special Regulations of the invitation to tender.

     6.4 Bidders requesting to benefit from the margin of preference must furnish all the necessary information to prove that they satisfy the eligibility criteria set in article 33 of the General Regulations of the invitation to tender.

Article 7: Visit of works site

7.1 The bidder is advised to visit and inspect the site and its environs and obtain by himself and under his own responsibility, all the information which may be necessary for the preparation of the bid and the execution of the works. The related cost of the visit of the site shall be borne by the bidder.

    7.2 The Project Owner shall authorise the bidder and his employees or agents to enter the premises and the land for the said visit but only on the express condition that the bidder, his employees and agents free the Project Owner, his employees and agents of any responsibility that may ensue and indemnify them if necessary and that they shall remain responsible for any deadly or corporal accident, loss or material damages, costs and fees incurred from this visit.

     7.3 The Project Owner may organise a visit of the site of the works during the preparatory meeting to establishing the bids mentioned in article 19 of the General Regulations of the invitation to tender.

B. Tender File

Article 8: Content of Tender File

   8.1 The Tender File describes the works forming the subject of the contract, sets the consultation procedure of contractors and specifies the terms of the contract.  Besides the addendum (addenda) published in accordance with article 10 of the General Regulations of the invitation to tender, it includes the following documents:


Document No. 1. The tender notice;


Document No. 2. The General Regulations of the invitation to tender;


Document No. 3. The Special Regulations of the invitation to tender;


Document No. 4. The Special Administrative Conditions;


Document No. 5. The Special Technical Conditions;


Document No. 6. The schedule of unit prices;


Document No. 7. The bill of quantities and estimates;


Document No. 8. The sub details of unit prices;


Document No. 9. Model documents of the contract:

a. The execution schedule;

b. Model of forms presenting the equipment, personnel and references;

c. Model bidding letter;

d. Model bid bond;

e. Model final bond;

f. Model of bond of start-off advance;

g. Model of guarantee in replacement of the retention fund;

h. Model contract;

Document No. 10. Models to be used by bidders; 

a. Model contract;

         Document No. 11. Justifications of preliminary studies; to be filled by the Project Owner or Delegated Project Owner;

         Document No. 12. List of first grade banking establishments or financial institutions approved by the Minister in charge of Finance authorised to issue bonds for public contracts to be inserted by the Contracting Authority.

8.2 The bidder must examine all the regulations, forms, conditions and specifications contained in the Tender File. It is up to him to furnish all the information requested and prepare a bid in compliance with all aspects of the said file. 

Article 9: Clarifications on the Tender File and complaints

9.1 Any bidder who wants to obtain clarifications on the Tender File may request them from the Contracting Authority in writing or by electronic mail (fax or e-mail) at the Contracting Authority’s address indicated in the Special Regulations of the invitation to tender and send a copy to the Project Owner. The Contracting Authority replies in writing to any request for clarification received at least fourteen (14) days prior to the deadline for the submission of bids.

 A copy of the Contracting Authority’s response, indicating the question posed but not mentioning the author, is addressed to all bidders who bought the Tender File.

9.2 Between the publication of the tender notice including the pre-qualification phase of candidates and the opening of bids, any bidder who feels aggrieved in the public contracts award procedure may lodge a complaint to the Minister in charge of Public Contracts.

9.3 A copy of the complaint should be addressed to the Contracting Authority and to the body in charge of the regulation of public contracts and the chairperson of the Tenders Board.

9.4 The Contracting Authority has five (5) days to react. A copy of the reaction shall be forwarded to MINMAP and the body in charge of the regulation of public contracts.

Article 10:  Amendment of the Tender File

10.1The Contracting Authority may at any moment, prior to the deadline for the submission of  bids and for any reason, be it at his initiative or in reply to a request for clarification formulated by a bidder, amend the Tender File by publishing an addendum.

10.2 Any published addendum shall be an integral part of the Tender File, in accordance with article 8.1 of the General Regulations of the invitation to tender and must be communicated in writing or made known by a traceable means to all bidders who bought the Tender File.

10.3 In order to give bidders sufficient time to take account of the addendum in the preparation of their bids, the Contracting Authority may postpone as is necessary, the deadline for the submission of bids, in accordance with provisions of article 22 of the General Regulations of the invitation to tender.

C   Preparation of bids

Article 11: Tender costs

The candidate shall bear the costs related to the preparation and presentation of his bid and the Contracting Authority and the Project Owner shall in no case be responsible for these costs nor pay for them whatever the evolution or outcome of the invitation to tender procedure. 

Article 12: Language of bid

The bid as well as any correspondence and any document exchanged between the bidder and the Contracting Authority shall be written in English or French. Complementary documents and the forms provided by the bidder may be written in another language on condition that a precise translation into either English or French of the passages concerning the bid is included; in which case for reasons of interpretation, the translation shall be considered to be authentic.

Article 13: Constituent documents of the bid

 13.1 The bid presented by the bidder shall include the documents detailed in the Special Regulations of the invitation to tender, duly filled and put together in three volumes:

a. Volume 1:  Administrative file

It includes:

i) all documents attesting that the bidder:

· has subscribed to all declarations provided for by the laws and regulations in force;

· paid all taxes, duties, contributions, fees or deductions of whatever nature;

· is not winding up or bankrupt;

· is not the subject of an exclusion order or forfeiture provided for by the law in force; 

           ii)   The bid bond established in accordance with the provisions of article 17 of the General Regulations of the invitation to tender;

           iii)  the written confirmation empowering the signatory of the bid  to commit the bidder, in accordance with the provisions of article 6(1) the General Regulations of invitation to tender.

b. Volume 2: Technical bid


b.1 Information on qualifications


The Special Regulations list the documents to be furnished by bidders to justify the qualification criteria mentioned in article 6(1) of the Special Regulations of the invitation to tender.


b.2 Methodology 


The Special Conditions of the invitation to tender specifies the constituent elements of the technical bid of the bidders especially: a methodological statement on an analysis of the works and specifying the organisation and programme which the bidder intends to put in place or use to execute the works (installations, schedule, Quality Assurance Plan (QAP), sub-contracting, attestation of visit of the site, where necessary, etc).


b.3 Proof of acceptance of conditions of the contract

The bidder shall submit duly initialled copies of the administrative and technical documents relating to the contract, namely:

1. The Special Administrative Conditions (SAC);

2. The Special Technical Conditions (STC).


b.4 Commentaries (optional) 


A commentary on the technical choices of the project and possible proposals.

c. Volume 3: Financial bid

The Special Regulations specify the elements that will help in justifying the cost of the works, namely:

1. The signed and dated original bid prepared according to the attached model, stamped at the prevailing rate;

2. The  duly filled Unit Price Schedule;

3. The duly filled detailed estimates;

4. The sub-details of prices and/or breakdown of all-in prices;

5. The projected schedule of payments, where need be.

In this regard, the bidders will use the documents and models provided in the Tender File, subject to the provisions of article 17(2) of the General Regulations of the invitation to tender concerning the other possible forms of guarantees.

      13.2    If in accordance with the provisions of the Special Regulations of the invitation to tender, the bidders present bids for several lots of the same invitation to tender, they could indicate rebates offered in case of award of more than one lot.

Article 14:  Bid price 

     14.1    Except otherwise stated in the Tender File, the amount of the contract shall cover all the works described in article 1.1 of the General Regulations of the invitation to tender, on the basis of the price schedule and the detailed bill of quantities and estimates presented by the bidder .

     14.2   The bidder shall fill the unit prices and totals of all items on the schedule and bill of quantities and estimates.

 14.3   Subject to contrary provisions provided for in the Special Regulations and in the Special Administrative Conditions, all dues, taxes and fees payable by the bidder on grounds of the contract or on any other ground, thirty (30) days prior to the submission of the bids, shall be included in the prices and in the total amount of the bid presented by the bidder.

14.4 If a price revision/updating clause is provided for in the contract, the date of establishment of the initial price, as well as the price revision/updating conditions for the said price must be specified. This is with the understanding that any contract of duration less than one (1) year shall not be subject to price revision.

      14.5 All unit prices must be justified by sub-details established in accordance with the structure proposed in document 8 of the Tender File.

Article 15: Currency of bid and payment

       15.1 In case of international invitations to tender, the currencies of the bid shall follow the provisions of either Option A or Option B below, the applicable option being that retained in the Special Regulations of the invitation to tender.


15.2 Option A:The amount of the bid shall be entirely made in the national currency.


The amount of the bid, unit prices of the price schedule and the prices of the bill of quantities and estimates are completely made in CFA francs in the following manner:

a) Prices shall be entirely drawn in the national currency. The bidder who intends to commit expenditures in other currencies for the execution of the works shall indicate in the annex to the bid the percentage(s) of the amount of the bid necessary to cover the needs in foreign currencies, without exceeding the maximum of the three currencies of member countries of the funding institution of the contract.

b) The exchange rates used by the bidder to convert his bid into the national currency shall be specified by the bidder in an annex to the bid in compliance with the specifications of the Special Regulations. These rates shall be applied for any payment within the framework of the contract so that the retained bidder does not bear any change in the exchange rate.


15.3 Option B:The amount of the bid shall be directly made in the national and foreign currency at the rates fixed in the Special Regulations.

The bidder shall draw the unit prices of the price schedule and the prices of the bill of quantities and estimates in the following manner:

(a) The prices of inputs necessary for the works which the bidder intends to procure in the Contracting Authority’s country shall be in currency of the Contracting Authority’s country specified in the Special Regulations and called “national currency”;

(a) The prices of inputs necessary for works which bidder intends to procure out of the Contracting Authority’s country shall be in the currency of the country of origin of the bidder or of the currency of an eligible member country widely used in international trade.

15.4 The Contracting Authority may request the bidders to explain the needs in national and foreign currencies and to justify that the amounts included in the unit and total prices and indicated in annex to the bids are reasonable; to this end, a detailed statement of their needs in foreign currencies shall be furnished by the bidder.

15.5 During the execution of the works, most of the foreign currency to be paid as part of contract may be revised by mutual agreement between the Contracting Authority and the entrepreneur in a way as take account of any modification in the foreign currency needs within the context of the contract.

Article 16: Validity of bids

16.1 Bids must remain valid during the period stated in the Special Regulations from the date of submission of the bids fixed by the Contracting Authority, in application of article 22 of the Special Regulations. A bid valid for a shorter period shall be rejected by the Contracting Authority as not being in compliance.

16.2 Under exceptional circumstances, the Contracting Authority may seek the approval of bidders to extend the validity time-limit.  The request and the responses that will be given shall be in writing (or by fax). The validity of the bid bond provided for in article 17 of the General Regulations shall equally be extended for a corresponding duration. A bidder may refuse to extend the validity of his bid without losing his bid bond. A bidder who consents to an extension shall not be asked to modify his bid nor shall he be authorised to do so.

16.3 Where the contract does not include a price revision clause and that the period of validity of bids is extended by more than sixty (60) days, the amounts payable to the bidder retained shall be updated by application of the related formula featuring in the request for extension that the Contracting Authority addressed to bidders.

The updating period shall run from the date of overrun of sixty (60) days to the date of notification of the contract or the Administrative Order for start of execution of works by the retained bidder, as specified in the Special Administrative Conditions. The effect of updating shall not be taken into account for purposes of evaluation of bids.

Article 17: Bid bond

17.1   In application of article 13 of the General Regulations, the bidder shall furnish a bid bond of the amount specified in the Special Regulations and which bid bond shall be a full part of his bid.

17.2 The bid bond must conform to the model presented in the Tender File; other models may be authorised subject to the prior approval of the Contracting Authority. The bid bond will remain valid for thirty (30) days beyond the original date set for the validity of bids or any other validity  time-limit  requested by the Contracting Authority and accepted by the bidder, in accordance with the provisions of article 16 (2) of the General Regulations.

17.3   Any bid without an acceptable bid bond shall be rejected by the Tenders Board as not in conformity.  The bid bond of associated enterprises must be established in the name of the group submitting the bid and mention each member of the associated grouping.

17.4    The bid bonds of bidders who are not retained shall be returned within fifteen (15) days after publication of the award result.

17.5   The bid bond of the successful bidder shall be released as soon as the latter would have signed the contract and furnished the required final bond.

17.6    The bid bond may be seized:

(a) if the bidder withdraws his bid during the period of validity; 

(b)  if the retained bidder:

i)   DISPLAYNFC \l 0 fails in his obligation to register the contract in application of  article 38 of the General Regulations;

ii) fails in his obligation to furnish the required final bond in application of article 38 of the General Regulations;

iii) Refuses to receive notification of the Administrative Order to commence execution.

Article 18: Varying proposals of bidders

18.1 Where the works can be executed within variable deadlines, the Special Regulations shall specify these deadlines and shall indicate the method retained for the evaluation of the completion deadline proposed by the bidder within the specified deadlines. Bids that propose deadlines beyond those specified shall be considered as not being in conformity.

18.2 Except in the case mentioned in article 18(3) below, bidders wishing to offer technical variants must first assess the basic solution of the Contracting Authority as described in the Tender File and furnish in addition all the information which the Contracting Authority needs for a complete evaluation of the proposed variant, including the plans, calculations, technical specifications, sub-details of prices and proposed construction methods and all other useful information. If necessary, the Contracting Authority will examine only the technical variants of the bidder whose bid is in compliance with the basic solution has been evaluated as the lowest bid.

18.3 When according to the Special Regulations the bidders are authorised to directly submit the technical variants for certain parts of the works, these parts of the works must be described in the technical specifications. Such variants shall be evaluated on their own merit in accordance with the provisions of article 31(2) (g) of the General Regulations.

Article 19: Preparatory meeting to the establishment of bids

19.1   Except otherwise stipulated in the Special Regulations, a bidder may be invited to take part in a preparatory meeting which will hold at the date and place indicated in the Special Regulations.

19.2 The subject of the preparatory meeting shall be to furnish clarifications and answer any questions which may be raised at this stage.

19.3    As much as possible, the bidder is requested to submit any question in a way as to reach the Contracting Authority at least one week before the meeting The Contracting Authority may not reply to questions received too late. In this case, the questions and answers shall be transmitted according to the methods set in article 19(4) below.  

19.4    The minutes of the meeting, including the text of the questions asked and the replies given, including questions prepared after the meeting, shall be forwarded immediately to everyone who bought the Tender File. Any modification of documents of the Tender File listed in article 8 of the General Regulations which may prove to be necessary at the end of the preparatory meeting shall be done by the Contracting Authority by publishing an addendum in accordance with the provisions of article 10 of the General Regulations and not through the minutes of the preparatory meeting.

19.5 The fact that a bidder does not attend a preparatory meeting for the establishment of bids shall not be a reason for disqualification.

Article 20: Form and signature of bid

20.1 The bidder shall prepare an original of the constituent documents described in article 13 of the General Regulations in a volume clearly indicated “ORIGINAL”. In addition, the bidder shall submit the number required in the General Regulations, bearing “COPY”. In case of discrepancy, the original shall be considered as authentic.

20.2  The original and copies of the bid must be typed or written in indelible ink (photocopies shall be accepted in the case of copies) and shall be signed by the person(s) duly empowered to sign on behalf of the bidder, in accordance with article 6(1a) or 6(2c) of the General Regulations, as the case may be. All the pages of the bid containing alterations or changes must be initialled by the signatory (ies) of the bid.

20.3 The bid shall be bearing no modification, suppression or alteration unless such corrections are initialled by the signatory (ies) of the bid.

D.  SUBMISSION OF BIDS

Article 21:  Sealing and marking of bids

21.1 The bidder shall seal the original and each copy of the bid in separate envelopes (internal envelopes) by marking on these envelopes “ORIGINAL” and “COPY”, as the case may be. The envelopes shall then be placed in another envelope which will equally be sealed but which will not give any indication regarding the identity of the bidder.

21.2 The external and internal envelopes:

         a) should be addressed to the Contracting Authority at the address indicated in the Special Regulations;

b) should bear the name and identification number of the project as indicated in the Special Regulations  and  bear the inscription “TO BE OPENED ONLY DURING THE BID-OPENING SESSION” as specified in the Special Regulations.

21.3 The internal envelopes should equally carry the name and address of the bidder in a way as to enable the Contracting Authority return the sealed bid if it is late in accordance with article 23 and 24 of the General Regulations.    

21.4 If the external envelope is not sealed and marked as indicated in paragraphs 21(1) and 21(2) above, the Contracting Authority shall not be responsible if the bid is misplaced or opened prematurely. 

Article 22: Date and time-limit for submission of bids 

22.1 The bids must be received by the Contracting Authority at the address specified in article 21(2) of the Special Regulations not later than the date and time stated in the Special Regulations.

22.2 The Contracting Authority may, at his discretion, postpone the deadline set for the submission of the bids by publishing an addendum in accordance with the provisions of article 10 of the General Regulations.  In this case, all the rights and obligations of the Contracting Authority and bidders previously governed by the initial date will henceforth be governed by the new date.

Article 23: Late bids

Any bid received by the Contracting Authority beyond the deadline for the submission of bids in accordance with article 22 of the General Regulations shall be declared late and consequently rejected.

Article 24: Modification, substitution and withdrawal of bids

24.1 A bidder may modify or withdraw his bid after submitting it, on condition that the written notification of the modification or withdrawal is received by the Contracting Authority prior to the end of the time-limit prescribed for the submission of the bids. The said notification must be signed by an authorised representative in application of article 20(2) of the General Regulations. The modification or the corresponding replacement bid must be attached to the written notification. As the case may be, the envelopes must bear the inscription “WITHDRAWAL”, and “REPLACEMENT BID” or “MODIFICATION”.
24.2 Notification of modification, replacement or withdrawal of the bid by the bidder should be prepared, sealed, marked and forwarded in accordance with the provisions of article 21 of the General Regulations. Withdrawal may equally be notified by telex but should in this case be confirmed by a duly signed written notification whose date, post mark being authentic, shall not be posterior to the time-limit set for the submission of bids.

24.3 In application of article 24(1), bids being requested to be withdrawn by bidders shall be returned to them unopened.

24.4 No bid may be withdrawn during the interval between the submission of bids and the expiry of the validity of bids specified by the model tender. The withdrawal of a bid by a bidder during this interval may lead to the confiscation of the bid bond in accordance with the provisions of article 17(6) of the General Regulations.

E.  Opening of envelopes and evaluation of bids

Article 25: Opening of envelopes and petitions

25.1 The MOMO Divisional  Tenders Board shall open the envelopes in single phase and in the presence of the representatives of bidders who wish to attend at the date, time and address specified in the Special Regulations. Representatives of bidders shall sign a register attesting to their presence.

25.2 Firstly, envelopes marked “withdrawal” shall be opened and the contents announced to the hearing of everyone, while the envelope containing the corresponding bid shall be returned to the bidder unopened. Withdrawal shall be allowed only if the corresponding notification contains a valid empowerment of the signatory to request this withdrawal and if this notification is read to the hearing of everyone. Then the envelopes marked “Replacement bid” are opened and announced to the hearing of everyone and the new corresponding bid substituted for the preceding one which will be sent to the bidder concerned unopened. The replacement of the bid shall only be allowed if the corresponding notification contains a valid empowerment of the signatory requesting the replacement and read to the hearing of everyone. Lastly, the envelopes marked “modification” shall be opened and their contents read to the hearing of everyone with the corresponding bid. The modification of the bid shall only be allowed if the corresponding notification contains a valid empowerment of the signatory requesting the modification and read to the hearing of everyone. Only bids which were opened and announced to the hearing of everyone during the opening of bids shall then be evaluated.

25.3 All envelopes shall be opened successively and the name of the bidder announced aloud as well as the possible modification mentioned, the price offered, including any rebates [in case of opening of financial bids] and any variant, where necessary, the existence of a guarantee of the bid if it is required and any other details which the Contracting Authority deems useful to be mentioned. Only rebates and variants of bids announced to the hearing of everyone during the opening of bids shall be submitted for evaluation.

 25.4 Bids (and modifications received in accordance with the provisions of article 24 of the General Regulations) which were not opened and read to the hearing of everyone during the bid-opening session for whatever reason, shall not be submitted for evaluation.

25.5 Bid-opening minutes are recorded on the spot mentioning the admissibility of bids, their administrative regularity, prices, rebates and time-limits as well as the composition of the Evaluation sub-committee. A copy of the said minutes to which is attached the attendance sheet is handed over to all the participants at the end of the session.

25.6 At the end of each bid-opening session, the chairperson of the Tenders Board immediately hands over to the focal point designated by the body in charge of regulation of public contract an initialled copy of the bids presented by bidders.

25.7 In case of petition as provided for by the Public Contracts Code, it should be addressed to the Minister Delegate in charge of Public Contracts with  copies to  the body in charge of the regulation of public contracts, the head of structure to which is attached the Tenders Board concerned. 


It must reach within a maximum deadline of three (3) working days after the opening of bids in the form of a letter to which is obligatorily attached a sheet of the petition form duly signed by the petitioner and possibly by the chairperson of the Tenders Board.


The Independent Observer attaches to his report the sheet that was handed to him, including any related commentaries or observations.

Article 26: Confidential nature of the procedure

26.1 No information relating to the examination, clarification, evaluation and comparison of bids and verification of the qualification of the bidders and the recommendation for the award shall be given to bidders or to any person not concerned with the said procedure as long as the preferred bidder has not been made public, subject to the disqualification of the bid of the bidder and suspension of the authors from all activities in the domain of public contracts. 

26.2 Any attempt by a bidder to influence the Tenders Board or the Evaluation sub-committee of bids or the Contracting Authority in its award decision may lead to the rejection of his bid.

26.3 Notwithstanding the provisions of paragraph 26.2 above, between the opening of bids and the award of the contract, if a bidder wishes to enter into contact with the Contracting Authority for reasons having to with his bid may do so in writing. 

Article 27: Clarifications on the bids and contact with the Contracting Authority

27.1 To ease the examination, evaluation and comparison of bids, the Tenders Board may, if it so desires, request any bidder to give clarifications on his bid. This request for clarification and the response thereto are formulated in writing but no change on the amount or content of the bid is sought, offered or authorised, except it is necessary to confirm the correction of calculation errors discovered by the Evaluation Sub-committee during the evaluation in accordance with the provisions of article 30 of the General Regulations.

27.2 Subject to the provisions of paragraph 1 above, bidders shall not contact members of the Tenders Board and the Evaluation Sub-committee for questions related to their bids, between the opening of envelopes and the award of the contract.

Article 28: Determination of compliance of bids

28.1 The Evaluation sub-committee shall carry out a detailed examination of bids to determine if they are complete, if the required guarantees are furnished, if the documents were correctly signed and if generally the bids are in proper order.

28.2 The Evaluation sub-committee shall determine if the bid is essentially in compliance with the conditions fixed in the Tender File based on the content without recourse to external elements of proof.  

28.3 A bid that complies with the Tender File shall essentially be a bid that respects all the terms, conditions and specifications of the Tender File, without substantial divergence or reservation.  A substantial divergence or reservation is that:

i) which substantially limits the scope, quality or realisation of the works;

ii) which substantially limits, contrary to the Tender File, the rights of the Contracting Authority or his obligations in relation to the contract; 

iii) Whose correction would unjustly affect the competitiveness of the other bidders who presented bids that essentially complied with the Tender File.

28.4   If a bid is essentially not in compliance, it shall be rejected by the competent Tenders Board and shall not subsequently be rendered in compliance.

28.5   The Contracting Authority reserves the right to accept or reject any modification, divergence or reservation. Modifications, divergences, variants and other factors which are beyond the requirements of the Tender File shall not be considered during the evaluation of bids.

Article 29: Qualification of the bidder


  The Evaluation sub-committee shall ensure that the successful bidder retained for having submitted a bid substantially in compliance with the provisions of the Tender File, fulfils the qualification criteria stipulated in article 6 of the Special Regulations. It is essential to avoid any arbitrariness in determining qualification.

Article 30: Correction of errors

30.1 The Evaluation sub-committee shall verify bids considered essentially in compliance with the Tender File to correct the possible calculation errors. The Evaluation sub-committee shall correct the errors in the following manner:

(a) where there is an incoherence between the unit price and the total obtained by multiplying the unit price by the quantity, the unit price being authentic, the total price shall be corrected, unless the Evaluation sub-committee judges that it is a gross error of decimal point in the unit price in which case the total price as presented shall be authentic and the unit price corrected.

(b) if the total obtained by addition or subtraction of the totals is not exact, the sub totals shall be considered authentic and the total corrected.

(c) where there is a difference between the price indicated in letters and in figures, the amount in letters shall be considered authentic, unless the amount is linked to an arithmetical error confirmed by the sub-detail of the said price, in which case the amount in figures shall prevail subject to paragraphs (a) and (b) above.

30.2 The amount featuring in the bid shall be corrected by the Evaluation sub-committee, in accordance with the error correction procedure above and with confirmation by the bidder, the said amount shall be deemed to commit him.

30.3 If the bidder who presented the bid evaluated as the lowest refuses the correction thus carried out, his bid shall be rejected and the bid bond may be seized. 

Article 31: Conversion into a single currency

31.1 To facilitate the evaluation and comparison of bids, the Evaluation sub-committee shall convert the prices of bids expressed in various currencies into those in which the bid is payable in CFA francs. 

31.2 The conversion shall be done using the selling rate fixed by the Bank of Central African States (BEAC) under the conditions defined by the Special Regulations.

Article 32: Evaluation and comparison of financial bids 

32.1   Only bids considered as being in compliance, as per the provisions of article 28 of the General Regulations, shall be evaluated and compared by the Evaluation sub-committee.

32.2 By evaluating the bids, the Evaluation Sub-committee shall determine for each bid the evaluated amount of the bid by rectifying the amount as follows:

a)  By correcting any possible error in accordance with the provisions of article 30.2 of the General Regulations;

b) By excluding projected sums and where necessary provisions for unforeseen occurrences featuring in the bill of quantities and estimates but by adding the amount of works done under State supervision where they are costed in a competitive manner as specified in the Special Regulations.

c)  By converting into a single currency the amount resulting from the rectifications (a) and (b) above, in accordance with the provisions of article 31(2) of the General Regulations;

d) By appropriately adjusting any other modification, divergence or quantifiable reservation on technical or financial basis.

e) By taking into consideration the various execution time-limits proposed by the bidders, if they are authorised by the Special Regulations;

f) If need be, in accordance with the provisions of article 13(2) of the General Regulations and the Special Regulations by applying the rebates offered by the bidder for the award of more than one lot, if this invitation to tender is launched simultaneously for several lots.

g)  If need be, in accordance with the provisions of article 18(3) of the Special Regulations and the Technical Specifications, the proposed technical variants, if they are permitted, shall be evaluated on their own merit and independently of the fact that the bidder offered or not a price for the technical solution specified by the Contracting Authority in the Special Regulations.

32.3 The estimated effect of price revision formulae featuring in the GAC and SAC applied during the period of execution of the contract shall not be considered during the evaluation of bids.

32.4 If the bid judged the lowest bid is considered abnormally low or strongly unbalanced in relation to the estimates of the Project Owner for the works to be executed in this contract, the Tenders Board may, from the sub-details of prices furnished by the bidder for any element or all the elements of the bill of quantities and estimates, verify if these prices are compatible with the construction methods and proposed calendar. In the case where the justifications presented by the bidder are not satisfactory, the Contracting Authority may reject the bid after the technical opinion of the Public Contracts Regulatory Agency.


Article 33: Preference granted national bidders
National contractors shall benefit from a margin of national preference during the evaluation of bids as provided for in the Public Contracts Code.

Article 34: Award 

34.1     The Contracting Authority shall award the contract to the bidder whose bid was judged essentially in compliance with the Tender File and who has the required technical and financial capacities to execute the contract satisfactorily and whose bid was evaluated as the lowest by including, where necessary, proposed rebates

34.2     If, according to article 13(2) of the General Regulations, the invitation to tender comprises several lots, the lowest bid shall be determined by evaluating this contract with other lots to be awarded concurrently, by taking into account the rebates offered by the bidders in the case of more than one lot. 

34.3       Any award of contract shall be made to the bidder fulfilling the technical and financial capacities required resulting from the evaluation criteria and presenting the bid evaluated as the lowest. 

Article 35:  The right by the Contracting Authority to declare an invitation to tender unsuccessful or cancel a procedure 

The Contracting Authority reserves the right to cancel a procedure of invitation to tender after the authorisation of the Minister Delegate at the Presidency in charge of Public Contracts where the bids have been opened or to declare an invitation to tender unsuccessful after the advice of the competent Tenders Board, without any claims being entertained.

Article 36: Notification of award of the contract

               Before the expiry of the validity of the bids set in the Special Regulations, the Contracting Authority shall notify the preferred bidder by telecopy confirmed by registered mail or by any other means that his bid was retained. This letter will indicate the amount the Project Owner will pay the contractor to execute the works and the execution time-limit.

Article 37: Publication of results of award and petitions

37.1 The Contracting Authority shall communicate to any bidder or administration concerned, upon request addressed to it within a maximum deadline of five (5) days after publication of the award results, the Independent Observer’s report as well as the minutes of the award session of the related contract to which shall be attached the evaluation report of the bids.

37.2 The Contracting Authority is bound to communicate the reasons for the rejection of bids of the bidders concerned who so request.

37.3 After publication of the award results, bids that are not withdrawn within fifteen (15) days shall be destroyed, without any claims for compensation being entertained. Only the copy destined for the body in charge of regulation shall be kept.

37.4 In case of petition, it should be addressed to the Public Contracts Authority, with copies to the body in charge of the regulation of public contracts, the Contracting Authority and the chairperson of the Tenders Board concerned.

It must take place within a maximum deadline of five (5) working days after the publication of the results.

Article 38: Signing of the contract

38.1    After publication of the results, the draft contract subscribed by the successful bidder is submitted to the Tenders Board for examination and where applicable, to the Minister in charge of Public Contracts for prior endorsement. 

38.2     The Contracting Authority has a deadline of seven (7) days to sign the contract from the date of reception of the draft contract examined by the competent Tenders Board and subscribed by the successful bidder and where applicable, the endorsement of the Minister in charge of Public Contracts.

38.3    The contract must be notified to the successful bidder within five (5) days of its date of signature.

Article 39:  Final Bond 

 39.1    Within twenty (20) days of the notification by the Contracting Authority, the contractor shall furnish the Project Owner with a final bond, to guarantee the complete execution of the works. 

39.2    The bond whose rate varies between 2 and 5 percent of the amount of the contract inclusive of all taxes, may be replaced by a guarantee from a banking establishment approved according to the instruments in force with the Project Owner  as beneficiary or by a joint or several guarantee.

39.3   Small and medium-sized enterprises (SME) constituted of national capital and managed by nationals may, in lieu of the guarantee, provide a statutory lien or a bond issued by a banking establishment or first rate financial institution approved in accordance with the instruments in force.

39.4     Failure to produce the final bond within the prescribed time limit shall likely cause the termination of the contract under the terms laid down in the General Administrative Conditions.     
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Special regulations of the invitation to tender
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.
	References of the General regulations
	General

	1.1
	Definition of works:
THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION 
Name and address of the Contracting Authority: The Senior Divisional Officer Momo
Reference of Invitation to tender, emergency procedure: N° 02/ONIT/NW06/DTB/2024 OF ____/___/2024

	1.2
	Execution deadline: six (06) calendar months


	2.1
	Source of financing
Works which form the subject of this invitation to tender are financed by the 2024 Public Investment Budget of the Ministry of Public Works.


	4.1
	List of pre-qualified candidates, not applicable


	5.1
	Origin of building materials, equipment, materials, supplies and equipment: The materials will generally be from natural sources in Cameroon.


6.1 Evaluation criteria

The bids shall be evaluated according to the main criteria as follows:

A. Eliminatory criteria

1. Absence bid bond(from bank only) in the administrative file; 

2. No purchase receipt Momo Divisional Tresury

3. No reference ≥ 50,000,000frs in this domian(Momo Division)

4. Deadline for delivery higher than prescribed; 

5. False declaration or falsified documents; 

6. A bid with the external envelope carrying a sign or mark leading to the identification of the bidder; 

7. Incomplete financial file; 

8. Change of quantity or unit; 

9. Suspended by MINMAP or ARMP in 2024. 

10. Non respect of 75%of essential criteria;

During the opening session of the bids if a document of the administrative bid is absent or noncompliant, the bidder will be given fourty eight (48) hours to produce or replace said document else will be eliminated during the evaluation of the bids. No such document will be accepted after this deadline.

B. Essential criteria

1. General presentation of the tender files;

2.  Financial capacity; 

3. References of the company in  similar achievements;

4. Quality of the personnel;  

5. Technical organization of the works;

6. Safety measures on the site;
7. Logistics;

8. Attestation and report of site visit;
9. Special Technical Clauses initialed in all the pages;

10. Special Administrative Clauses completed and initialed in all the pages.

This evaluation will be done in a purely a purely binary method with a positive (yes) or negative (no) with an acceptable minimum of 75% of the essential criteria taken into account.

The contract will be awarded to the bidder who would have proposed the offer with the lowest reasonable amount, in conformity with the regulations of the Tender Documents and having satisfied to 100% of the eliminatory criteria and at least 75%of the essential criteria.

ARTICLE 6 : Language of the bids:

            The offer like any correspondence and all documents concerning the tender, exchanged between the renderer and the Project Owner will be written in French or English. The complementary documents and the printed papers form provided by the Bidder can be written in another language in condition of being accompanied by a precise translation in French or English; in which case and for purposes of interpretation of the offer, the translation will be taken. 

PRESENTATION OF THE TENDER.

The bids prepared in English or French and in seven (07) copies with one (01) original and six  (06) copies marked thus, shall be presented in three (03) volumes as follows: 

A)
Administrative Documents

B)
Technical Documents

C) Financial Documents

5.1
External envelope. 


Each bidder shall seal these three (03) envelopes (A, B and C) in one common envelope on which shall be written. TO THE DELEGATED  CONTRACTING AUTHORITY
“OPEN NATIONAL INVITATION TO TENDER, EMERGENCY PROCEDURE  N° 02/ONIT/NWO6/DTB/SEFA/2024 OF ____/___/2024
FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION
“To be opened only during the bid-opening session”
N.B:
The external envelope should not carry any mark or sign that can lead to the identification of the bidder. 

8.2
Internal envelopes

Three (03) internal envelopes must be sealed in an external envelope. 

The   first internal envelope shall be labeled; 

<<ENVELOPE A: ADMINISTRATIVE DOCUMENTS>> and shall contain the administrative documents of the enterprise.  These documents shall be original or copies certified by competent authorities   not more than three months.

ADMINISTRATIVE DOCUMENTS.

	DOCUMENT N°
	DESCRIPTION

	A.1
	Certified Copy of the Business Registration, not more than three months old.

	A.2
	Declaration of intention to tender stamped with the tariff in force (written by the bidder).

	A.3
	Certificate of non-bankruptcy established by the Court of 1st instance or the Chamber of Commerce, Industry and Trade of the place of residence of the bidder, not more than three (03) months.

	A.4
	Attestation of bank account of the bidder, issued by a first rate-bank approved by the Ministry in charge of Finance or by a foreign bank the first order not more than three months. 

	A.5
	Purchase receipt of tender file issued by public treasury

	A.6
	A bid bond of 2,544,437 FCFA (Two million five hundred and forty four thousand four hundred and thirty seven FCFA), certified cheque or bank cheque issued by a first rate-bank approved by the Ministry in charge of Finance in conformity with COBAC conditions

	A.7
	An attestation of non-exclusion from Public Contracts issued by the Public contract Regulatory 
Board (ARMP)

	A.8
	An Attestation of the National Social Insurance Fund stating that the bidder has met all his obligations vis a vis the Fund; the attestation should be less than three months old.

	A.9
	Attestation of fiscal confirmity

	A.10
	Certified Copy of a valid taxpayers card, delivered by the chief of center of Taxes. 

	A.11
	Plan and attestation of location of the Company


The absence or the non-conformity of the one of these documents will result to the elimination 
of the offer either during the opening session of the bids (absence of bid bond) or during the evaluation
The second Internal Envelope shall be labeled <<ENVELOPE B:  TECHNICAL DOCUMENT>> and shall contain the following: 

	B.1
	 General presentation of the tender files

	· Document spirally bound
· Neatness and clarity of documents
· Page numbering
· Table of content page
· Colour sheets separation
· Presentation of documents in the order given in this tender
	
	

	B.2
	LIST OF REFERENCES OF THE ENTERPRISE IN SIMILAR JOBS 

	B.2.1
	List of references of the enterprise in similar jobs justified by certified true copies of contracts (first and last pages) and minutes of reception or attestation of clearances of works executed. Minimum of two contracts realized in the domain of building construction over the past five years 

	
	1st Reference ≥ 50,000,000frs
	
	

	
	2nd  Reference≥ 20,000,000frs
	
	

	B.3
	QUALIFICATION AND EXPERIENCE OF SUPERVISORY STAFF 

	B.3.1
	01 works supervisor (at least Degree or equivalent certificate)

	.
.
.
	Qualification of the works supervisor: (Senior Technician certificate in Civil or Rural Engineering (BAC +3)
	
	

	
	Professional experience of the project engineer ≥ 03 years (signed CV)
· CV signed by the candidate, 
· A certified copy of the technical diploma 
· An attestation of availability signed by the candidate

	
	

	B.3.2
	01 Site foreman(Senior Civil Engineering BAC+2)

	
	Qualification of the Site foreman: (Technical certificate in civil engineering         (BAC+2 or equivalent certificate)
	
	

	
	Professional experience of the Site foreman ≥ 03 years (signed CV)
A certified copy of 
· CV signed by the candidate, 
· A certified copy of the technical diploma 
· An attestation of availability signed by the candidate

	
	

	B.3.3
	Other personnel

	
	· 01 one civil engineering technicain with 3 years professional experience in building construction or similar works Only( CVs signed by the candidate + copy of certificate)
(Must be holders of  at least BAC F4 certificate)
	
	

	
	· 01one Carpenter with 3 years professional experience on carpentry or similar works. Only (CVs signed by the candidate+ copy of certificate)
(Must be holders of  at least CAP certificate)
	
	

	B.4
	METHODOLOGY

	B.4.1
	Organizational chart of the enterprise/site with comments
	
	

	B.4.2
	Planning of work execution with comments

-installation, origin of materials


	
	

	B.4.3
	Methodology of execution of works
	
	

	B.4.4
	Safty measures
	
	

	B.4.5
	Himo/maintenance measures
	
	

	B.5
	LOGISTICS (Equipment put aside for this project)
	
	

	B.5.1
	Prove of ownership or rental of a pick-up or other vans
	
	

	B.5.2
	Prove of ownership or rental of a dump truck
	
	

	B.5.3
	Prove of ownership or rental of a Concrete mixer
	
	

	B.5.4
	Prove of ownership or rental of a concrete vibrator
	
	

	B.5.5
	Prove of ownership or rental of a Hand compactor
	
	

	B.5.6

	Masonry Kit : Wheelbarrows, masonry clamps, masonry harmer 300g, shovel, dig axe, building level, masonry bucket , trowels, etc.
	
	

	
	Carpentry Kit  : carpentry clamps, saws, harmers, etc.
	
	

	B.6
	FINANCIAL CAPACITY
	
	

	B.6.1
	An attestation of financial capacity (solvency) of the enterprise issued by a 1st class bank located in any area in Cameroon and approved by the Ministry of Finance and respect COBAC conditions. 25% of amount = 31,806,000 or more
	
	

	B.7
	Attestation of site visit signed by the company administrator or engineer
	
	

	B.8
	Comprehensive report of site visit signed by the company administrator or engineer 
	
	

	B.9
	Special Technical Clauses initialed in all the pages and last page signed
	
	

	B.10
	Special Administrative Clauses completed and initialed in all the pages and last page signed 
	
	


ENVELOPE C- FINANCIAL FILE

	No.
	DESIGNATION.

	C1
	A submission letter, signed, dated and stamped.(see ANNEX 3)

	C2
	Completed and signed frame work of unit prices. 

	C3
	Signed Bills of quantities and cost estimates indicating the total amount without taxes (HT) and with taxes (TTC) 

	C4
	Sub details of unit prices


· The bidders will use for this purpose the documents and models envisaged in the Tender Documents, subject to the provisions of Article 19.2 of the RGAO concerning the other possible forms of bid bond. 

· The various parts of the same file must be separated with colour page separators as well in the original as in the copies, so as to facilitate its examination
Supply price

ARTICLE 8: Currency of payment

This National Invitation to tender is awarded on total and contractual price, inclusive of all taxes, firm and non-revisable for the whole of the works and the equipment defined in the present Invitation to tender. 


The corresponding amount will be calculated inclusive of all taxes and the prices will be obligatorily expressed in francs CFA. 


The unit Schedule price expressed out in figures and letters and in six (07) copies will be joined to the offer. In the event of error between the prices in figures and letters, the latter will precede and be used as a basis of calculation of the amount of the offer. 


The establishment of the prices will be done on the basis of economic condition into force in Republic of Cameroon at the handover date of the offers.

ARTICLE 9:Transport and delivery
The materials for work must be protected during transportation through packaging whether by air, railway or road according as the case may be. The conditions of storage must be of tropical type.  

ARTICLE 10:Guarantee and retention guarantee
10.1 Provisional guarantee
The amount of the provisional guarantee or guarantee of tender is fixed at 2,544,437 FCFA (Two million five hundred and forty four thousand four hundred and thirty seven FCFA). As per article 90 (9) of the Public contract Code (Decree No. 2018/366 OF 20 June 2018), certified cheques or bank cheques are acceptable in the place of bid bond.

The time of validity of this guarantee is sixty (60) days as from the date of depositing of the offers.

10.2 Final Bond
The final Bond is fixed at Two percent (2%) of the initial amount of the services envisaged in the country. 

It could be replaced by a guarantee personal and interdependent of a banking house approved by the Ministry of Finances following COBAC conditions.  

It will have to be made up in the twenty (20) days following the notification of the signature of the contract in a bank approved by the Minister in charge of Finances.

10.3   Guarantee Retention 

Guarantee Retention of ten percent (10%) will be operated on amount including all taxes of the contract. The corresponding sum will be paid or the released guarantee, one year after provisional reception of works.
ARTICLE 11: Period of validity of the offers
The bidder will remain committed to his offer for sixty (60) days as from the handover date of the offers. 

If at the end of this period, the contract were not notified to him, the bidder will be able, either to cancel his offer, or to ask for a new negotiation of the unit prices.


ARTICLE 12: A number of copies of the offer which must be filled and sent

The tender, as all the parts accompanying it will have to be given in seven (0 7) copies, including one (01) original and six (06) copies. The bidder will present his dossier inside a sealed outer jacket being marked:

 TO THE DELEGATED PROJECT OWNER (CONTRACTING AUTHORITY)
<< N° 02/ONIT/NW06/DTB/2024 OF ____/___/2024
FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION.>>
<<TO BE OPENED ONLY DURING THE OPENING SESSION>>
ARTICLE 13: Date and latest time of deposit of offers


The offers will have to arrive under closed fold and seal latest ____/___/2024 at 10AM, by mail registered with acknowledgement of delivery or by deposit against receipt to the following address:

Divisional Delegation of Public Contracts for MOMOsituated at MBENGWI, Beyond this time no offer will be received nor accepted.
ARTICLE 14: Opening of the tenders

The opening of the folds will be carried out in the conference room of the Senior Divisional Office  for MOMO situated at MBENGWI on ___/___/2024 as from 11AM, by the MOMO Divisional Tenders Board sitting in the presence of the duly elected bidders or their representatives and having a good knowledge of the file.
AWARD OF THE CONTRACT
ARTICLE 15: Award of the contract

 The Tenders Board will propose to the Contracting Authority to award the contract to the bidder who will have presented the offer with the lowest offer, essentially conforming to the regulations of the Tender File and having satisfied to 100% of all the eliminatory criteria and at least 75% of the essential criteria taken into account. 


The decision carrying attribution of the contract will be published by way of press release or any other means of publication in force in the Administration.
If the contract passed on the basis of technical alternative suggested by the bidder, the contracting authority reserves the right to introduce all the provisions there allowing him to guarantee itself against the real overrun costs of the alternative compared to his estimate of origin. In the absence of these last precise details, any additional charge due to an alternative will be inadmissible. 


To this end, it is specified that a bidder cannot claim to be compensated, if his offer is not accepted. 


The contracting authority reserves the right not to take action on an Invitation to tender, if it   did not obtain a proposal which appears acceptable to him.

Pursuant to justification by bidder, bids with unconvincing abnormally low costing will be rejected by the Delegated Project Owner as proposed by the Tenders Board. 

Prior to this reject, the bidder must have been requested to produce written justification(s)  and that these justifications have been appreciated to be unconvincing.

These justifications will concern amongst others

· The production of detailed pricing, its content and the coherency between the unit price, its mode of realisation and its timing. 

· The purchase prices of materials

· The cost of exploitation of equipment

· The wages of technicians and labourers

· comparative advantages or favourable exceptional conditions that the bidder has for the realisation of the works

· measures relative to the condition of works

In the case where these justification(s) is or are not convincing, the Contracting Authority decides but before the reject, he can only decide when the Public Contracts Regulatory  Agency(ARMP) must have examined the unconvincing justification(s) and given his opinion in seven (07) working days from the date of receipt of these justifications from the Contracting Authority. (The Tenders Board requests for justifications, bidder replies by writing, board examines and if not convincing, proposes reject to contracting Authority who decides after consulting ARMP)
ARTICLE 16: COMMENCEMENT OF WORK:

Before the commencement of works, the contractor must make sure that she respects the elements of maturity of the project especially those shown to him during the site visit. 

However if for one reason or the other the initial location shown to the contractor during the site visit has to change at this phase, the following adhoc commission members will be convened to established A report of the change:

· The Authorizing Officer or his representative                         ……  (chairperson)

· The Divisional Delegate of MINMAP or his representative;………….(member)
· The Divisional Chief Technical Service ………………. …..………….(secretary)

· The contractor…………………………………………….…………..(member)
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Chapter I: General

Article 1:  Subject of contract

The subject of this contract shall be the CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION 
Article 2: Contract award procedure

This contract shall be awarded by Open National Invitation To Tender, emergency procedure             
    N° 02/ONIT/NW06/DTB/2024 OF ____/___/2024
Article 3: Definitions and duties (article 2 of GAC supplemented)

3.1 General definitions (cf. Code)

· The Contracting Authority is the Senior Divisional Officer Momo
               He awards the contract, ensures the preservation of originals of said contract documents and the transmission of copies to Ministry in charge of Public Contracts and to the body in charge of regulation.

· The Contract Manager is the  ;  DIVISIONAL DELEGATE OF PUBLIC WORKS MOMO. He defends the interests of the Project Owner and represents the delegated Project Owner in all the levels of the project

· The Contract Engineer is the Chief Of Techenical Sevice at The Divisional Delegation Of Public Work Momo. Hereinafter referred to as the Engineer.

· The Project Owner is the DIVISIONAL DELEGATE OF PUBLIC WORKS MOMO. He represents the beneficiary administration of the works.
· The project Manager is the Follow up engineer at  the Divisional Delegation Of Public Work Momo. He ensures respect of the administrative, technical and financial conditions and contractual deadlines.  He ensures the interest of the project owner at the definition, preparation, execution and acceptance stages

· The Service in charge of ensuring the effectiveness of the execution of works is  the the Technical Service of Public Works Momo. 
· The contractor is be [to be specified].

3.2 Security

This contract may be used security subject to any form of transfer of the debt.

In this case:

· The authority in charge of ordering payment shall be the the Divisional Delegate of Public Works Momo.
· The authority in charge of the clearance of expenditures shall be the Divisional Finance Controller for Momo.
· The body or official in charge of payment shall be the Divisional Treasurer for Momo
· The official competent to furnish information within the context of execution of this contract shall be the Delegated Project Owner (The Senior Divisional Officer Momo); Contracting Authority/ Divisional Delegate of Public Contracts for Momo.
3.3    Duties of the Control Mission, Project Manager 

3.3.1 Missions [to be completed, where need be]
3.3.2 Means put at the disposal of the Control Mission and the other stake holders of the project:  
In accordance with the provisions of article 153 paragraphs one (01) and two (02) of the Public contract Code. (Decree No. 2018/366 OF 20 June 2018). The Contract Manager, the Contract Engineer as well as the other persons in charge of the control and follow up of the project shall perceive indemnities as well as logistics support for the realisation of the project from that shall be fixed by a decision of the Project Owner or delegated Project Owner.  
Article 4: Language, applicable law and regulation

1.2 The language to be used shall be [English and/or French].
1.3 The contractor shall be bound to observe the law, regulations and ordinances in force in Cameroon both within his own organization and in the execution of the contract.

If the laws and regulations in force at the date of signature of this contract are amended after the signature of the contract, the possible direct resulting costs shall be taken into account without gain or loss for either party.

Article 5: Constituent documents of the contract (Article 4 of GAC)
The constituent contractual documents of this contract are in order of priority: (to be adapted to the nature of the works).
1)  The tender or commitment letter; 

2)  The bidder’s tender and its annexes in all provisions not contrary to the Special Administrative Conditions (GAC) and the Special Technical Conditions (STC) hereunder;

3)  The Special Administrative Conditions (SAC); 

4)  The Special Technical Conditions (STC);

5)  The particular elements necessary for the determination of the contract price, such as, in order of priority: the unit price schedule, the statement of all-in prices, detailed estimates, the breakdown of all-in prices and the sub-details of unit prices;

6)  Plans, calculation notes, trial documents, geotechnical documents [insert and indicate, where need be, names and references].

7)  The General Administrative Conditions applicable on public works contracts that went into effect by Order No. 033/CAB/PM of 13 February 2007;

8)  The General Technical Condition(s) applicable on the services forming the subject of the contract [insert and indicate, where need be, names and references].
Article 6: General instruments in force
This contract shall be governed by the following general instruments [to be adapted according to the case]:

1. Framework Law No. 96/12 of 5th August 1996 on the management of the environment; 

2. The Mining Code; 

3. Instruments governing the various professional bodies; 

4. Decree No. 2001/048 of 23rd February 2001 relating to the Setting up, Organization and Functioning of the Public Contracts Regulatory Agency  

5. Decree No. 2003/651/PM of 16th April 2003 to lay down the Procedure for Implementing the Tax and Customs System applicable to Public Contracts; 

6. Decree No. 2018/366 of 20th June 2018 to institute the Public Contracts Code; 

7. Decree No. 2012/075 of 8th March 2012 to organise the Ministry in charge of Public Contracts; 

8. Letter No. 00908/MINTP/DR of 1997 to publish guidelines for the consideration of environmental impact of road maintenance; 

9. Circular N°00000026/C/MINFI of 29th December 2024 on instructions relating to the implementation of the Finance laws, the Monitoring and control of the execution of the Budgets of the State and other public entities for the 2024 fiscal year;. 

10. Unified Technical Documents (DTU) for building works; 

11. Applicable standards; 

12. Order No 212/A/MINMAP of 28th September 2021 organizing the functioning of SIGAMP; 13. Other instruments specific to the domain concerned with the Contract. 

Article 7: Communication (Articles 6 and 10 supplemented)

1.1  All communications within the framework of this contract shall be written and notifications sent to the following address: 
a) In the case where the contractor is the addressee: Sir/Madam..........
Beyond the time-limit of 15 days fixed in article 6(1) of the GAC to make his domicile  known to the Project Owner and Contract Manager, correspondences shall be validly addressed to the [to the specified] council, chief town of the 

region in which the work was done;
b) In the case where the Project Owner is the addressee:
Sir/Madam_______ [to be specified] with a copy addressed to the Contracting Authority, Contract Manager, Contract Engineer, Project Manager and where need be, within the same deadline.

c) In the case where the Contracting Authority is:

Sir/Madam [to be specified] with a copy addressed within the same deadline to the Project Owner, Contract Manager, Contract Engineer and Project Manager, where applicable 

1.2 The contractor shall address all written notifications or correspondences to the Project Manager with a copy to the Contract Manager.
Article 8: Administrative Orders (Article 8 of GAC)

The various Administrative Orders shall be established and notified as follows:  

8.1 The Administrative Order to start execution of works shall be signed by the Contracting Authority and notified to the contractor by the Project Owner with a copy to the Contracting Authority, the Contract Manager, Contract Engineer, the Paying Body and the Project Manager, where applicable.

8.2 Upon proposal by the Project Owner, Administrative Orders with an incidence on the objective, the amount and execution deadline shall be signed by Contracting Authority and notified by the Project Owner to the Contractor with a copy to the Contracting Authority, the Contract Manager, the Contract Engineer, the Project Manager and the Paying Body. The prior endorsement of the Paying Body shall possibly be required before the signature of those that have an incidence on the amount. 

8.3 Administrative Orders of a technical nature linked to the normal progress of the work and without financial incidence shall be signed directly by Contract Manager and notified to the contractor by the Contract Engineer or Project Manager  (where applicable) with a copy to the Contracting Authority and Contract Manager.

8.4 Administrative Orders serving as warnings shall be signed by the Project Owner and notified to the contractor by the Contract Manager with a copy to the Contracting Authority, the Contract Engineer and Project Manager.

8.5 Administrative Orders for suspension or resumption of work as a result of the weather or any other case of force majeure shall be signed by the Contracting Authority and notified by his services to the contractor with a copy to the Project Owner, Contract Manager, Contract Engineer and Project Manager. 

8.6 Administrative Orders prescribing works necessary to remedy disorders which could appear on structures during the guarantee period and not related to normal usage shall be signed by the Contract Manager upon the proposal of the Contract Engineer and notified to the contractor by the Contract Engineer. 

8.7 The contractor has a time-limit of fifteen (15) days to issue reservations on any Administrative Order received. Having reservations shall not free the enterprise of executing the Administrative Orders received.

8.8 Concerning Administrative Order signed by the Contracting Authority and notified by the Project Owner, the notification must be done within a maximum of 30 days from the date of transmission by the Contracting Authority to the Project Manager. Beyond this deadline, the Contracting Authority shall establish the default of the Project Owner, take over from him and carry out the said notification.

Article 9: Contracts with conditional phases (Article 9 of GAC)
9.1  [Specify if the contract has one or several phases]

At the end of a phase, the Project Owner shall carry out the acceptance of the works and issue an attestation of proper execution to the contractor. This attestation shall condition the start of the following conditional phase.

9.2   The time-limit granted for notification of the Administrative Order to start execution of a conditional phase shall be five (5) days.

Article 10: Contractor’s equipment and personnel (Article 15 of GAC supplemented)

10.1 Any modification, even partial, made to the technical bid shall only occur after the written approval of the Contract Manager. In case of modification, the contractor shall have himself replaced by a member of staff of equal competence (qualifications and experiences).

10.2 In any case, the lists of supervisory staff to be used shall be subject to the approval of the Project Owner in the days following notification of the Administrative Order to start execution. The Project Manager has 5 (five) days to notify his opinion in writing with a copy sent to the Contract Manager. Beyond this time-limit, the staff list shall be considered as approved.

10.3 Any unilateral modification on the supervisory staff made in the technical bid prior to and during the works shall be a reason for termination of the contract as mentioned in article 45 below or the application of penalties [to be specified where need be].

Chapter II: Financial conditions

Article 11 Guarantees and bonds (Articles 29 and 41 of GAC)

11.1 Final bond

The final bond shall be set at 2 % of the amount of the contract, inclusive of all taxes.

It is constituted and transmitted to the Contract Manager within a maximum deadline of twenty (20) days of the notification of the contract.

The bond shall be returned or the guarantee released within one month following the date of provisional acceptance of the works, following a release issued by the Contracting Authority upon request by the contractor.

11.2  Performance bond

The retention fund shall be set at 10 % of the amount of the contract, inclusive of all taxes.

The return or release of the retention fund or security shall be done within one month after final acceptance by release issued by the Contracting Authority upon request by the contractor.

11.3 Guarantee of start-off advance

[Specify, if need be, the rates (20% maximum of the amount of the contract inclusive of all taxes guaranteed at 100%) and conditions for the return of the guarantee]

Article 12: Amount of the contract (Articles 18 and 19 of GAC supplemented) 

The amount of this contract as indicated by the attached [detail or estimates] is _______ (in figures) ______(in words) CFA francs Inclusive of All Taxes; that is: 

· Amount exclusive of VAT: _________(_______) CFA F

· Amount of VAT: __________(______) CFA F.

· Amount of TSR and/or _____________CFA F

· Net to be paid= EVAT-TSR and/or AIR

Article 13: Place and method of payment

The Project Owner shall release the sums due in the following manner:

a. For payments in CFA francs (amount in figures and letters exclusive of taxes) by credit to account No._________ opened in the name of the contractor in the ___________bank.

b. For payments in foreign currencies (amount in figures and letters exclusive of taxes) by credit to account No._________ opened in the name of the contractor in ________bank.

Article 14: Price variation (Article 20 of GAC)

1.1 Prices shall be firm.

a. Payments on account made to the contractor as advances shall not be revisable.

b. Revision shall be “frozen” upon expiry of the contractual time-limit, except in the case of price reductions.

1.2   Price updating modalities (not applicable)

Article 15: Price revision formulae (article 21 of GAC)

(not applicable)
Article 16: Price updating formulae (article 21 of the GAC)

(not applicable)
Article 17: Works under State supervision (Article 22 of GAC supplemented)

17.1 The percentage of works under State supervision shall be [must not exceed 2 %] of the amount of the contract and its additional clauses, where applicable.

17.2 In the case where the contractor were invited to execute works under State supervision, the submitted and duly justified expenditures shall be reimbursed to him under the following conditions:

· The quantities considered shall be the hours used or the quantities of building materials and materials used that was the subject of joint job cost sheets;

· The remunerations and salaries effectively paid to local labour shall be increased by forty percent (40 %) to take account of  social benefits; 

· The hours put in by the heavy equipment shall be counted at the rate featuring in the sub-detail of prices;

· Building materials and materials shall be reimbursed at cost price duly justified at the place of use, marked up by ten percent for loss, stocking and handling;

· The amount for services thus calculated, including the hours put by heavy equipment shall be marked up by 25 % to take into account the overheads, profits and the contractor’s unforeseens.

Article 18: Evaluation of works (article 23 of the GAC)

This contract is at [unit price, all-in price or unit and all-in price].

Article 19: Evaluation of supplies (article 24 of the GAC supplemented)

19.1 [indicate, where applicable, the modalities for payment of supplies].

19.2 No security shall be requested for payments on account on supplies.
Article 20: Advances (article 28 of the GAC)

20.1 The Contracting Authority may grant a start-off advance equal to 20 % of the amount of the contract. 
20.2  This advance whose value cannot exceed twenty (20%) percent of the initial amount inclusive of all taxes, it shall be guaranteed at one hundred (100%) percent by a banking establishment governed by Cameroon law or a first-rate financial institution in accordance with the instruments in force and reimbursed by deduction of the payments on accounts to be paid to the contractor during the execution of the contract according to the modalities laid down in the Special Administrative Conditions. 
20.3  The total amount of the advance must be reimbursed not later than when the value in basic price of the works reaches eighty (80) percent of the amount of the contract.
20.4  As the reimbursement advances, the Project Owner shall issue the release of the corresponding part of the guarantee upon the express request by the contractor. 
20.5 The possibility of granting start-off advance or advance for supplies must be expressly stipulated in the Tender File.  
Article 21: Payment for works (articles 26, 27 and 30 of the GAC supplemented)

21.1 Establishment of works executed

Before the 30th of each month, the contractor and the Engineer shall jointly establish a job cost sheet which summarises and fixes the quantities executed and established for each item on the schedule during the month and capable of giving entitlement to payment. This sheet shall be based on the certification of the various tasks jointly established by the contractor and the Project Manager
21.2 Monthly detailed account

Every month of during a periodic sequence established by contractor and representative of the project owner, the contractor shall hand over to the Contract Engineer two draft provisional monthly detailed accounts in seven copies (one detailed account exclusive of VAT and the other inclusive of taxes), according to the agreed model and establishing the total amount of the sums to which he may lay claim as a result of the execution of the contract since the start of the contract.

Only the detailed account exclusive of VAT shall be paid to the contractor. The detailed account of the amount of the taxes shall be the subject of an entry into the budgets of the Ministry in charge of Finance

Only the amount exclusive of VAT shall be paid to the contractor as follows:

· [100-2.2 and/or – (5.5 or 15%)] paid directly into the account of the contractor;

· 2.2 % paid to the public treasury as AIR due by the contractor.

· 7.5% or 15% paid into the public treasury as TSR due by the contractor.

The Project Manager has a time-limit of seven (7) days to forward to the Contract Manager the detailed accounts he has approved.

The Contract Engineer has a maximum time-limit of twenty-one (21) days to forward the detailed accounts he approved such that they are in his possession not later than the twelfth of the month.  

The Contract Manager has a deadline of fourteen (14) days maximum to sign the detailed accounts.

Payments shall be done by the Divisional Treasurer for MOMOwithin a maximum deadline of twenty one (21) calendar days from the date of submission of the approved detailed accounts.

21.3 Detailed account of start-off account (if applicable).

Article 22: Interest on overdue payments (Article 31 of the GAC)

Possible interests on overdue payments are paid by statement of sums due in accordance with article 88 of Decree No. 2004/275 of 24 September 2004 to institute the Public Contracts Code.

Article 23: Penalties (Article 32 of the GAC supplemented)

A. Penalties for delay
23.1 The amount set for penalties for delays shall be set as follows:

a) One two thousandth (1/2000th)  of the initial contract amount all taxes inclusive per calendar day of delay from the first to the 30th day beyond the contractual time-limit;

b) One thousandth (1/1000th) of the initial amount of the contract inclusive of all taxes per calendar day beyond the 30th day.

23.2 The cumulated amounts of penalties for delay shall be limited to ten percent (10 %) of the initial contract inclusive of all taxes.
B. Specific penalties [amount to be indicated]

23.3 Independently of penalties for overrun of contractual time-limit, the contractor shall be liable for the following special penalties for the non-observation of the provisions of the contract, especially:

· Late submission of final bond;

· Late submission of insurances;

· Late submission of the draft execution schedule if the lateness is caused by the contractor. 

Article 24: Payment in case of a group of enterprises (article 33 of the GAC)

1. In the case of a group of enterprises, indicate the method of payment of co- and sub-contractors, where need be.

2. Indicate the method of payment of sub-contractors, where need be.

Article 25: Final detailed account (article 34 of the GAC)

25.1 [Indicate the time-limit available to the contractor to forward the draft to the Project Manager, after the date of provisional acceptance of the works (maximum 1 month)].
After completion of the works and within a maximum time-limit of fourteen (14) days after the date of provisional acceptance, the contractor shall establish, based on joint reports, the draft final detailed account of works executed and which detailed account summarises the total sums to which the contractor may be entitled as a result of the execution of the whole contract.

25.2  The Contract Manager has up to thirty (30) days to notify the corrected and approved draft to the Project Manager.
25.3 The contractor has up to thirty (30) days to return the signed final detailed account. 
Article 26: General and final detailed account (article 35 of the GAC)

26.1 The Contract Manager or the Project Manager has up to thirty (30) days to establish the general detailed account and forward to the contractor after final acceptance.
At the end of the guarantee period which results in the final acceptance of the works, the Contract Manager draws up the general and final detailed accounts of the contract which he has had signed jointly by the contractor and the Contracting Authority. This detailed account includes:

· the final detailed account, 

· the balance

· the summary of monthly payments on account.

The signing of the general and final detailed account without reservation by the contractor definitely binds the two parties, puts an end to the contract, except with regard to interest on overdue payments.

26.2 The contractor has up to thirty (30) days to return the signed final detailed account.
Article 27: Tax and customs regulations (article 36 of the GAC)

Decree No. 2003/651/PM of 16 April 2003 lays down the terms and conditions for implementing the tax regulations and customs procedures applicable to public contracts. The taxes applicable to this contract include notably:

· Taxes and dues relating to industrial and commercial profits, including the IAR which is a deduction on company taxes;

· Registration dues in accordance with the Tax Code;

· Dues and taxes attached to the execution of services provided for in the contract;

· Duties and taxes of entry into Cameroonian territory (customs duties, VAT, computer tax);

· Council dues and taxes;

· Dues and taxes relating to the extraction of building materials and water.

These elements must be included in the costs which the undertaking imputes on its running costs and constitute one of the elements of the sub-details of prices exclusive of taxes.

All taxes inclusive prices means VAT included.

Article 28: Stamp duty and registration of contracts (article 37 of GAC) 

Seven (7) original copies of the contract shall be stamped by and at the cost of the contractor, in accordance with the applicable regulations.

Chapter III: Execution of works

Article 29: Nature of the works (article 46 of GAC)

The works shall include especially: (position or volume of works)

(To be specified cf. Special Technical Conditions)
Article 30: Role and responsibilities of the Project Owner (GAC supplemented)

30.1 The Project Owner shall be bound to furnish the contractor with information necessary for the execution of his mission and to guarantee, at the cost of the contractor, access to sites of projects.

30.2 The Project Owner shall ensure the contractor of protection against threats, insults, violence, assault and battery, slander or defamation of which he could be victim by reason of or during the exercise of his mission.

Article 31: Execution time-limit of the contract (article 38 of the GAC)

31.1 The time-limit for the execution of the works forming the subject of this contract shall be six (06) calendar months.

31.2   This time-limit shall run from the date of notification of the Administrative Order to commence execution of the works [or that fixed in this Administrative Order- to be specified].

Article 32: Role and responsibilities of the contractor (article 40 of the CAG)

The detailed and general plan of progress of the works shall be communicated to the Project Manager in five (05) copies at the beginning of each.

Article 33: Provision of documents and site (article 42 of the GAC)

A reproducible copy of the plans featuring in the Tender File shall be submitted by the Contract Manager .

The Project Owner shall make available the site and access ways to the contractor at the appropriate time as the works progress.

Article 34: Insurance of structures and civil liabilities (article 45 of GAC)

The following insurance policies are required within the scope of this contract in the minimum amounts indicated hereafter within fifteen (15) days of the notification of the contract (to be adapted): 

· Liability insurance, business manager;
· Comprehensive insurance  of the site;

· Insurance covering its ten-year obligation, where applicable.
Article 35: Documentsto be furnished by the contractor (Article 49 of the GAC supplemented)
[Specify the deadlines for the transmission of documents as well as those of approval by persons to be designated]

35.1 Programme of works, Quality Assurance Plan and others (to be specified).
a) Within a minimum deadline of [fifteen (15) days] from the date of notification of the Administrative Order to commence execution, the contractor shall submit in [six (6)] copies for the approval of [Contract Manager after the endorsement of the Project Engineer] the execution programme of the works, his supply calendar, his draft Quality Assurance Plan and the Environment Management Plan, where applicable.

This programme shall be exclusively presented according to the furnished models.

Two (2) copies of these documents will be returned to him within a deadline of fifteen (15) days from the date of reception with:

· Either the indication “GOOD FOR EXECUTION”;

· Or the indication of their rejection including the reasons for the said rejection.

The contractor has eight (8) days to present a new draft. The Contract Manager or the Project Manager then has a deadline of five (5) days to give his approval or possibly make comments.   Delay in approving the draft execution schedule shall stay the execution deadline.

The approval given by the Contract Manager or Project Manager does not in any way release the contractor of his responsibilities. Meanwhile, works executed before the approval of the programme shall neither be ascertained nor paid for. The updated and approved schedule will become the contractual schedule.

The contractor shall constantly update on site, a schedule that will take account of real progress of the site. Significant modifications may only be made on the contractual programme upon receiving the approval of the Project Manager. After approval of the execution schedule by the Contract Manager, the latter shall transmit it within five (5) days to the Contracting Authority without staying its execution. However, if important modifications alter the objective of the contract or the nature of the works, the Contracting Authority shall return the execution schedule accompanied by reservations to be lifted within fifteen (15) days of the date of reception.  

b) The Environment Management Plan should bring out notably the choice technical conditions of the site and basic life, conditions of the backfill of the extraction sites and conditions for reinstating the works and installation sites.

c) The contractor shall indicate in this schedule the equipment and methods which he intends to use as well as the personnel he intends to employ.

d) The approval granted by the Contract Manager or Project Manager shall in no way diminish the responsibility of the contractor with regard to the harmful consequences which their implementation may cause both towards third parties and the respect of clauses of the contract.

35.2  Execution draft

a)  The execution plan documents (calculations and drawings) necessary for the realisation of all the parts of the structure must be submitted for the endorsement of the [Contract Manager or Project Manager] at most fifteen (15) days prior to the date provided for the commencement of execution of the corresponding part of the structure.

b) The [Contract Manager or Project Manager] has a deadline of [five (05) days] to examine and make known his observations. The contractor then has a deadline of [04) four days] to present a new file including the said observations.

35.3   In case of the non-observance of the approval deadlines of the above documents by the Administration, these documents shall be deemed to have been approved. 

Article 36: Organisation and safety of sites (article 50 of the GAC)

36.1  Signboards at the beginning and end of each section must be placed within a maximum deadline of fifteen days after the notification of the Administrative Order to commence work.

36.2  The services to inform in case of interruption of traffic or along the deviated itinerary: [To be specified in accordance with article 50(2) of the GAC].

36.3  Indicate the special measures demanded of the contractor, other than those provided for in the GAC, for rules of hygiene and safety and for circulation around or in the site.
Article 37: Implantation of structures

 The Project Manager shall notify within [five] days following the date of notification of the Administrative Order to commence work, the basic points and levels of the project.

Article 38: Sub-contracting (article 54 of the GAC)

The part of the works to be sub-contracted shall be [specify] % of the initial amount of the contract and its additional clauses (the ceiling is 30 %).

Article 39: Site laboratory and trials (article 55 of GAC)

39.1 Indicate if necessary the modalities for carrying out the trials and geotechnical studies provided for in the Special Technical Conditions.

39.2 The Contract Manager has a deadline of three days to approve the contractor’s personnel and laboratory as soon as the request is made.

Article 40: Site logbook (article 56 of the GAC supplemented)

40.1  The Site logbook must be systematically jointly signed by the Project Manager or Engineer, where need be and the contractor’s representative each day.

40.2  It is a joint document in a single copy. Its pages must be numbered and initialled. No page should be removed. The erased or cancelled parts must be mentioned on the margin for validation.

Article 41: Use of explosives (article 60 of the GAC)

[Specify the possible restrictions or bans]

Chapter IV: Acceptance

Article 42: PROVISIONAL ACCEPTANCE  

42.1
PRE- ACCEPTANCE OPERATIONS


Before the acceptance of the works the contractor shall ask in writing to the Contract Engineer, to organize a technical visit for pre-acceptance. This visit shall include the following operations.

· Qualitative and quantitative evaluations of the different works that have been executed.

· Findings and statement of the unexecuted task envisaged in the present jobbing order.

· Findings relative to the completion of the work

· Findings on the quantity of works that have been effectively realized 


These operations shall be subject to a site report drawn up on the field, signed by the following. 

-Contract Engineer,

-Contractor. 


During this pre-acceptance, the Contract Engineer shall eventually specify the reserves to be lifted and the corresponding works to be effected before the acceptance. The Contract Engineer shall fix the acceptance date in collaboration with the chief of service for the contract. 

42.2
Acceptance


The acceptance commission shall comprise: 

· The Authorizing Officer or his representative……………….……  (Chairperson)
· The Contractinf Authority or Representative …………………………...(Member)

· The Divisional Delegate of MINMAP or his representative;…………….(Member)
· The Contract Engineer or his representative …………………….……..(Secretary)
· The S/A DDMINTP Momo………………………………………………(Member)
· The Project Maneger……………………………………………………(Member)

· The contractor…………………………………………………………...(Member)
The commission shall examine the report of the pre-acceptance and shall proceed to the acceptance. An acceptance report (process - verbal) of the works shall be prepared by the Engineer and signed by all the commission members. 
However, the report (process - verbal) shall be valid if two third (2/3) of the members including the chairperson append their signatures. 

The chairperson can only convene the acceptance of works when he must have received from the Contract Engineer the report (process - verbal) of the technical acceptance of works with no reserves pending clearance. 
This report (process - verbal) of the technical acceptance of works shall be an integral part of the acceptance of works’ report (attached to acceptance of works report) and shall accompany the bills for settlement

In accordance with the provisions of article 153 paragraphs 1 and 2 of the Public contracts Code (Decree No. 2018/366 OF 20 June 2018), an indemnity to be fixed by the project Owner shall be perceived by the members. 

Article 43: GUARANTEE PERIOD.


The guarantee period is one (01) year from the date of the provisional reception for the section of new civil Engineering works. 

Article 44: Article 45: Final acceptance (article 72 of the GAC)

44.1 Final acceptance shall take place within a maximum deadline of [fifteen (15) days] from the date of expiry of the guarantee.

44.2 The Project Manager [shall [not] be member of the commission.

The procedure for final acceptance shall be the same as for provisional acceptance    

Chapter V: Sundry provisions

Article 45: Termination of the contract (article 74 of the GAC)

The contract may be terminated as provided for in  article 182 of the Decree No. 2018/366 OF 20 June 2018 of the Public contract Code and equally under the conditions laid down in articles 74, 75 and 76 of the GAC especially in one of the following cases:

· dead of the contractor

· bankruptcy of the contractor

· judicial liquidation (contractor not authorised by court to exploit her enterprise

· sub contracting of works without the authorisation of the  project owner or Delegated Project Owner, Contracting Authority in this case;  

· Incompetence of the contractor duely notified by the Delegated project owner; Contracting Authority in this case.

· Non respect of labour code rules and regulations

· fraud and corruption duly noticed

Article 46: Case of force majeure (article 75 of the GAC)

If the contractor were to raise the issue of force majeure, the thresholds below which claims shall not be admitted are:

· Rainfall: 200 millimetres in 24 hours;

· Wind: 40 metres per second;

· Flood: decennial flood frequency.

Article 47: Disagreements and disputes (article 79 of the GAC)

Disagreements and disputes resulting from the execution of this contract may be settled amicably.

Where no amicable solution can be found for a disagreement, it is brought before the competent Cameroonian jurisdiction, subject to the following provisions: [to be filled, where need be].

Article 48: Production and dissemination of this contract

In accordance with the provisions of article 125 of Decree No. 2018/366 OF 20 June 2018 of the Public contract Code, [Ten (10)] copies of this contract shall be produced by the Delegated Project Owner. Seven of which shall be notified to the contractor for registration. 

Article 49 and last: Entry into force of the contract

This contract shall be final only upon its signature by the Contracting Authority. It shall enter into force as soon as it is notified to the contractor by the Contracting Authority.

Document No. 5:

Special Technical Conditions (STC)

CHAPTER ONE: GENERAL PROVISIONS 

TECHNICAL SPECIFICATIONS OF WORKS 
OBJECT OF THIS DOCUMENT 
 This book of technical specification of works is aimed at setting the rules and techniques of construction as well as the procedure of work envisaged for the CONSTRUCTION OF SOME BRIDGE AT ANGAI  
PROCEDURE OF WORK  
The realization of the works was conceived according to the principles of the construction of bridges in Cameroon. 

CONSISTENCE OF WORK  
The complete project comprises the following lots: 

· Serie 000: SITE INSTALLATION  

· Serie 100: cleaning & levelling 

· Serie 300: drianage 

· Serie 400: engineering structures 

· Serie 500: signalsation & security equipment

· Serie 600: others 
These works shall be executed as outlined in the next few paragraphs 

GENERAL TECHNICAL SPECIFICATIONS 
A.1.  TECHNIQUES OF REFERENCE DOCUMENTS 
For the execution of the work, the contractor will be subject to the requirements and following basic technical documents: 
· New technical rules of design and calculations of the works and constructions in reinforced concrete method of the limit states’ (BAEL)-EDITION 91. 
· French or similar standards approved in Cameroon. 
· The rules of Cameroon for the construction and urban planning. 
· The notebooks of the clauses and conditions imposed on the construction of public works and buildings in the Republic of Cameroon. 
· Standards (AFNOR-CSTB) and technical documents unified (DTU) 
A.4. MATERIALS CONSTITUTING THE CONCRETE 
A.4.1  Aggregates. 
All aggregate sites will be stored in compartments designed to this effect.  Only aggregate authorized on the site are the following; 
· 0/5 Crushed gravel 
· Crushed gravel 5/15 
· Crushed gravel 15/25 
· Natural sand or crushing /5 (proportion of items retained on the sieve of 5mm must be less than 10%) 
A.4.2.  Gravel 
They shall be obtained from a variety of quarries including river deposits, manual or machine crushed, chosen by the Contractor and approved by the Supervisor.  They should be clean 
(constituents eliminated through settling should be less than 2%) and their grading will be 5 to 15mm and 15 to 25mm suited to various use.  If deemed necessary, it shall be washed before use.  Gravel particles of less 5mm retained in each of the above grades should not exceed 10% by weight. 
Gravel shall be free from dirt, clay or any organic, matter which should be less than 1.5% and if deemed necessary, it should be washed before use as indicated by the supervisor. 
A.4.4.  Sands 
Sands will have the characteristics specified in the tables relating to the type-approval tests.  Sands will be fine, granular and crunching on hand, not sticking.  They will get rid of any part earthy or limestone, of various waste, debris and wood. 
The nature and origin of sand remains a subject to the controller’s approval. The sand component should be more than 75% and the very fine constituents eliminated by settling should be less than 5%.  The sand should pass a standard sieve and must be of high quality and free from dirt, clay or any organic matter and if deemed necessary, it should be washed before use. 
· For mortar mixes the recommended standard sieve size is 2 to 2.8mm 
· For plaster mortar mixes the recommended standard sieve size is 2mm  For mass concrete mixes the recommended standard sieve is 5mm  For reinforced concrete mixes the recommended standard sieve is 5mm. 
A.4.4.  Cement. 
The cement will be CPA 45 or 45CPJ artificial Portland cements 215.425 standard P.15.402.  They will be delivered on site paper bagged six layers.  Any wet cement or having been altered by the humidity will be dismissed and removed immediately from the site. 

They shall be Ordinary Portland Cement, CPJ 45 manufactured only by CEMENCAM or any other national cement factory, obtained from an approved bulk cement supplier.  The bulk supplier must have not kept the cement in stock for more than two weeks.  The contractor shall not stock cement on the site for more than three months.  The cement must be stacked on 10cm wooden surface in a well ventilated store that is dry and warm, free from moisture.  The quality and state of cement shall be verified by the supervising engineer before use.  The use of imported cement is strictly prohibited. The contractor will inform the work of the constitution of its supplies. 

Conflicting samples will be carried out on each batch and submitted at the expense of the contractor to the tests prescribed by the standard P.15.401 of the AFNOR in a certified laboratory. Lots that do not possess characteristics required will have to be removed from the stock intended for work and evacuated from the site. 

BaGTC must be in good condition at the time of their installation on the site and retained areas covered, perfectly dry and an area of isolated boards of ten centimeter ground (10cm) to a minimum. 

A.4.5.  Water. 
The water used for construction purpose should be clean and free from any impurities which can affect the quality of the mixed materials.  It should therefore be fit for drinking and the mix ratio should range between 0.4 and 0. by weight and context. 

A.4.6.  Steel 
All frames or metal mesh implemented in concrete shall conform to the specifications of the 91 BAEL.  The steel will have the characteristics of the standard French 45.001AFNOR.  steels used on site will be the grade Fe E24 for mild steel and Fe E40 for high yield steels.  The bars will be cut to the shear. 

Bending will be cold, either manually or mechanically and diameter or greater than 42mm, provided that it is made use of control device in avoiding overheating and following the opinion of the representative of the control. 

Diameter of cores used for bending will be consistent with the BAEL 91 rules and the approval certificates.  The provisions of anchorage will be normal elbows 45º to return of square or double anchor elbow.  Used steels will be degreased and free of scale.  Bars with defects detrimental to their mechanical resistance, such as delamination, crack or chapped skin, will not be accepted. The reinforcements will be shaped to provide exactly the lengths and the forms provided by the drawings of the company. 

Assembly of the frames must be on the workshop of the site, but in a form of beam after implementation of the cheeks ever. 

Coverings of reinforcement to the shuttering walls will be 2.5cm for concrete in elevation.  Coverings of reinforcement to the shuttering walls will be 4cm for foundation concrete.  Coverings of reinforcement in concrete forms will be obtained using precast concrete spacers or plastic spacers that dimension will be adapted to the result to get. 

The concrete spacers include chevelus of attachment to the frame.  Ligatures and mounting bars will be sufficient to avoid any distortion of assembly frame, both during the manipulation at the pouring of concrete. 

In case of doubt on the quality of steels supplied on site, the employer or a representative of the contractor or, where applicable, the designated contractor may request, the responsibility of the company, to tests on samples taken on site.  The tests will be carried out by an approved body. For reinforcement of floor joists, all provisions will be taken to maintain the bars in the vicinity of support in a good position.  Employment in sufficient number of cross-sectional distributions will prevent this possible effect.  Recoveries shall conform to the requirements of the 91 BAEL. Reinforcement with no-adherent rust traces will be vigorously brushed before implementation in concrete forms.  Shaped or not reinforcement will be stored on some planks and not on the ground. The reinforcements will be supplied in minimum length of 12metres.  The reinforcement iron rods to be used will be mild or high yield steel.  No use of recycled and rusted reinforcement rods is permissible. A.4.6.  wood 
Wood for formwork: type white wood or equivalent 

Wood for scafold: type hard wood, moabi, mouvingui, frake or equivalent.  

A.5.  THE  CONCRETE. 
A.5.1  Quality of Concrete. 
Fifteen (15) days later after the opening of the construction site, and before any execution, the contractor shall submit to the National Laboratory “LABOGENIE” Civil Engineering or any other laboratory authorized by the control for approval, a composition of all concrete and mortars to be implemented, taking account of the materials delivered to the site. 

All concrete used in the foundations (lean concrete, mass concrete, stressed and pre-stressed….) will be executed with the CPJ 45 cement.  The composition of concrete implementation will be defined by 

an analysis of composition of FAURY, VALLETTA, DE DREUX of BOLOMAY methods, carried out by the National Laboratory of Civil Engineering.  The contractor shall bear the costs of new composition in laboratory studies.  All concrete for reinforced concrete must meet the conditions of required resistance.  The requirements are the following. -Characteristic of 28 days compressive strength; 20 bars 

-Resistance to traction at 28 days; 22 bars. 

In case these values are not obtained, the company will produce a supporting calculation note of security works concerned in accordance with the rules BAEL. 91.  Otherwise, it will request the demolition of the concerned works or their strengthening.  

A.5.2  Manufacture of concrete and mortar. 
The manufacture of concrete will be conducted by a central concrete to weight determination.  Whatever the manufacturing process used, the products obtained shall be homogeneous and perfectly coated aggregates of binders.  The duration of mixing to be sufficient to achieve the result intended; once this is achieved, the mixing should not be extended. 

The contractor will have any, realize a liquid concrete, given the decrease in resistance caused by excess water.  The implementation of dry concrete will be facilitated by the compulsory use of the vibrator. 

A sample of concrete taken directly in a waste will have to form a regular ball after quick reciprocating in the palm of the hand and detach easily from the latter without dirt.  Testing the cone may be imposed.  The water/cement ratio will be determined by the moisture of aggregates. 
Concrete: 
   Concrete works shall be of 4 types: 

i. Lean concrete for foundation works where indicated shall be PC 150kg/m4 and 75mm thick. 

ii. Mass concrete for floor works; All concrete in floor construction shall be 80mm/150mm thick and dosage of PC400kg/m4 

iii. Reinforced concrete for works above ground level and not submerged for beams, slabs,lintel,columns and pillar works shall be PC450kg/m4 with thickness as shown on the construction drawings. 

 Reinforced concrete for underground and submerged structure works including; beams, slabs and pillar works: All reinforced concrete work dosage in these locations shall be PC400kg/m4 

Underground concrete works shall be mixed with waterproof additives (Super Zaikalite-1kg powder imported) in recommended manufacturer’s dosage. 

Mortar: 
Mortar shall be a mixture of 250 (two hundred and fifty) kilogrammes of cement per cubic metre of dry sand. 

If the M250 mortar is more than 20 (twenty) millimeters thick, micro-concrete mixed with 400 

(three hundred) kilogrammes of cement whose composition shall first of all be submitted for the Supervisor’s approval shall be used. (Use mortar mixes for various structural components works as specified in project consulting documents available in the procurement unit of PNDP). 

A.5.4. Implementation of concrete. 
Concrete will be implemented as their manufacture; storage in containers requiring an addition of water at the time of employment is strictly prohibited concrete will be always carefully vibrated by cylindrical needles. 

Reinforcement nodes will be willing to allow a good implementation of the concrete on the height of the considered work.  The company will take all provisions to ensure an altimeter and a correct fixation of the steel to avoid their displacement during casting.  Similarly, it will add all bar mounts and ligatures for correct maintenance of the works (sheaths, tubes, pipes, boxes, cleats, preframes. etc) taken by itself or other bodies of state in concrete forms. 

The implementation of concrete will be made to the right of the beams and the sails.  Before casting of a recovery, the former concrete will be carefully disposed of all gravât the jet of air compressed, transplanted to overhang or project outboard gravels and eliminate milt, then washed if necessary, resumption of concrete additives used according to the sheet fact of the product.  No r resumption of concrete will be made in the visible parts of the works. 

Stripping of the works will be carried out when the concrete will have acquired sufficient strength. 

A.5.4. Test of Convenience. 
It will be executed on the site before the start of the work, a concrete witness to each “workshop” of concrete.  Workshop of concrete, consider a set determined position fixed or movable one site to another and which is served by a determined team fixtures.  The minimum number of tubes subjected to test is 9. 

The actual manufacture of concrete for the construction can start, after agreement of the control, if the nominal resistance to traction and compression to 7 days, are at least equal to 75/100 minimum resistance required in 28 days.  The typical 28 day compressive resistance must be at least equal to 270 bars.  Otherwise should immediately repeat the test with a new composition. 
A.5.5. Tests of concrete during work, test tube, 
They are defined in article  “Test of receipt of materials”. 

B.5.6.  Failure to implement, surface condition. 
For no-admissible by the Contracting Authority considered on concrete surface conditions, the contractor will have to run to exclusive costs a full patching of the corresponding works with a coating synthetic resin of the type SIKALATEX or equivalent.  Implementation and measurements of this coating must conform to the manufacturer’s technical background. 

NB:  (Concrete mixes for various structural component works as specified can be consulted from the Request for Financing Document at PNDP Procurement Unit upon award of contract). 

A.6.  FORMWORK 
A.6.1  General. 
All foundation concrete structures will be carried out in ordinary form unless otherwise directed by the Contracting Authority and unless otherwise indicated on the plans. 

(a) If the ordinary forms consist of simply juxtaposed sawn wood, the latter must be level and proper bearings.  The maximum gauge tolerated in joints is 2mm.  the maximum vertical normally tolerated a siding between two juxtaposed sawn wood plan will be of three millimeters. 

(b) If the ordinary forms are composed of panels of agglomerated wood or plywood simply juxtaposed fibres, these panels will be proper bearings and on the same level.  Joints tolerated between panels will be the same as between sawn wood.  The tolerances are those of DTU 24 mentioned in the chapter IV section A. 

A.6.2.  Forming holes. 
The holes and gaps to seal or for other purposes will be reserved by the establishment of appropriate forms, arranged so that all of their elements can be easily removed during stripping.  He will be allowed to use expanded polystyrene blocks. A.6.4.  Care before concreting. 
(a) Clean 
The forms do not have to be stained by hydrocarbon products, such as fat, greasy, wax or rust etc. The spots will be carefully removed if necessary with ease. 

(b)  Cleaning 
Immediately prior to the implementation of concrete, formwork will be cleaned carefully to remove dust and debris of all kinds. 

Finishing of cleaning will be provided for by the air compressor. 

(c)  Humidification 
Common wood forms will be heavily sprayed before implementation of the concrete. 

Watering will be conducted as needed in several phases spread to obtain as complete as possible of the wood humidification, which will aim to strengthen the joints by swelling of the wood. Wet surfaces shall however not be slick.  Excess water will be evacuated to compressed air. 

(d) Oil coating 
Will be oiled coated before implementation of concrete: 

· all metal formwork 

· the treated forms composed of plywood panel or wood agglomerate and all concrete fibre forms for curves. 

· The oil in excess at the bottom of mussels will be offset before concreting.  Used oils will be so-called special release oils. 

A.6.4.  Maintenance. 
If several jobs are planned for the same form, it will be perfectly cleaned and eventually returned in state before any new use. 

A.6.5.  Security staff and third parties. 
The concrete forms and structural elements, which after employment possess any nails or spikes or knobs will be immediately bald their points if they are intended to be re-used. 

Otherwise, they will be immediately burnt or stored out of the site, in a no-publicly accessible location. 

A.7.  Acceptance of materials testing. 
The DTU standards specify the result of the tests required on materials and their pace. 

The resistors mentioned in the tables correspond to characteristic resistance.  These tests must run by the Civil Engineering National Laboratory or any other laboratory approved by the MINTP, at the expense of the company. 
A.8  Pointing shall be applied to joints of all external stone masonry walls that are visible to be aesthetic. mortar shall be used for pointing, to give good cement finish. 

ORIGIN OF MATERIALS  
As shown on table 14 

CHAPTER TWO :  EXECUTION OF WORKS 

A.1.1.  General Instructions 
It should be noted that these specifications complete the construction plans and the construction plans complete the specifications.  The Supervisor shall give modifications to plans provided or technical specifications in writing.  For this purpose, a numbered page book shall be on site in which the instructions are written.  Both the contractor and the Supervisor shall initial the book pages.  Therefore, the contractor must execute the works in conjunction with the three documents.  The contractor shall take note of any omissions or discrepancies that may exist in the three documents and call the attention of the Supervisor who is at his disposal for necessary information and inquiries.  Any works carried out in negation of these instructions or provisions shall be demolished at the expense of the contractor. 

A.1.2. Security. 
The contractor shall be required to place at the entrance to the works site and in its vicinity, signboards indicating that work is underway and he shall be responsible for any accident that occurs on the works site and/or suffered by a third party, his staff and employees and officials of the Administration as a result of their presence of the works site.  Organization of work and security on the works site shall be the responsibility of the contractor. 

A.1.4. Traffic  
The contractor shall be responsible for ensuring that traffic is not obstructed on the entire stretch of his works site throughout the period of work up till provisional acceptance.  No obstruction of traffic shall be allowed for more than two hours.  Maintenance of traffic flow shall be the responsibility and at the expense of the contractor and in case of any breach of contract by the latter, the supervisor may bring in a third party to correct any faults.  All related expenses shall be borne by the contractor. 

Where interference with traffic is inevitable, the opinion of local administrative authorities shall be required for any obstruction for a given period. 

A.1.4.  Site clearance. 
The building site shall be cleared of grass, vegetable soil and tree stumps to prepare it for construction.  Roots of trees shall be completely removed and any vegetable matter before backfilling of the foundation.  The vegetable soil of 15cm should be completely cleared and piled aside before bringing back for landscaping and implementation of environmental aspects at the end of construction works. 

A.1.5.  Nomenclature of work (setting out of works) 
The contractor shall be responsible for the setting out of the constructions works, respecting environmental and water supply norms related to positioning and distances of stand taps stipulated in the distribution network plan.  He shall ensure accuracy in the positioning of the structures on the site.  It shall be checked and approved by the supervisor before any excavation work can begin. 

A.1.7. IMPLEMENTATION OF STRUCTURE 
Implementation of buildings will be provided by the company, and approved by the controller before any commencement of work.  Errors of elevations that implementation operations might reveal must be immediately reported to the employer to make the necessary changes to the smooth running of the site. 

A.1.8. MODIFICATION OF WORK. 
The contractor shall be deemed having sufficient knowledge of the conditions and context of the project and suggestions for the work. 

However, in cases where changes in the nature of earthworks prove necessary in work, either by the nature of the altitude of the land, or by the presence of obstacles, such as pipelines, remains, etc.  The Contracting Authority will define the impact on the schedule and the settlement of expenditure result from these changes.  The contractor shall continue the work with the agreement of the Contracting Authority.  

A.1.9. USE OF EXPLOSIVES 
The use of explosives is strictly prohibited. 

A.1.10. IMPLANTATION 
The bottom of the trenches must attain good sub-soil.  Foundations should rest on the bedrock.  If in the performance of excavations, there is water or the water seepage, the company will take any provision for the support of excavations and bailout the water entering these works. 

If the trenches are invaded by water of any kind whatsoever, the company must achieve the exhaustion, which will remain in his expense, and all the costs associated with the losses, both day and night, that will be needed for a good performance of the work. 

The soil to be used for backfilling would be the assessment of the controller and for other jobs in the work will be the contractor, brought to landfills from any place without special compensation regardless of the distance. 

It may be ordered application of backfilling in the right-of-way of the site without that there is place for special compensation. Embarkments around the excavations will be carried out with materials from excavations on the condition that it be approved by the control.  The backfilling around the works will be performed by successive layers of maximum 20cm thick, pounded, sprayed and compacted.  In case a contribution of land would be necessary, he will have to achieve healthy places and in all cases of sites approved by the controller.  It is prohibited to obtain soil-material from recent masonry work, to do these backfilling executed by hand to load the walls evenly and avoid all constraints that could result from a poorly distributed load. 
B-TECHNICAL CONDITIONS FOR EXECUTION 

1) STRUCTURE AND EXECUTION PLANS: It is the duty of the project owner to provide all the structure and the execution plans to the contractor. 

2) PRILIMINARY WORKS: The contractor shall obtain authorisations necessary for the realisation of works from the competent authorities. He shall also make contact with water and electricity authorities in case their lines shall be tampered with. 

3) INSTALLATION OF WORKSITE: The contractor shall furnish the owner of the job within the shortest possible time with an installation plan showing clearly how he intends to run the site.  

4) PROTECTION OF STRUCTURES AND MATERIALS: The contractor shall be responsible 

for the protection of the structures before final reception. He shall by equally responsible for all tools and materials present at the work site. He shall seek insurance cover for theft and fire. 

5) PRECAUTION AGAINST ACCIDENTS: The contractor shall take all preventive measures against accidents. The owner of the job reserves the right to intervene in case of emergency without necessary interfering with the responsibility of the contractor. 

6) VERIFICATION OF DIMENSIONS: The contractor shall verify all dimensions on the plans. For execution no dimension shall be measured with a scale rule from the plans. The contractor shall check in situ the possibility of translating the dimensions on plans to the structure before work begins. He shall refer to the Control Engineer in case of any doubt. He shall not on his own modify anything on the structure and shall inform the Control Engineer of all changes that he considers necessary. 

          All modifications accepted by the contractor shall be accomplished in a specified duration and at his cost without modification of the contract amount. The owner of the job shall have the right to the final choice in any modification. 

7) ERRORS AND OMISSIONS IN THE DOCUMENTS: The descriptions complete or confirm the indications on plans. In the case of contradictions between the plans and the description contact the Control Engineer for examination 

C-WORKS 

· Studies: After this feasibility studies by the consultant, the contractor has to carry out his/her own studies using the plans, specifications, bill of quatities, visit the site to have a mastery of the project before he/she can prepare a bid for the project. In case of an omission or an error his should indicate to the authorities concerned. 

· Execution documents: The following documents will be needed for the proper execution of works: 

· Tender document 

· A registered contract/jobbing order 

· Service order to start work 

· The working plans 

· Work execution program 

· Site log book/minutes book 

· As-built plan (at the end of works) 

 Mobilisation, site installation and implantation project  
The installation of the working site will be at the expenses of the executing enterprise.  It will include:   

· The construction or renting of a base were the equipment of the contractor shall be kept. 

· The construction of a provisional fence round the base;   

· Provisional water connections, electricity and telephone  

· The cleaning and the guarding of the project site  

· Providing and installation of 02 project sign boards very visible and displayed on positions indicated by the project manager. These site signboards shall be according to the model provided in the annexes.  

· Necessary measures for the respect of legal/lawful provisions relating to hygiene and safety on site.  (Installation of a latrine, provision of drinkable water, provision of a first aid box equipped with products such as:  aspirin, nivaquine, adhesive plaster, bétadine, bands, compress, alcohol...);   

· Provisional access roads to the project site;  

· A storeroom on site;  

· A site office, where the site book, the building plans will be available permanently throughout all realization of works;   

· An office or room of at least of 8 m² equipped with a table office and two chairs reserved with the Project superintendent;   

· A meetings room for the building site which can receive at least 5 people equipped with a table, two benches of 1.5 m, a display board for plans and planning placed permanently.  Receptacles to receive waste are to be installed near the various installations.  These receptacles are to be emptied periodically and waste to be deposited in a vat for recovery or a dump (pit).  This pit must be located at least 150m installations and in the event of presence of river with at least 150m.  At the end of work, the pit is to be filled with ground up to the level of the original ground.   

1  Preparatory  works 
1/1 Bush cleaing  

            The site shall be cleared of all grass to a height of not more than 5cm.  

1/2 Debris/Cleaning of water run way.  

The section to receive the structure and its surroundings shall be cleaned and free from all debris, mud, excess soil and others for easy flow of water through the bridge.  

1 /4 Installation of the work site. 

 
The installation of the site shall be done on a section agreed between the contractor and the Control Engineer together with the areas for stockpiling materials. The site shall be fenced with local materials and signboard mounted by the contractor. Access to the site shall be prohibited to the public. The contractor shall be responsible for the total security of the site. 

1/4 Implantation 
 
The contractor shall indicate the implantation of the structure according to the plans. This implantation shall be done in accordance with the Control Engineer. The contractor shall be responsible for errors of levels and alignments that were not signalled earlier. 

1 /5 Excavation 
           All trenches for foundation footings shall be excavated according to the plans. 

The foundation trenches shall be sunk to the good soil as indicated by soil studies and agreed by the Control Engineer. The trenches shall be shaped accordingly. 

1/6 Backfilling 
           All backfilling, where necessary shall be done with well-drained lateritic soil and compacted in layers of 20 cm successively.    

2/ Foundation 
2/1 Blinding Concrete 
 
A blinding concrete of 5 cm thick and a concrete mix of 150 kg of cement (CPA 425) per m4 shall be cast at the base of the hardcore.  

2/4 Reinforced Concrete foundation footings 
· The foundation footings shall be cast with R.C. of 450 kg of cement (CPA425) per m4.  

· Realization of the iron works, form work and concreting of  footings for the abutements and wing walls batched at  450 kg/m4 Formwork: 
Material for formwork shall be wood.  This shall be cut, shaped and assembled on site to the required forms and sizes.  Simple conventional wooden formwork shall be used in the construction of the various concrete structural elements (footings, slabs, beams, etc.).  These shall be fabricated in-situ and, lifted into position.   
4/Abutments 
· Building of stone masonry aabutments which shall be built with shaped stones and cement mortar dosed at 400kg/m4  Provision of weep holes 

4/Decking of the bridge 

The bridge shall be decked with the following 
· The bridge beams with IPE 500 and brace with with IPE 400 .  

· Reinforced concrete deck dosed at 400 kg/m4 

· Provision of drainage holes to drain off water 

· Shaping of the bridge deck so the easy evacuation of water 

   5/Equipment 

· Mixed handrails of reinforced concrete and 50mm metallic poles built according to the laid down norms and painted. 

· Reinforced concrete deck dosed at 400 kg/m4 

· Provision of drainage holes to drain off water 

· Shaping of the bridge deck so the easy evacuation of water 

6/Finishes and protection of embankments 

6/1 Pointing  
Shall be applied to joints of all external stone masonry walls that are visible to be aesthetic including the wing walls. Mortar shall be used for pointing, to give good cement finish. 

6/2 Planting of grass  
Grass shall be planted along the backfilled wing walls of the abutment for protection. 

7/ Maintenance for the project  

After the provisional acceptance of works the contractor is still responsible for the maintenance of the structure for a minimum of 12 months from the date of provisional acceptance. This maintenance includes repairing cracks on the structure, functioning of the weep holes, replacement of demange signs and hand rails, repainting of repaired portions.  

After the final acceptance of works of the contractor, the maintenance of the structure is now the responsibility of the project management committee by making sure the structure is at all times ready for use. 

8/ Filling From Borrow Pit: These works shall comprise of: the Provision of selected material (laterite) from an approved borrow pit;  Spreading of the material on the road surface with the use of trucks and graders;  Watering of the road surface containing the material and  

Compaction of the material with a cylinder compactor upto obtaining a compaction of 95%OPM and a thickness of 20cm.  

The approval of the material and the borrow pitsshall be done at least two (02) weeks before the start of this activity. At the end of this activity, the road surface should be moulded with a slope of 

4% and shall present a convex (curved outwards) shape to avoid water stagnation and enable drainage of the water into the road side gutters for onward freeflow evacuation. 

HEALTH AND SAFETY AT WORK  

 
A first aid team will handle injuries sustain by workers during work while critical cases will be taken to any nearby hospital. To avoid accidents on the project site, we shall ensure that all our workers and visitors on site are in position of helmets, safety boots and jackets.  During weekly site meetings, safety topics will be introduced to all the workers on site.  The Population and our workers will be sensitized against the aids pandemic and other sexually transmitted diseases. Prevention shall be our watch word. 

SITE SECURITY 

A direction board displaying site installation element, circulation trend, display of position housing material deposit, offices and other facilities will future at the construction site.  Access roads easing internal circulation within the base and working areas will be constructed in proximity of services, operating positions of warehouses, fabrication posts, offices, recreational areas and material stockage areas to assure internal security of personnel’s.  Temporal structures of wood will be put up to house offices, workstations, warehouses, dressing rooms conference room for site meetings and fabrication post. A temporal wooden fence will be put in place around the base boundary location.  Concreting materials such as sand, gravel, cement, concrete mixer and rod bending production post will be position in function of task operation.    Environmental conservation, security measures and life protection will constitute our watchword fixed at all offices, production post and open areas. 
CHAPTER FOUR: MECHANISMS FOR THE PROTECTION OF THE                                                           ENVIRONMENT     
              The contractor will propose to the control engineer, before the beginning of works, the place of his yard facilities and will request his authorization of installation.    

The site must be chosen outside of the sensitive zones, in order to limit the site clearing, the extraction of bushes, the setting out of the structure and general circulation. The site must foresee an adequate drainage of waters on the whole surface.  

At the end the works, the entrepreneur will do all necessary works to the restoration of the various places of the site. The entrepreneur should fold all his material, and equipment. He should demolish all stationary installation, as foundation, slab, support made of wood or metallic, etc.. in order to put back the site in its nearest initial state. No equipment nor materials should be abandoned on the site, nor in the vicinity after the execution of all the works.  Left-over materials are to be covered with a layer of earth, and the site has to receive an adequate drainage in order to avoid all erosion as the case may be. 
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Schedule of unit prices

	UPS FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION  

	N°
	DISCRIPTION OF WORKS
	Unit
	Qty
	U.P IN FIGURES
	U.P IN WORDS

	SERIES 000
	 SITE INSTALLATION
	 
	 
	 
	 

	TM001
	Site installation
	FF
	1.0
	
	

	TM002
	Transporting of the Equipments to and From
	FF
	1.0
	
	

	 
	Sub Total Installation
	 
	 
	
	

	SERIES 100
	CLEANING AND LEVELLING
	 
	 
	
	

	TM101
	Clearing
	m2
	300.0
	
	

	TM108a
	Backfilling with laterite gravel from borrowed pit
	m3
	400.0
	
	

	 
	Sub Total Cleaning and Levelling
	 
	 
	
	

	SERIES 300
	DRAINAGE
	 
	 
	
	

	TM304
	Cleaning the river way
	m3
	120.0
	
	

	TM314
	Anti errosion protection(hard core)
	m3
	150.0
	
	

	TM315
	Weep holes
	u 
	60.0
	
	

	 
	Sub total drainage
	 
	 
	
	

	SERIES 400
	ENGINEERING STRUCTURES
	 
	 
	
	

	TM407
	Ordinary site excavation
	m3
	200.0
	
	

	TM413
	Continuous backfilling of the structures
	m3
	150.0
	
	

	TM409b
	Stone work for abutment 3m<H<4m
	U
	2.0
	
	

	TM409b
	Intermidiate stone work for abutment 3m<H<4m
	U
	1.0
	
	

	TM423a
	Lean concrete dosed at 200kg/m3
	m3
	11.0
	
	

	TM423f
	Reinforced concrete dosed at 400kg/m3
	m3
	91.0
	
	

	TM430d
	Putting in place beams of IPE 500
	ml
	90.0
	
	

	TM430b
	Putting in place beams of IPE 400
	ml
	24.0
	
	

	TM431a
	Ordinary formwork
	m2
	75.0
	
	

	TM431b
	Neat formwork
	m2
	110.0
	
	

	TM433
	 HA25 steel or equivilent Anchored  to the rock
	U
	30.0
	
	

	TM438
	Drain holes
	U
	20.0
	
	

	TM441
	Geotechnical studies and executing documents
	ff
	1.0
	
	

	 
	Sub total Engineering structures
	 
	 
	
	

	SERIES 500
	SIGNALISATION AND SECURITY EQUIPMENT
	 
	 
	
	

	TM501c
	Mixed hand rail with 75mm pipe
	ml
	36.0
	
	

	TM516a
	Type A metallic sign board
	u
	2.0
	
	

	TM528a
	Wooden poles
	u
	8.0
	
	

	TM528b
	Reinforced concrete poles
	u
	4.0
	
	

	 
	Sub total Signalisation and security equipment
	 
	 
	
	

	SERIES 600
	DIVERS
	 
	 
	
	

	TM606a
	Anti rust paint
	m2
	110.0
	
	

	TM606b
	Oil paint
	m2
	55.0
	
	

	 
	Sub total Divers
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 Bill of quantities and estimates

	BILL OF QUANTITIES AND ESTIMATES FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION  

	N°
	DISCRIPTION OF WORKS
	Unit
	Qty
	U.P
	AMOUNT

	SERIES 000
	 SITE INSTALLATION
	 
	 
	 
	 

	TM001
	Site installation
	FF
	1.0
	
	

	TM002
	Transporting of the Equipments to and From
	FF
	1.0
	
	

	 
	Sub Total Installation
	 
	 
	
	

	SERIES 100
	CLEANING AND LEVELLING
	 
	 
	
	

	TM101
	Clearing
	m2
	300.0
	
	

	TM108a
	Backfilling with laterite gravel from borrowed pit
	m3
	400.0
	
	

	 
	Sub Total Cleaning and Levelling
	 
	 
	
	

	SERIES 300
	DRAINAGE
	 
	 
	
	

	TM304
	Cleaning the river way
	m3
	120.0
	
	

	TM314
	Anti errosion protection(hard core)
	m3
	150.0
	
	

	TM315
	Weep holes
	u 
	60.0
	
	

	 
	Sub total drainage
	 
	 
	
	

	SERIES 400
	ENGINEERING STRUCTURES
	 
	 
	
	

	TM407
	Ordinary site excavation
	m3
	200.0
	
	

	TM413
	Continuous backfilling of the structures
	m3
	150.0
	
	

	TM409b
	Stone work for abutment 3m<H<4m
	U
	2.0
	
	

	TM409b
	Intermidiate stone work for abutment 3m<H<4m
	U
	1.0
	
	

	TM423a
	Lean concrete dosed at 200kg/m3
	m3
	11.0
	
	

	TM423f
	Reinforced concrete dosed at 400kg/m3
	m3
	91.0
	
	

	TM430d
	Putting in place beams of IPE 500
	ml
	90.0
	
	

	TM430b
	Putting in place beams of IPE 400
	ml
	24.0
	
	

	TM431a
	Ordinary formwork
	m2
	75.0
	
	

	TM431b
	Neat formwork
	m2
	110.0
	
	

	TM433
	 HA25 steel or equivilent Anchored  to the rock
	U
	30.0
	
	

	TM438
	Drain holes
	U
	20.0
	
	

	TM441
	Geotechnical studies and executing documents
	ff
	1.0
	
	

	 
	Sub total Engineering structures
	 
	 
	
	

	SERIES 500
	SIGNALISATION AND SECURITY EQUIPMENT
	 
	 
	
	

	TM501c
	Mixed hand rail with 75mm pipe
	ml
	36.0
	
	

	TM516a
	Type A metallic sign board
	u
	2.0
	
	

	TM528a
	Wooden poles
	u
	8.0
	
	

	TM528b
	Reinforced concrete poles
	u
	4.0
	
	

	 
	Sub total Signalisation and security equipment
	 
	 
	
	

	SERIES 600
	DIVERS
	 
	 
	
	

	TM606a
	Anti rust paint
	m2
	110.0
	
	

	TM606b
	Oil paint
	m2
	55.0
	
	

	 
	Sub total Divers
	 
	 
	
	

	 

	 
	TOTAL WITHOUT TAXES
	

	 
	VAT (19.25%)
	

	 
	 AIR (2.2%)
	

	 
	TOTAL (TTC)
	

	 
	NET TO BE PAID
	

	CLOSED THE PRESENT ESTIMATE AT THE SUM OF: 
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Schedule of sub-detail of prices
Schedule of sub-detail of prices
	DESIGNATION 

	No 
	Daily out put
	Total quantity
	Unit
	Duration of activity

	 
	 
	No
	 
	 
	 

	WORKMAN SHIP
	Category
	
	Daily wage
	Days break up
	Amount

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	 
	 
	 
	 
	 

	
	 
	 
	 
	 
	 

	
	 
	 
	 
	 
	 

	
	 
	 
	 
	 
	 

	
	TOTAL A
	 

	EQUIPMENT/MECHINES
	Type
	No
	Daily rate
	Days break up
	Amount

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	TOTAL B
	 

	MATERIAL AND MISCELLANOUS
	Type
	Unit
	Unit cost
	Quantity
	Amount

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	
	 
	
	
	

	
	 
	 
	 
	 
	 

	
	 
	 
	 
	 
	 

	
	 
	 
	 
	 
	 

	
	 
	 
	 
	 
	 

	
	 
	 
	 
	 
	 

	
	TOTAL C
	 

	D
	DIRECT TOTAL COST                                       
	A+B+C
	 

	E
	GENERAL SITE EXPENESES
	Dx%
	 

	F
	GENERAL OFFICE EXPENSES
	Dx%
	 

	G
	NET COST
	D+E+F
	 

	H
	RISK + BENEFITS
	Gx%
	 

	P
	TOTAL COST (HT)
	G+H
	 

	V
	UNIT COST (HT)
	P/Q’TY
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Model contract

	RÉPUBLIQUE DU CAMEROUN

Paix – Travail – Patrie

-----------
	
	REPUBLIC OF CAMEROON

Peace – Work – Fatherland

-----------

	RÉGION DU NORD OUEST 

----------------
	
	NORTH WEST REGION 

----------------------------

	DÉPARTEMENTALE DE MOMO 

-----------------------
	
	MOMO DIVISION

-----------------------------------

	PREFECTURE DE LA MOMO

----------------------------
	
	DIVISIONAL OFFICE BATIBO 

----------------------------

	SERVICE DES AFFAIRES

ECONOMIQUES ET FINANCIERES


	
	SERVICE FOR ECONOMIC

AND FINANCIAL AFFAIRS




CONTRACT  N°:______________________ OF ___/___/2024
AWARDED AFTER OPEN NATIONAL INVITATION TO TENDER, EMERGENCY PROCEDURE  N° 02/ONIT/NW06/DTB/2024 OF ____/___/2024
FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION
Project Owner [Indicate name and full address]
HOLDER


: [indicate name and full address of holder]

P.O. Box_________, Tel:_________Fax: ____________

Business Registry No.___________at

Taxpayer’s No._____________

SUBJECT                   : Execution of ______________works;

Lot No.__________; Network______________
PLACE



:Region_____________________________

EXECUTION DEADLINE :_____________________(_______) months

AMOUNT IN CFA F:

	IAT
	

	EVAT
	

	VAT 
	

	AIR (Income tax)
	

	Net to be paid
	


FINANCING

: [indicate the source of financing]

BUDGET HEAD
: [to be completed]





SUBSCRIBED ON:________________





SIGNED ON:_____________________





NOTIFIED ON:___________________





REGISTERED ON:_________________
Between:

The Government of the Republic of Cameroon, represented by________________ hereinafter referred to the “Contracting Authority”

On the one hand,

And

 ______________________(enterprise)

P.O. Box________Tel:_________Fax:_________

Business Registry No. ___________

Taxpayer’s No. ___________________

Represented by M _________________, its General Manager, hereinafter referred to as the “Contractor”

On the other hand,

Agree on the following:

Summary

Part I:
   Special Administrative Conditions (SAC)

Part II:   Special Technical Conditions (STC)

Part III:  Schedule of Unit Prices (SUP)

Part IV:  Details or Estimates 

Page_______ and last of CONTRACT  N°:______________________ OF ___/___/2024
AWARDED AFTER OPEN NATIONAL INVITATION TO TENDER, EMERGENCY PROCEDURE  N° 02/ONIT/NW06/DTB/2024 OF ____/___/2024
FOR THE CONSTRUCTION OF A 18M BRIDGE OVER RIVER MUNAM AT PK 0+150 ON MUNAM -GUFOM ROAD, MBENGWI SUB DIVISION, MOMO DIVISION, NORTH WEST REGION

With __________,

For the execution of _______________works




Lot No.________; _______________Network

EXECUTION DEADLINE: ____________(______) months

Amount of contract in CFA F:

	IAT
	

	EVAT
	

	VAT (
	

	AIR (2.2% or 5.5 %)
	

	Net to be paid
	


	Read and accepted by the contractor

(place of signature)__________(date)

	Signature of Contracting Authority

                                   (place of signature)__________(date)

	Registration
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Forms and models to be used by bidders

Table of models

Annex No. 1: Model tender

Annex No. 2: Model bid bond

Model No. 3:  Model final bond

Model No. 4:  Model of start-off advance bond

Model No. 5:  Model retention fund

Annex No. 6:  Framework of schedule 

Annex No. 7:  Evaluation grid

Annex No. 8:  Attestation of site visit

Annex No. 1: Model tender

I, the undersigned______________[indicate the name and capacity of  signatory]

Representing the ______________company or enterprise or group with head office at_____________ registered in the trade register of____________ under the number No_________

Having taken cognisance of all the documents featured or mentioned in the Tender File including the addendum (addenda): the invitation to tender [recall the subject of the invitation to tender]
· After having personally taken account of the situation of the site and evaluated from my point of view and under my responsibility, the nature and difficulty of the works to be carried out;

· Hereby submit, bearing my signature, the schedule of unit prices as well as the quotations in accordance with the structure featuring in the Tender File.

· Submit and commit myself to execute the works in accordance with the Tender File, in return for  the prices which I myself establish for each type of structure which prices reveal the amount of the tender for lot No. ________ at _______________[in figures and words] CFA francs exclusive of VAT and at ________________CFA francs Inclusive of all Taxes. [In figures and words].

· I pledge to execute the works within a deadline of ……………months.

·  I pledge to maintain my bid for [indicate duration of validity, in principle 90days for national invitations to tender 120 days for international invitations to tender] from the deadline of submission of bids.

· Rebates and the modalities of application the said rebates shall be the following (in case of the possibility of award of several lots).

The Delegated Project Owner shall pay the sums due for this contract by crediting account No…………………… opened in………………………Bank………………………..Branch

Prior to the signing of the contract, this tender accepted by you shall constitute an agreement between us.

Done at....................................... on.....................................

ANNEX No. 2: MODEL BID BOND

Addressed to [indicate the Contracting Authority and his address] “Contracting Authority”

Whereas the undertaking _____________ hereinafter referred to as the “bidder” has submitted his bid on __________for [recall the subject of the invitation to tender], hereinafter referred to as “the bid” and to which must be attached a bid bond equivalent to [indicate the amount] CFA francs.

We___________ [name and address of the bank], represented by _________[names of signatories], hereinafter referred to as “the bank” hereby guarantee payment to the Contracting Authority of the maximum sum of [indicate the amount] CFA francs, that the bank pledges to pay in full to the Contracting Authority, binding itself, its successors and assignees.

The conditions of this commitment are as follows:

If the bidder retires his bid during the validity period provided for in the Tender File;

Or

If the bidder, having been notified of the award of the contract by the Contracting Authority during the validity period:

· Fails or refuses to sign the contract, even though required to do so;

· Fails or refuses to furnish the final bond for the contract (final bond) as provided for by the contract;

We pledge to pay to the [Contracting Authority] an amount up to the maximum of the sum referred to above upon reception of the his first written request, without the Contracting Authority having to justify his request, given, however, that in his request the Contracting Authority shall note that he is due the amount he is claiming because one or the other or both of the above condition(s) has (have) been fulfilled and he shall specify which condition(s) took effect.

This bond shall enter into force from the date of signature and from the date set by the Contracting Authority for the submission of bids. It shall remain valid up till the thirtieth day inclusive following the end of the deadline for the validity of bids. Any request by the Contracting Authority to cause it to take effect should reach the bank by registered mail with an acknowledgement of receipt before the end of this period of validity.

This bond shall, for purposes of its interpretation and execution, be subject to Cameroon law. Cameroon courts shall be the only jurisdictions competent to rule on this commitment and its consequences.

Signed and authenticated by the bank at____________, on____________

[Bank’s signature]

Annex No. 3: Model final bond

Bank:

Reference of the bond: No_____________________

Addressed to [Indicate the Project Owner and his address] Cameroon, hereinafter referred to as the “Project Owner”

Whereas ________________ [name and address of Contractor], hereafter referred to as “the Contractor”, has committed himself, in execution of the contract referred to as “the contract”, to carry out [indicate the nature of the works].

Whereas it is stated in the contract that the Contractor shall entrust to the Project Owner a final bond of an amount equal to [indicate the percentage between 2 and 5%] of the amount of the corresponding portion of the contract, as guarantee of the execution of his full obligations in accordance with the terms of the contract,

Whereas we have agreed to issue the Contractor this guarantee,

We, __________________________   [name and address of bank]
represented by______________________ [name of signatories],

hereinafter referred to as “the bank”, commit ourselves to pay the Project Owner, within a maximum deadline of eight (8) weeks, upon the simple written request declaring that the Contractor has not satisfied his contractual commitments within the meaning of the contract, without being able to defer the payment nor raise any contests for whatever reason, any sum up to the sum of _____________  [in figures and words] .

We agree that no change or addendum or any other amendment to the contract shall free us of any obligation incumbent on us by virtue of this final bond and we hereby incline to any notification, addendum or change. 

This final bond shall enter into force upon signature and notification of the contract. It shall be released within a deadline of [indicate the deadline] from the date of the provisional acceptance of the works.

After this date, the bond shall be baseless and should be returned to us without the express request on our part.

Any request for payment made by the Project Owner by virtue of this guarantee should be done by registered mail with acknowledgement of receipt to reach the bank during the period of validity of this commitment.

This bond shall, for purposes of its interpretation, be subject to Cameroon law. Cameroon courts shall be the only jurisdictions competent to rule on this commitment and its consequences.

Signed and authenticated by the bank at _________  on __________________

[Signature of the bank]

ANNEX No. 4: Model of start-off advance bond

Bank: reference, address________________________________________________

We, the undersigned, (bank, address) hereby declare by the present to guarantee on behalf of______________________________________________ [the holder] to the benefit of the Project Owner [address of the Project Owner]

(the beneficiary)

The payment, without contest and upon receipt of the first written request by the beneficiary, declaring that____________[the holder] has not fulfilled his obligations relating to the reimbursement of the start-off advance according to the terms of contract No._________ of _____________ relating to ________________ works [indicate the subject of the works, the references of the invitation to tender and the lot, if possible] of the total sum corresponding to to the advance of [twenty (20) %] of the amount inclusive of all taxes of contract No. _____________, payable upon notification of the corresponding Administrative Order that is, _____________CFA francs.

This bond shall enter into force and shall take effect upon reception of the respective parts of this advance into the accounts of____________ [the holder] opened in the_________________ bank under No. ___________________.

This bond shall remain in force up till the reimbursement of the advance in accordance with the SAC. However, the amount of the bond shall be proportionately reduced on the progressive reimbursement of the advance.

The applicable law and jurisdiction shall be those of the Republic of Cameroon.

Signed and authenticated by the bank at______________ on _____________

[Signature of the bank]
ANNEX No. 5: Model of performance bond (Retention fund)

Bank: ____________

Reference of the bond: No________________

Addressed to [Indicate the Delegated Project Owner]
[Address of Contracting Authority]
Hereinafter referred to as “the Project Owner”

Whereas________________ name and address of Supplier] hereinafter referred to “the contractor”, pledged, in execution of the contract, to carry out the works of [indicate the subject of the works]
Whereas it is stipulated in the contract that the retention fund fixed at [percentage below 10 % to be specified] of the amount of the contract may be replaced by a joint guarantee,

Whereas we have agreed to provide the Contractor with this guarantee,

We,____________________________________ [name and address of the bank],

Represented by _________________________ [names of signatories] and hereinafter referred to as “the bank”,

Hence, we hereby affirm that on behalf of the Contractor, we guarantee and are responsible to the Project Owner for a maximum amount of______________________________

[in figures and letters] corresponding to [percentage below 10 % to be specified] of the contract price.

And we pledge to pay to the Project Owner within a maximum deadline of eight (8) weeks upon his simple written request declaring that the contractor has not fulfilled his contractual obligations or is indebted to the Delegated Project Owner within the meaning of the contract, amended where need be, by its additional clauses, without being able to defer the payment nor raise any contest for whatever reason, any sum(s) within the limits of the amount equal to [percentage below 10 % to be specified] of the total amount of the works featuring in the final detailed account, without the Delegated Project Owner having to prove or give the reasons nor the motive for the amount of the sum indicated above.

We hereby agree that no change or addendum or any other amendment shall release us of any obligation incumbent on us by virtue of this bond and we hereby incline by the present to the notification of any amendment, addendum or change.

This bond shall enter into force upon signature. It shall be released within thirty (30) days from the date of the final acceptance of the works and upon release issued by the Project Owner.

Any request for payment made by the Delegated Project Owner by virtue of this bond should be done by registered mail with acknowledgement of receipt to reach the bank during the period of validity of this commitment.

This bond shall, for purposes of its interpretation and execution, be subject to Cameroon law. Cameroon courts shall be the only jurisdictions competent to rule on this pledge and its consequences.

  Signed and authenticated by the bank at__________ on _______

[Signature of the bank]
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 Preliminary studies

[To be systematically filled by the Delegated Project Owner based on the nature of services to be executed and according to the specifications of Point 5.a of Circular No. 003/CAB/PM of 18 April 2008 relating to the respect of rules governing the award, execution and control of public contracts]

Note on preliminary studies
In accordance with the Public Contracts Code, the Delegated Project Owner or Delegated Project Owner must, prior to commencing the procedure to award contracts or refer to the competent Tenders Board, ensure that draft tender files are prepared based on preliminary studies.

These studies must be required during the examination of the Tender File (TF) by the Tenders Board.

The Delegated  Project Owner is bound to fill the questionnaire in annex 1 accompanied by justifications of the said studies.

Annex No. 7: Justification of preliminary studies

1. Attach the preliminary studies.

2. Indicate

2.1. The date studies were carried out;

2.2. The name of the public or private Project Manager

2.3. References of the contract, if Private Manager  carried it out;
2.4. If  maintenance works

2.4.1  Description of the studies;

2.4.2 Attach the outline of the itinerary bringing out readings of degradations as well as the approved programming documents.
2.5 Rehabilitation or new works

2.5.1 Are quantities in the quotations the same as those of the studies?

2.5.2 Description of studies: Draft Preliminary Study, Detailed Preliminary Study;

2.5.3 Attach the said studies.
N.B.  For services of less scope, the Delegated  Project Owner may furnish a justification of calculation of quantities of the tender file.

· The chairperson of the Tenders Board may, before taking a decision, seek expert advice on the quality of the studies.
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List of banking establishments and financial bodies authorised to issue bonds for public contracts

I- BANKS

1. Afriland  First   Bank

2. Banque Atlantique
3. Banque Gabonaise pour le Financement International (BGFI BANK)

4. Banque International du Cameroun pour l’Epargne et le Crédit (BICEC)

5. CITI Bank

6. Commercial Bank of Cameroon (CBC)

7. Ecobank

8. National Financial Credit Bank
9. Société Camerounaise de Banque au Cameroun

10. Société Générale de Banque au Cameroun

11. Standard Chartered  Bank Cameroon

12. Union Bank of Cameroon

13. United Bank for Africa.

II- Insurance companies

14. Chanas   Insurance;

15. Activa Insurance
16. ZENITHE Insurance

17. AREA INSURANCE
ANNEX 7: EVALUATION GRID

ADMINISTRATIVE DOCUMENTS.

	DOCUMENT N°
	DESCRIPTION

	A.1
	Certified Copy of the Business Registration, not more than three months old.

	A.2
	Declaration of intention to tender stamped with the tariff in force (written by the bidder).

	A.3
	Certificate of non-bankruptcy established by the Court of 1st instance or the Chamber of Commerce, Industry and Trade of the place of residence of the bidder, not more than three (03) months.

	A.4
	Attestation of bank account of the bidder, issued by a first rate-bank approved by the Ministry in charge of Finance or by a foreign bank the first order not more than three months. 

	A.5
	Purchase receipt of tender file issued by public treasury

	A.6
	A bid bond of 2,544,437 FCFA (Two million five hundred and forty four thousand four hundred and thirty seven FCFA), certified cheque or bank cheque issued by a first rate-bank approved by the Ministry in charge of Finance in conformity with COBAC conditions

	A.7
	An attestation of non-exclusion from Public Contracts issued by the Public contract Regulatory 
Board (ARMP)

	A.8
	An Attestation of the National Social Insurance Fund stating that the bidder has met all his obligations vis a vis the Fund; the attestation should be less than three months old.

	A.9
	Attestation of fiscal conformity

	A.10
	Certified Copy of a valid taxpayers card, delivered by the chief of center of Taxes. 

	A.11
	Plan and attestation of location of the Company


The absence or the non-conformity of the one of these documents will result to the elimination 

of the offer either during the opening session of the bids (absence of bid bond) or during the evaluation
The second Internal Envelope shall be labeled <<ENVELOPE B:  TECHNICAL DOCUMENT>> and shall contain the following: 

	B.1
	 General presentation of the tender files

	· Document spirally bound
· Neatness and clarity of documents
· Page numbering
· Table of content page
· Colour sheets separation
· Presentation of documents in the order given in this tender
	
	

	B.2
	LIST OF REFERENCES OF THE ENTERPRISE IN SIMILAR JOBS 

	B.2.1
	List of references of the enterprise in similar jobs justified by certified true copies of contracts (first and last pages) and minutes of reception or attestation of clearances of works executed. Minimum of two contracts realized in the domain of building construction over the past five years 

	
	1st Reference ≥ 50,000,000frs
	
	

	
	2nd  Reference≥ 20,000,000frs
	
	

	B.3
	QUALIFICATION AND EXPERIENCE OF SUPERVISORY STAFF 

	B.3.1
	01 works supervisor (at least Degree or equivalent certificate)

	.
.
.
	Qualification of the works supervisor: (Senior Technician certificate in Civil or Rural Engineering (BAC +3)
	
	

	
	Professional experience of the project engineer ≥ 03 years (signed CV)
· CV signed by the candidate, 
· A certified copy of the technical diploma 
· An attestation of availability signed by the candidate

	
	

	B.3.2
	01 Site foreman(Senior Civil Engineering BAC+2)

	
	Qualification of the Site foreman: (Technical certificate in civil engineering         (BAC+2 or equivalent certificate)
	
	

	
	Professional experience of the Site foreman ≥ 03 years (signed CV)
A certified copy of 
· CV signed by the candidate, 
· A certified copy of the technical diploma 
· An attestation of availability signed by the candidate

	
	

	B.3.3
	Other personnel

	
	· 01 one civil engineering technicain with 3 years professional experience in building construction or similar works Only( CVs signed by the candidate + copy of certificate)
(Must be holders of  at least BAC F4 certificate)
	
	

	
	· 01one Carpenter with 3 years professional experience on carpentry or similar works. Only (CVs signed by the candidate+ copy of certificate)
(Must be holders of  at least CAP certificate)
	
	

	B.4
	METHODOLOGY

	B.4.1
	Organizational chart of the enterprise/site with comments
	
	

	B.4.2
	Planning of work execution with comments

-origin of materials


	
	

	B.4.3
	Methodology of execution of works
	
	

	B.4.4
	Safty measures
	
	

	B.4.5
	Himo/maintenance measures
	
	

	B.5
	LOGISTICS (Equipment put aside for this project)
	
	

	B.5.1
	Prove of ownership or rental of a pick-up or other vans
	
	

	B.5.2
	Prove of ownership or rental of a dump truck
	
	

	B.5.3
	Prove of ownership or rental of a Concrete mixer
	
	

	B.5.4
	Prove of ownership or rental of a concrete vibrator
	
	

	B.5.5
	Prove of ownership or rental of a Hand compactor
	
	

	B.5.6

	Masonry Kit : Wheelbarrows, masonry clamps, masonry harmer 300g, shovel, dig axe, building level, masonry bucket , trowels, etc.
	
	

	
	Carpentry Kit  : carpentry clamps, saws, harmers, etc.
	
	

	B.6
	FINANCIAL CAPACITY
	
	

	B.6.1
	An attestation of financial capacity (solvency) of the enterprise issued by a 1st class bank located in any area in Cameroon and approved by the Ministry of Finance and respect COBAC conditions. 25% of amount = 31,806,000 or more
	
	

	B.7
	Attestation of site visit signed by the company administrator or engineer
	
	

	B.8
	Comprehensive report of site visit signed by the company administrator or engineer 
	
	

	B.9
	Special Technical Clauses initialed in all the pages and last page signed
	
	

	B.10
	Special Administrative Clauses completed and initialed in all the pages and last page signed 
	
	


ENVELOPE C- FINANCIAL FILE

	No.
	DESIGNATION.

	C1
	A submission letter, signed, dated and stamped.(see ANNEX 3)

	C2
	Completed and signed frame work of unit prices. 

	C3
	Signed Bills of quantities and cost estimates indicating the total amount without taxes (HT) and with taxes (TTC) 

	C4
	Sub details of unit prices


This evaluation will be done in a purely binary method; (yes) or (no) with an acceptable minimum from at least 75% of the essential criteria taken in account.
The contract will be awarded to the bidder who would have proposed the offer with the lowest amount, in conformity with the regulations of the Tender Documents and having satisfied to 100% of the eliminatory criteria and at least 75%of the essential criteria. 
Eliminatory criteria

1. Absence bid bond(from bank only) in the administrative file; 

2. No purchase receipt Momo Divisional Tresury

3. No reference ≥ 50,000,000frs in this domian(Momo Division)

4. Deadline for delivery higher than prescribed; 

5. False declaration or falsified documents; 

6. A bid with the external envelope carrying a sign or mark leading to the identification of the bidder; 

7. Incomplete financial file; 

8. Change of quantity or unit; 

9. Suspended by MINMAP or ARMP in 2024. 

10. Non respect of 75%of essential criteria;

During the opening session of the bids if a document of the administrative bid is absent or noncompliant, the bidder will be given fourty eight (48) hours to produce or replace said document else will be eliminated during the evaluation of the bids. No such document will be accepted after this deadline.

(a) Essential criteria

1. General presentation of the tender files; 

2.  Financial capacity; 
3. References of the company in  similar achievements;
4. Quality of the personnel;  
5. Technical organization of the works;
6. Safety measures on the site;
7. Logistics;
8. Attestation and report of site visit;
9. Special Technical Clauses initialed in all the pages;
10. Special Administrative Clauses completed and initialed in all the pages.
11.  Main qualification criteria
The criteria relating to the qualification of candidates could be indicative on the following:

The essential criteria are subjected to minima whose detail is given in the Special Tender Regulation (RPAO).

This evaluation will be done in a purely binary method; (yes) or (no) with an acceptable minimum from at least 75% of the essential criteria taken in account.

The contract will be awarded to the bidder who would have proposed the offer with the lowest amount, in conformity with the regulations of the Tender Documents and having satisfied to 100% of the eliminatory criteria and at least 75% of the essential criteria.

Abnormally low costing will be rejected as per the special tender regulations 
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Plans/technical drawings

2

