| REPUBLIC OF CAMEROON Peace-Work-Fatherland …………….. NORTH-WEST REGIONAL ASSEMBLY …………….. REGIONAL EXECUTIVE COUNCIL …………….. PEACE-JUSTICE-UNITY-HARD WORK- SOLIDARITY …………….. |  | REPUBLIQUE DU CAMEROUN Paix-Travail-Patrie …………….. ASSEMBLEE REGIONALE DU NORD-OUEST …………….. CONSEIL EXECUTIF REGIONAL …………….. PAIX-JUSTICE-UNITE-TRAVAIL-SOLIDARITE …………….. |
| --- | --- | --- |

OPEN NATIONAL INVITATION TO TENDER 		***************** 
TENDER FILE 
		*****************

PROJECT OWNER: 
THE PRESIDENT OF THE NORTH WEST REGIONAL ASSEMBLY

CONTRACTING AUTHORITY: 
THE PRESIDENT OF THE NORTH WEST REGIONAL ASSEMBLY

TENDER BOARD: 
NORTH WEST REGIONAL ASSEMBLY INTERNAL TENDERS BOARD (NWRAITB)

TENDER FILE N° 010 /ONIT/NWRA/ITB/2026 OF 19 / JAN / 2026 FOR THE CONSTRUCTION OF WORKSHOPS IN SOME GOVERNMENT TECHNICAL HIGH SCHOOLS OF THE NORTH WEST REGION DIVIDED INTO TWO (02) LOTS

for the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots 
AUTHORIZATION NO:

BUDGETARY HEAD:

2026 FINANCIAL YEAR

1

TABLE OF CONTENTS

Document No. 1: Tender Notice……………………………….……………......…………3 Document No. 2: General Regulations of the Invitation to Tender……………………….12 Document No. 3: Special Regulations of the Invitation to Tender………………………..28 Document No. 4: Special Administrative Conditions……………………………………...37 Document No. 5: Special Technical Conditions…………………………………………...50 Document No. 6: Schedule of unit prices ………………………………………….……...63 Document No. 7: Bill of quantities and estimates………………………………….……...73 Document No. 8: The sub-detail of prices……………………………………....…….…..83 Document No. 9: Model Contract………………………………………...……….……...85 Document No. 10: Model documents to be used by bidders…………...……………..….90 Document No. 11: Justifications of preliminary studies………………………...……….103 Document No. 12: List of banking establishments and financial bodies authorised to issue 	bonds for Public Contracts………………………..……………....….105

2

Document No. 1

TENDER NOTICE

3

| REPUBLIC OF CAMEROON Peace-Work-Fatherland …………….. NORTH-WEST REGIONAL ASSEMBLY …………….. REGIONAL EXECUTIVE ASSEMBLY …………….. PEACE-JUSTICE-UNITY-HARD WORK- SOLIDARITY …………….. |  | REPUBLIQUE DU CAMEROUN Paix-Travail-Patrie …………….. ASSEMBLEE REGIONALE DU NORD-OUEST …………….. CONSEIL EXECUTIF REGIONAL …………….. PAIX-JUSTICE-UNITE-TRAVAIL-SOLIDARITE …………….. |
| --- | --- | --- |

TENDER NOTICE

OPEN NATIONAL INVITATION TO TENDER FILE N° ____/ONIT/NWRA/ITB/2026 OF __ / __ /

2026 FOR THE CONSTRUCTION OF WORKSHOPS IN SOME GOVERNMENT TECHNICAL HIGH

SCHOOLS IN THE NORTH WEST REGION DIVIDED INTO TWO (02) LOTS

Financing: Public Investment Budget – 2026

1.  Subject of the Invitation to Tender: 
	Within the framework of 2026 Public Investment Budget, The President of the North West Regional Assembly, Contracting Authority, hereby launches an Open National Invitation to tender for the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots

| 2. | Nature of works: Works to be done consists of |
| --- | --- |

100 : PRELIMINARY WORKS 
200: FOUNDATION 
300 : GROUND FLOOR ELEVATION 
400 : GROUND FLOOR DECKING 
500 : RAMP 
600 : FIRSTFLOOR ELEVAION 
700 : ROOFING 
800 : CARPENTRY AND WOOD WORKS 
900 : ALLUMINIUM AND METALLIC WORK 
1000: PLUMBING 
 1100: ELECTRICITY AND FIRE PROTECTION 
 1200: RETAINING WALL 
 1300: FINISHING 
 1400: LANDSCAPING AND TREE PLANTING

Execution deadline 
	The maximum deadline provided by the Contracting Authority for the execution of the works subject of this Invitation to tender is Four (04) calendar Months per Lot.

3.Lots: Two (02) Lots 
The works are in Two (02) lots as follows:

| LOT No. | DIVISION | LOCALITY | PROJECT |
| --- | --- | --- | --- |
| 01 | DONGA/MANTUNG | Misaje | Construction of a Building Workshop at GTHS Misaje in Donga/Mantung Division of the North West Region (Lot 1) |
| 02 | MEZAM | Bamendakwe | Construction of a G+1 IT Centre at GTHS Bamendakwe in Mezam Division of the North West Region (Lot 2) |

| 4.Estimated Cost | 4 |
| --- | --- |

The estimated cost of the projects after preliminary studies is as follows:

| LOT No. | DIVISION | LOCALITY | PROJECT | AMOUNT |
| --- | --- | --- | --- | --- |
| 01 | DONGA/MANTUNG | Misaje | Construction of a Building Workshop at GTHS Misaje in Donga/Mantung Division of the North West Region (Lot 1) | 45,179,915 |
| 02 | MEZAM | Bamendakwe | Construction of a G+1 IT Centre at GTHS Bamendakwe in Mezam Division of the North West Region (Lot 2) | 70,000,000 |
| TOTAL |  |  |  | 115,179,915 |

5. Participation and origin Participation in this Invitation to tender is opened under the same conditions to all Cameroonian companies and business persons that have proven experience in the field of building construction and provided they are in compliance with the Cameroonian laws. 6. Financing Works which are the subject of this Invitation to Tender shall be financed by the 2026 Public Investment Budget assigned to the North-West Regional Assembly. 7. Bid bond The bidder must include in his administrative documents, a bid bond issued by a first-rate financial establishment approved by the Ministry in charge of Finance and whose list is found in document No. 12 of the Tender File, of an amount, (See table below) valid for thirty (30) days beyond the date of validity of bids.

| LOT No. | PROJECT | AMOUNT | AMOUNT OF BID BOND | TENDER FILE FEE |
| --- | --- | --- | --- | --- |
| 01 | Construction of a Building Workshop at GTHS Misaje in Donga/Mantung Division of the North West Region (Lot 1) | 45,179,915 | 903,600 | 79,000 |
| 02 | Construction of a G+1 IT Centre at GTHS Bamendakwe in Mezam Division of the North West Region (Lot 2) | 70,000,000 | 1,400,000 |  |

8. Consultation of Tender File: The file may be consulted during working hours at theoffice of the Director of General Affairs at the North West Regional Assembly (Annex Building of Block “A”) Tel N° 2 33 36 00 92 or online using the address; www.marchespublics.cm, as soon as this notice is published.

10.     Acquisition of Tender File: 
	The file may be obtained from the office of the Director of General Affairs at the North West Regional Assembly, Tel N°2 33 36 00 92 or online using the address: www.marchespublics.cm, as soon as this notice is published against payment of the sum of Seventy Nine Thousand, (79,000) Francs CFA,into the North West Regional Assembly Treasury (Block B), representing the cost of purchasing the Tender File.

11. Submission of bids: 
	The method of submission shall be online.

The Tender must be submitted by the Tenderer on the COLEPS Platform not later than 25/FEV/2026 at 10:00am. A backup copy of the Tender saved in a USB key or a CD/DVD must be sent in a sealed envelope with a clear and legible indication “backup copy” within the time limitbearing the label:

| OPEN NATIONAL INVITATION TO TENDER FILE N° ______/ONIT/NWRA/ITB/2026 OF ___ / ___ / 2026 FOR THE CONSTRUCTION OF WORKSHOPS IN SOME GOVERNMENT TECHNICAL HIGH SCHOOLS OF THE NORTH WEST REGION DIVIDED INTO TWO (02) LOTS “To be opened only during the bid-opening session” | 5 |
| --- | --- |

File Size and Format: 
The maximum size of the documents that will be uploaded on the platform and constituting the bidder’s offer shall be; 
	-	5 Mb for Administrative offers; 
	-	15 Mb for the Technical offers; 
		5 Mb for the financial offers. 
-Supported formats shall include: 
	-	PDF formats for texts documents; 
	-	JPEG formats for images.

The Tenderer shall use a compression software to reduce the size of the file to be submitted.

12. 	Admissibility of bids 
	 Under penalty of being rejected, only originals or certified true copies signed by the issuing service or administrative authorities (Governor, Senior Divisional Officer, Divisional Officers….) must imperatively be produced in accordance with the Special Regulations of the Invitation to Tender.

They must obligatorily not be older than three (3) months preceding the date of submission of bids or may be established after the signature of the tender notice

Any bid not in compliance with the prescriptions of the Tender File shall be rejected. This refers especially to the absence of a bid bond issued by a first-rate bank approved by the Minister in charge of Finance

13. Opening of bids: 
The bids shall be opened in a single phase. The opening of the administrative documents, the Technical and Financial offers will take place on the 25/FEV/2026 at 11.00 am local time, in the conference hall of the North West Regional Assembly Internal Tenders’ Board, by its competent members. Only bidders may attend or be represented by duly mandated persons of their choice and having a good knowledge of their files.

14.Evaluation criteria 
The bids shall be evaluated according to the main criteria as follows:

A.Eliminatory criteria 
1.Absence or non-conformity of an element in the administrative file non regularized within 48 hours 		after opening of bids 
2.Execution deadline higher than prescribed in the Tender File; 
3.False declaration or falsified documents; 
4.Absence or insufficient bid bond; 
5.A bid with the external envelope carrying a sign leading to the identification of the bidder; 
6.Incomplete financial file; 
7.Non respect of 75% of essential criteria; 
8.Suspended by MINMAP for 2026.

9. 		Average annual turnover of at least the tendering amount (Average annual turnover calculated as 	total certified payments received for contracts in progress or completed, within the last five (5) years 	(from 2021). This should be justified by copies of past contracts (completed or ongoing). Final 	reception minutes for all completed contracts before 2026 and provisional reception minutes for 	contracts completed in 2025 should be presented.

10.Failure to provide a backup copy of offers saved in a USB key or a CD/DVD on time; 
11.Failure to comply with the format of file type and size for online submission; 
12.Failure to present a CDEC receipt or proof of  deposit of the amount of the bid bond requested into 		the Deposit and Guarantee Fund; 
13.Failure to present a certificate of categorization or receipt of deposit of file for categorisation of the 		enterprise in the “Building and General Equipment” sub-sector of activities.

B.Essential criteria 
1-General presentation of the Tender Files; 
2-Financial capacity; 
3-References of the company in similar achievements visa by the competent authority; 
		6

| REPUBLIC OF CAMEROON Peace-Work-Fatherland …………….. NORTH-WEST REGIONAL ASSEMBLY …………….. REGIONAL EXECUTIVE ASSEMBLY …………….. PEACE-JUSTICE-UNITY-HARD WORK- SOLIDARITY …………….. |  | REPUBLIQUE DU CAMEROUN Paix-Travail-Patrie …………….. ASSEMBLEE REGIONALE DU NORD-OUEST …………….. CONSEIL EXECUTIF REGIONAL …………….. PAIX-JUSTICE-UNITE-TRAVAIL-SOLIDARITE …………….. |
| --- | --- | --- |

AVIS D’APPEL D'OFFRES

PAR PROCEDURE D’URGENCE

APPEL D’OFFRE NATIONAL OUVERT 
N° ___/ ONIT/NWRA/NWRAITB/2026 DU __ /__ 2026 POUR LA CONSTRUCTION D’ATELIERS DANS CERTAINS  LYCÉES TECHNIQUES  D’ETAT DE LA RÉGION DU NORD-OUEST, DIVISE EN DEUX (02) LOTS

Financement : Budget d’Investissement Public 2026

1. 	Objet de l'Appel d'Offre 
Dans le cadre de l’exercice budgétaire 2026, le Président de l’Assemblée Régionale du Nord-Ouest, Autorité Contractante lance  un Appel d’Offres National Ouvert pour la Construction d’Ateliers dans certains Lycées Techniques d’Etat de la Région du Nord-Ouest, Divisées en deux (02) lots

2. 		Consistance des travaux
	 Les travaux comprennent notamment :

100 : TRAVAUX PRELIMINAIRES 
200: FONDATION 
300 : GROUND FLOOR ELEVATION 
400 : ELEVATION DU NIVEAU DU SOL 
500 : RAMP 
600 : NIVEAU DU PREMIER ETAGE 
700 : COUVERTURE - TOITURE 
800 : CHARPENTERIE ET MENUISERIE 
900 : TRAVAUX EN METAL ET ALUMINIUM 
1000: PLUMBERIE 
 1100: ELECTRICITE ET PROTECTION CONTRE L'INCENDI  1200: MUR DE SOUTENEMENT 
 1300: FINITION 
 1400: PAYSAGISME ET ARBORICULTURE

| 3. Délais d’exécution Le délai maximum prévu le Maître d’Ouvrage Délégué pour la réalisation des travaux objet du présent appel d’offres est de Quatre (04) Mois par lot. |  |
| --- | --- |
| 4. | Allotissement Le travail est ci-après défini à 02 lots : |

| LOT No. | DEPARTEMENT | LOCALITE | PROJET |
| --- | --- | --- | --- |
| 01 | DONGA/MANTUNG | Misaje | Construction d’un atelier au lycée technique de Misaje dans le département de la Donga/Mantung, Region du Nord-Ouest (Lot 1) |
| 02 | MEZAM | Bamendakwe | Construction d’un bâtiment G+1 pour un Centre IT au lycée technique de Bamendakwe dans le département de la Mezam, Region du Nord-Ouest (Lot 2) |

8

| 5. | Coût de prévisionnel Le coût prévisionnel de l’opération à l’issue des études préalables est de; |
| --- | --- |
| LOT No.; DEPARTMENT; LOCALITÉ; PROJET; MONTANT. 01; DONGA/MANTUNG; Misaje; Construction d’un atelier au lycée technique de Misaje dans le département de la Donga/Mantung, Region du Nord- Ouest (Lot 1); 45,179,915. 02; MEZAM; Bamendakwe; Construction d’un bâtiment G+1 pour un Centre IT au lycée technique de Bamendakwe dans le département de la Mezam, Region du Nord-Ouest (Lot 2); 70,000,000. TOTAL; 115,179,915. 6. Participation et origine La participation à cette consultation est ouverte aux entreprises de droit camerounais. 7. Financement Les travaux objet du présent appel d'offres sont financés par le Budget d’Investissement Publics du Camerounde l’exercice 2026. 8. Cautionnement provisoire Chaque soumissionnaire doit joindre à ses pièces administratives, une caution de soumission établie par une banque de premier ordre agréée par le Ministère chargé des finances et dont la liste figure dans la pièce 12 du DAO, d’un montant, (voir tableur) valable pendant trente (30) jours au-delà de la date originale de validité des offres. LOT No.; PROJET; MONTANT; MONTANT DE LA CAUTION DE SOUMISSION; FRAIS DE DOSSIER D'APPEL D'OFFRES. 01; Construction d’un atelier au lycée technique de Misaje dans le département de la Donga/Mantung, Region du Nord-Ouest (Lot 1); 45,179,915; 903,600; 79,000. 02; Construction d’un bâtiment G+1 pour un Centre IT au lycée technique de Bamendakwe dans le département de la Mezam, Region du Nord-Ouest (Lot 2); 70,000,000; 1,400,000. 9. Consultation du Dossier d'Appel d'Offres Le Dossier d’Appel d’Offres peut être consulté et obtenu aux heures ouvrables au bureau du Directeur des Affaires Générales de l’Assemblee Regionale du Nord-Ouest (Tel N° 2 33 36 00 92) ou en ligne à l’adresse: www.marchespublics.cm dès Publication du présent avis. 10. Acquisition du Dossier d'Appel d'Offres Le dossier peut être obtenu aux heures ouvrables après Publication du présent avis au bureau de l’autorité contractant (Tel N° 2 33 36 00 92)ou en ligne à l’adresse: www.marchespublics.cm contre présentation d’une quittance de versement au Trésor de l’Assemblée Régionale du Nord-Ouest de la somme non remboursable de 79,000 (Soixante Dix-Neuf Mille) Francs CFA. 11. Remise des offres La méthode de remise doit être en ligne L’offre devra être déposée par le soumissionnaire sur la plateforme COLEPS au plus tard de le __/__/2026 à 10 h 00. Une copie de sauvegarde de l’offre sauvegardée sur une clé USB ou un CD/DVD devra être envoyée dans une enveloppe fermée avec la mention claire et lisible « copie de sauvegarde » portant le libellé dans le délai imparti. APPEL D’OFFRES NATIONAL OUVERT N° ___/ AONO/ARNO/ARNOCIPM/2026 DU ______ |

9

POUR LA CONSTRUCTION D’ATELIERS DANS CERTAINS  LYCÉES TECHNIQUES  D’ETAT DE LA RÉGION DU NORD-OUEST,  DIVISE EN DEUX (02) LOTS «A N’OUVRIR QU’EN SEANCE DE DEPOUILLEMENT»,

Taille et format du fichier : 
	Pour les enchéres en ligne, la taille maximale de documents qui seront téléchargés sur la plateforme et constituant l’offre du soumissionnaire sera de ;

-	5 Mo pour les offres administratives,

-	15Mo pour les offres Techniques,

-	5 Mo pour les offres financements.

Les formats pris en charge doivent inclure :

-	Formats PDF pour documents textes,

-	Formats JPEG pour les images.

Le soumissionnaire devra utiliser un logiciel de compression pour réduire la taille du fichier à soumettre.

12. 	Recevabilité des offres 
	Sous peine de rejet, les pièces du dossier administratif requises doivent être produites en originaux ou en copies certifiées conformes par le service  émetteur ou une autorité  administrative (Governeur, Préfet, Sous-préfet,…), conformément aux stipulations du Règlement Particulier de l’Appel d’Offres.

Elles doivent dater de moins de trois (03) mois précédant la date originale de dépôt des offres ou avoir été établies postérieurement à la date de signature de l’Avis d’Appel d’Offres.

Toute offre incomplète conformément aux  prescriptions du Dossier d'Appel d'Offres sera déclarée irrecevable. Notamment l'absence de la caution de soumission délivrée par une banque de premier ordre agréée par le Ministère chargé des Finances.

13. 	Ouverture des offres 
	L’ouverture des plis se fera en un temps. L’ouverture des pièces administratives et des offres techniques et financières  aura lieu le __/__/2026à 11h 00, heure locale, dans la salle de conférence du Président de l'Assemblée Régionale du Nord-Ouest siégeant en présence des soumissionnaires ou de leurs représentants dûment mandatés et ayant une parfaite connaissance du dossier.

14. 	Critères d’évaluation

Les offres seront évaluées selon les principaux critères suivants :

A - Critères éliminatoires 
Il s'agit notamment: 
		1-Absence ou non-conformité de document administratif qui ne peuvent pas ce régulariser pendant 			 quarante-huit heures appris ouverture des offres

2-Délai d’exécution supérieur à celui prescrit dan le DAO ;

3-Fausses déclarations ou pièces falsifiées ; 
4-Absence ou insuffisance de la caution provisoire de soumission ; 
5-Offres dont l’enveloppe extérieure porte des mentions permettant de reconnaître le Soumissionnaire ; 6-Offres financière incomplète ;

7-Le non-respect de 75% des critères essentiels ;

8-Suspendu par le MINMAP en 2026;

9-Chiffre d'affaires annuel moyen au moins égal au montant de l'offre (chiffre d'affaires annuel moyenne calculée comme le total des paiements certifiés reçus pour les contrats en cours ou achevés, au cours du dernier cinq (5) ans (à partir de 2021) à justifier par des copies des contrats passés (achevés ou en cours. Procès-verbal de réception définitif pour tous les marchés terminés avant 2026 et procès-verbal de réception provisoire pour les contrats terminés en 2025 à présenter)

| 10-11- | Défaut de fournir une copie de sauvegarde de l’offre sauvegardée sur une clé USB ou un CD/DVD à temps. Défaut de se conformer au foumat du type de fichier et de la taille pour la soumission en ligne ; |
| --- | --- |

10

12. Défaut de présenter un reçu du CDEC ou une preuve de dépôt du montant de la caution de soumission exigée auprès du Fonds de dépôt et de garantie;

13. Défaut de présenter un certificat de catégorisation ou un reçu de dépôt du dossier de catégorisation de l’entreprise dans le sous-secteur d’activité « Bâtiment et équipement général ».

B - Critères essentiels 
Les critères relatifs à la qualification des candidats porteront à titre indicatif sur : 
	1-Présentation générale de l’offre ; 
	2-Capacité financière ; 
	3-Références de l’entreprise dans les réalisations similaires ; 
	4-Qualité du personnel ; 
	5-Organisation technique des travaux ; 
	6-Sécurité au chantier ; 
	7-Moyens logistiques ; 
	8-Attestations de visite de site signée sur l’honneur par le soumissionnaire et rapport de visite du site 			avec photos ; 
	9-Cahier des Clauses Techniques Particulières paraphé à chaque page, signe et date a 
			la denier page ; 
	10-Cahier des Clauses Administratives Particulières complété et paraphé à chaque page, 
			signe et date à la denière page.

Les critères essentiels sont soumis à des minima dont le détail est donné dans le Règlement Particulier de l’Appel d’Offres (RPAO).

15. 	Attribution 
	Cette évaluation se fera de manière purement positive (oui) ou négative (non) avec un minimum acceptable d’au moins 75% de l’ensemble des critères essentiels pris en compte. (Un soumissionnaire peut soumissionner pour plusieurs lots mais ne peut se voir attribuer qu'un seul lot)

Le marché sera attribué au soumissionnaire qui aura proposé l’offre le moins disante, conforme pour l’essentiel aux prescriptions du Dossier d’Appel d’Offres, ayant satisfait à 100% des critères éliminatoires et au moins 75% des critères essentiels. Un enchérisseur peut soumissionner pour plus d’un lot mais ne peut se voir attribuer qu’un seul lot.

16. 	Durée de validité des offres 
	Les soumissionnaires restent engagés par leur offre pendant 90 jours à partir de la date limite fixée pour la remise des offres.

17. 	Renseignements complémentaires 
	Les renseignements complémentaires d’ordre technique peuvent être obtenus auprès de bureau du Directeur des Affaires Générales (Tel N° 2 33 36 00 92).

Fait à Bamenda, le_______________________

Copie :

- 	ARMP/NW

- 	DR/MINMAP/NW

- 	Présidents CIPM/NWRA

- 	Affichage

- 	Chrono/archive

Le Président de l’Assemblée Régionale du Nord Ouest (Autorité Contractante)

Document No. 2

GENERAL REGULATIONS OF THE

INVITATION TO TENDER

12

TABLE OF CONTENTS

A.General 
Article 1: Scope of the tender………………………………………………………. Article 2: Financing…………………………………………………………………… Article 3: Fraud and corruption……………………………………………………….

Article 4: Candidates admitted to compete………………………………………… Article 5: Building materials, materials, supplies, equipment and authorised services… Article 6: Qualification of the bidder………………………………………………… Article 7: Visit of work site ………………………………………………………

B.Tender File…………………………………………………………………………… 	Article 8: Content of Tender File……………………………………………………….

Article 9: Clarifications on Tender File and complaints ………………………… Article 10: Modification of the Tender File…………………………………………

C.Preparation of Bids 
Article 11: Tender fees……………………………………………………………… Article 12: Language of bid………………………………………………………… Article 13: Constituent documents of the bid……………………………………… Article 14: Amount of bid…………………………………………………………… Article 15: Currency of bid and payment………………………………………….. Article 16: Validity of bids…………………………………………………………… Article 17: Bid bond………………………………………………………………….. Article 18: Varying proposals by bidders…………………………………………… Article 19: Preparatory meeting to the establishment of bids……………………. Article 20: Form and signature of bids………………………………………………

D.Submission of bids………………………………………………………………… Article 21: Sealing and marking of bids……………………………………………. Article 22: Date and time-limit for submission of bids……………………………. Article 23: Out of time-limit bids……………………………………………………. Article 24: Modification, substitution and withdrawal of bids…………………….

E.Opening and evaluation of bids …………………………………………………  Article 25: Opening of bids…………………………………………………………. Article 26: Confidential nature of the procedure…………………………………… Article 27: Clarifications on the bid and contact with Contracting Authority……. Article 28: Determination of their compliance……………………………………. Article 29: Qualification of the bidder………………………………………………. Article 30: Correction of errors………………………………………………………. Article 31: Conversion into a single currency……………………………………… Article 32: Evaluation of financial bids…………………………………………… Article 33: National preference………………………………………………………

F.Award of the Contract……………………………………………………………….

Article 34: Award……………………………………………………………………… 
Article 35: Right of the Contracting Authority to declare an Invitation to Tender unsuccessful or to cancel a procedure……………………………….

Article 36: Notification of the award of the Contract……………………………… Article 37: Signature of the Contract………………………………………………… Article 38: Final bond…………………………………………………………………

13

GENERAL RULES OF THE INVITATION TO TENDER

A.GENERAL

Article 1: Scope of the tender 
The Contracting Authority, The President of the North West Regional Assembly hereby launches an Open National Invitation to Tender No ___/ONIT/NWRA/ITB/2026 of __/__/2026 for the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots

1.2The bidder retained or the preferred bidder must complete the works within the time- limit indicated in 	the Special Regulations which runs from the date of notification of the Administrative Order.

1.2In this Tender File, the term “day” means a calendar day.

Article 2: Financing 
The source of financing of the works forming the subject of this Invitation to Tender shall be specified in the Special Regulations.

Article 3: Fraud and corruption 
3.1 The Contracting Authority requires of bidders and Contractors the strict respect of rules of professional ethics during the award and execution of Public Contracts. By virtue of this principle:

a) The following definitions shall be admitted:

i)Shall be guilty of “corruption” whoever offers, gives, requests or accepts any advantage in view of 		influencing the action of a Public official during the award or execution of a Contract; 
ii) Is involved in “fraudulent manoeuvres” whoever deforms or distorts facts in order to influence the 		award or execution of a Contract; 
iii)		 “Collusive practices” shall mean any form of agreement between two or among several 		bidders (whether the Contracting Authority is aware or not) aimed at artificially maintaining the 		prices of bids at levels not corresponding to those resulting from competition; 
iv)		 “Coercive practices” shall mean any form of harm against persons or their property or threats 		against them in order to influence their action during the award or execution of a Contract.

b)Any proposed award shall be rejected if it is proved that the proposed preferred bidder is directly or through an intermediary, guilty of corruption or is involved in fraudulent manoeuvres, collusive or coercive practices for the award of this Contract.

3.2     The Minister Delegate at the Presidency in charge of Public Contracts may, as a precaution, take a decision of exclusion from bidding for a period not exceeding two (2) years against any bidder found guilty of influence peddling, of conflicts of interest, insider trading, fraud, corruption or production of non-genuine documents in the bid, without prejudice to criminal proceedings that may be brought against him

Article 4: Candidates are allowed to compete 
	 4.1 If the Invitation to Tender is opened, consultation is addressed to all candidates retained after a pre-	qualification procedure.

4.2 Generally, the Invitation to Tender is addressed to all entrepreneurs, subject to the following provisions:

(a) A bidder (including all members of a group of enterprises and all sub-Contractors to the bidder) 	must be from an eligible country, in accordance with the funding agreement.

14

(b)A bidder (including all members of a group of enterprises and all sub-Contractors to the bidder) must not be in a situation of conflict of interest, subject to disqualification. A bidder shall be judged to be in a situation of conflict of interest if he:

| i) | Is or was associated in the past with an enterprise (or a subsidiary of this enterprise) which provided consultancy services for the conception, preparation of specifications and other documents used within the scope of Contracts awarded for this Invitation to Tender; or |
| --- | --- |

ii)Presents more than one bid within the context of Invitation to Tender, except authorised variants according to article 17, where need be; meanwhile, this does not prevent the participation of sub-Contractors in more than one bid.

| iii) | The Contracting Authority or Project Owner has financial interests in the capital in a way as to compromise the transparency of the procedures of award of Public Contracts. |
| --- | --- |

(c)   The bidder must not have been excluded from bidding for Public Contracts.

(d)  A Cameroonian Public enterprise may participate in the consultation if it can demonstrate that it is (i) legally and financially autonomous, (ii) managed according to commercial laws and (iii) not under the direct supervisory authority of the Contracting Authority or Project Owner.

Article 5: Building materials, materials, supplies, equipment and authorised services 
5.1 Building materials, the Contractor’s materials, supplies, equipment and services forming the 		subject of this Contract must originate from countries meeting the criteria of origin defined in the 		Special Regulations of the Invitation to Tender and all expenditure done within the context of the 		Contract shall be limited to the said building materials, materials, supplies, equipment and 		services.

5.2  Within the meaning of this 5.1 above, the term “originate” shall designate the place where the 	goods are extracted, cultivated, produced, manufactured  and from where the services originate.

Article 6: Qualification of bidder 
	 6.1   As an integral part of their bid, bidders must:

(a)submit a power of attorney making the signatory of the bid bound by the bid; and

(b)  provide all information (complete or update information included in their request for pre-qualification which may have changed in the case where the candidates took part in pre-qualification) requested of bidders in the Special Regulations of the Invitation to Tender, in order to establish their qualification to execute the Contract.

Where necessary, bidders should provide information relating to the following points:

(i)  The production of certified balance sheets and recent turnovers;  (ii)  Access to a line of credit or availability of other financial resources;  (iii)  Orders acquired and Contracts awarded; 
 (iv)  Pending litigations;  
 (v)  Availability of indispensable equipment.

6.2   Bids presented by two or more associated undertakings (joint-Contracting) must satisfy the 	following conditions:

(a)The bid must include all the information listed in article 6(1) above. The Special Regulations must indicate the information to be furnished by the group and that to be furnished by each member of the group;

(b)The bid and the Contract must be signed in a way that is binding on all members of the group; (c) The nature of the group (joint or several) must be specified  in the Special Regulations and justified 		with the production of a joint venture agreement in due form;

15

(d)The member of the group designated as the representative will represent all the undertakings vis à 		vis the Project Owner and Contracting Authority with regard to the execution of the Contract; (e) In case of joint co-Contracting, the co-Contractors shall share the sums which are paid by the 		Project Owner into a single account. On the other hand, each undertaking is paid into its own 		account by the Project Owner where it is joint co-Contracting.

6.3 Bidders must equally present sufficiently detailed proposals to demonstrate that they comply with the technical specifications and execution time-limits set in the Special Regulations of the Invitation to Tender.

6.4 Bidders requesting to benefit from the margin of preference must furnish all the necessary information to prove that they satisfy the eligibility criteria set in article 33 of the General Regulations of the Invitation to Tender.

Article 7: Visit of works site 
		7.1 The bidder is advised to visit and inspect the site and its environs and obtain by himself and under his 	own responsibility, all the information which may be necessary for the preparation of the bid and the 	execution of the works. The related cost of the visit of the site shall be borne by the bidder.

7.2 The Project Owner shall authorise the bidder and his employees or agents to enter the premises and the land for the said visit but only on the express condition that the bidder, his employees and agents free the Project Owner, his employees and agents of any responsibility that may ensue and indemnify them if necessary and that they shall remain responsible for any deadly or corporal accident, loss or material damages, costs and fees incurred from this visit.

7.3 The Project Owner may organise a visit of the site of the works during the preparatory meeting to establishing the bids mentioned in article 19 of the General Regulations of the Invitation to Tender.

B. TENDER FILE 
Article 8: Content of Tender File 
	 8.1 The Tender File describes the works forming the subject of the Contract, sets the consultation 	procedure of Contractors and specifies the terms of the Contract.  Besides the addendum (addenda) 	published in accordance with article 10 of the General Regulations of the Invitation to Tender, it 	includes the following documents:

Document No. 1. The Tender Notice; 
Document No. 2. The General Regulations of the Invitation to Tender; Document No. 3. The Special Regulations of the Invitation to Tender; Document No. 4. The Special Administrative Conditions; 
Document No. 5. The Special Technical Conditions; 
Document No. 6. The schedule of unit prices; 
Document No. 7. The bill of quantities and estimates; 
Document No. 8. The sub details of unit prices; 
Document No. 9. Model documents of the Contract: 
	a.The execution schedule; 
	b.Model of forms presenting the equipment, personnel and references; 	c.Model bidding letter; 
	d.Model bid bond; 
	e.Model final bond; 
	f.Model of bond of start-off advance; 
	g.Model of guarantee in replacement of the retention fund; 
	h.Model Contract;

Document No. 10. Models to be used by bidders; 
	a.Model Contract;

16

Document No. 11. Justifications of preliminary studies; to be filled by the Project Owner or Delegated 	Project Owner; 
 Document No. 12. List of first grade banking establishments or financial institutions approved by the 	Minister in charge of Finance authorised to issue bonds for Public Contracts to be inserted by 	the Contracting Authority.

8.2 The bidder must examine all the regulations, forms, conditions and specifications contained in the Tender File. It is up to him to furnish all the information requested and prepare a bid in compliance with all aspects of the said file.

Article 9: Clarifications on the Tender File and complaints 
9.1 Any bidder who wants to obtain clarifications on the Tender File may request them from the Contracting Authority in writing or by electronic mail (fax or e-mail) at the Contracting Authority’s address indicated in the Special Regulations of the Invitation to Tender and send a copy to the Project Owner. The Contracting Authority replies in writing to any request for clarification received at least fourteen (14) days prior to the deadline for the submission of bids.

A copy of the Contracting Authority’s response, indicating the question posed but not mentioning the author, is addressed to all bidders who bought the Tender File.

9.2 Between the Publication of the tender notice including the pre-qualification phase of candidates and the opening of bids, any bidder who feels aggrieved in the Public Contracts award procedure may lodge a complaint to the Minister in charge of Public Contracts.

9.3 A copy of the complaint should be addressed to the Contracting Authority and to the body in charge of the Regulation of Public Contracts and the chairperson of the Tenders Board.

9.4 The Contracting Authority has five (5) days to react. A copy of the reaction shall be forwarded to MINMAP and the body in charge of the regulation of Public Contracts.

Article 10:  Amendment of the Tender File 
10.1The Contracting Authority may at any moment, prior to the deadline for the submission of  bids and for any reason, be it at his initiative or in reply to a request for clarification formulated by a bidder, amend the Tender File by publishing an addendum.

10.2 		Any published addendum shall be an integral part of the Tender File, in accordance with article 8.1 	of the General Regulations of the Invitation to Tender and must be communicated in writing or made 	known by a traceable means to all bidders who bought the Tender File.

10.3 	In order to give bidders sufficient time to take account of the addendum in the preparation of their bids, the Contracting Authority may postpone as is necessary, the deadline for the submission of bids, in accordance with provisions of article 22 of the General Regulations of the Invitation to Tender.

C   PREPARATION OF BIDS

Article 11: Tender costs 
The candidate shall bear the costs related to the preparation and presentation of his bid and the Contracting Authority and the Project Owner shall in no case be responsible for these costs nor pay for them whatever the evolution or outcome of the Invitation to Tender procedure.

Article 12: Language of bid 
The bid as well as any correspondence and any document exchanged between the bidder and the Contracting Authority shall be written in English or French. Complementary documents and the forms provided by the bidder may be written in another language on condition that a precise translation into either English or French of the passages concerning the bid is included; in which case for reasons of interpretation, the translation shall be considered to be authentic.

17

Article 13: Constituent documents of the bid 
 13.1 The bid presented by the bidder shall include the documents detailed in the Special Regulations of the Invitation to Tender, duly filled and put together in three volumes:

a.Volume 1:  Administrative file

It includes:

i)all documents attesting that the bidder: 
-has subscribed to all declarations provided for by the laws and regulations in force; -paid all taxes, duties, contributions, fees or deductions of whatever nature; 
-is not winding up or bankrupt; 
-is not the subject of an exclusion order or forfeiture provided for by the law in force;

ii)   The bid bond established in accordance with the provisions of article 17 of the General 	Regulations of the Invitation to Tender;

iii)  the written confirmation empowering the signatory of the bid  to commit the bidder, in 	accordance with the provisions of article 6(1) the General Regulations of Invitation to Tender.

b.Volume 2: Technical bid 
		b.1 Information on qualifications 
The Special Regulations list the documents to be furnished by bidders to justify the qualification criteria mentioned in article 6(1) of the Special Regulations of the Invitation to Tender.

b.2 Methodology 
The Special Conditions of the Invitation to Tender specifies the constituent elements of the technical bid of the bidders especially: a methodological statement on an analysis of the works and specifying the organisation and programme which the bidder intends to put in place or use to execute the works (installations, schedule, Quality Assurance Plan (QAP), sub-Contracting, attestation of visit of the site, where necessary, etc).

b.3 Proof of acceptance of conditions of the Contract 
The bidder shall submit duly initialled copies of the administrative and technical documents relating to the Contract, namely:

| 1. 2. | The Special Administrative Conditions (SAC); The Special Technical Conditions (STC). |
| --- | --- |

b.4 Commentaries (optional) 
A commentary on the technical choices of the project and possible proposals.

c.Volume 3: Financial bid 
The Special Regulations specify the elements that will help in justifying the cost of the works, namely: 1.The signed and dated original bid prepared according to the attached model, stamped at the 		prevailing rate; 
2.The  duly filled Unit Price schedule; 
3.The duly filled detailed estimates; 
4.The sub-details of prices and/or breakdown of all-in prices; 
5.The projected schedule of payments, where need be.

In this regard, the bidders will use the documents and models provided in the Tender File, subject to the provisions of article 17(2) of the General Regulations of the Invitation to Tender concerning the other possible forms of guarantees.

18

13.2    If in accordance with the provisions of the Special Regulations of the Invitation to Tender, the bidders present bids for several lots of the same Invitation to Tender, they could indicate rebates offered in case of award of more than one lot.

Article 14:  Bid price 
 14.1    Except otherwise stated in the Tender File, the amount of the Contract shall cover all the works 		described in article 1.1 of the General Regulations of the Invitation to Tender, on the basis of the 		price schedule and the detailed bill of quantities and estimates presented by the bidder.

14.2   The bidder shall fill the unit prices and totals of all items on the schedule and bill of quantities and estimates.

14.3   Subject to contrary provisions provided for in the Special Regulations and in the Special Administrative Conditions, all dues, taxes and fees payable by the bidder on grounds of the Contract or on any other ground, thirty (30) days prior to the submission of the bids, shall be included in the prices and in the total amount of the bid presented by the bidder.

14.4 If a price revision/updating clause is provided for in the Contract, the date of establishment of the initial price, as well as the price revision/updating conditions for the said price must be specified. This is with the understanding that any Contract of duration less than one (1) year shall not be subject to price revision.

14.5 All unit prices must be justified by sub-details established in accordance with the structure proposed in document 8 of the Tender File.

Article 15: Currency of bid and payment 
	 15.1 In case of international invitations to tender, the currencies of the bid shall follow the provisions of 	either Option A or Option B below, the applicable option being that retained in the Special Regulations 	of the Invitation to Tender.

15.2 Option A:The amount of the bid shall be entirely made in the national currency.

The amount of the bid, unit prices of the price schedule and the prices of the bill of quantities and estimates are completely made in CFA francs in the following manner:

a)Prices shall be entirely drawn in the national currency. The bidder who intends to commit expenditures in other currencies for the execution of the works shall indicate in the annex to the bid the percentage(s) of the amount of the bid necessary to cover the needs in foreign currencies, without exceeding the maximum of the three currencies of member countries of the funding institution of the Contract.

b)The exchange rates used by the bidder to convert his bid into the national currency shall be specified by the bidder in an annex to the bid in compliance with the specifications of the Special Regulations. These rates shall be applied for any payment within the framework of the Contract so that the retained bidder does not bear any change in the exchange rate.

15.3 Option B:The amount of the bid shall be directly made in the national and foreign currency at the rates fixed in the Special Regulations.

The bidder shall draw the unit prices of the price schedule and the prices of the bill of quantities and estimates in the following manner:

| (a) (a) | The prices of inputs necessary for the works which the bidder intends to procure in the Contracting Authority’s country shall be in currency of the Contracting Authority’s country specified in the Special Regulations and called “national currency”; The prices of inputs necessary for works which bidder intends to procure out of the Contracting Authority’s country shall be in the currency of the country of origin of the bidder or of the currency of an eligible member country widely used in international trade. |
| --- | --- |

19

15.4 The Contracting Authority may request the bidders to explain the needs in national and foreign currencies and to justify that the amounts included in the unit and total prices and indicated in annex to the bids are reasonable; to this end, a detailed statement of their needs in foreign currencies shall be furnished by the bidder.

15.5 During the execution of the works, most of the foreign currency to be paid as part of Contract may be revised by mutual agreement between the Contracting Authority and the entrepreneur in a way as take account of any modification in the foreign currency needs within the context of the Contract.

Article 16: Validity of bids 
16.1 Bids must remain valid during the period stated in the Special Regulations from the date of submission of 	the bids fixed by the Contracting Authority, in application of article 22 of the Special Regulations. A bid 	valid for a shorter period shall be rejected by the Contracting Authority or Contracting Authority as not 	being in compliance.

16.2 Under exceptional circumstances, the Contracting Authority may seek the approval of bidders to extend the validity time-limit.  The request and the responses that will be given shall be in writing (or by fax). The validity of the bid bond provided for in article 17 of the General Regulations shall equally be extended for a corresponding duration. A bidder may refuse to extend the validity of his bid without losing his bid bond. A bidder who consents to an extension shall not be asked to modify his bid nor shall he be authorised to do so.

16.3 Where the Contract does not include a price revision clause and that the period of validity of bids is extended by more than sixty (60) days, the amounts payable to the bidder retained shall be updated by application of the related formula featuring in the request for extension that the Contracting Authority addressed to bidders.

The updating period shall run from the date of overrun of sixty (60) days to the date of notification of the Contract or the Administrative Order for start of execution of works by the retained bidder, as specified in the Special Administrative Conditions. The effect of updating shall not be taken into account for purposes of evaluation of bids.

Article 17: Bid bond 
17.1   In application of article 13 of the General Regulations, the bidder shall furnish a bid bond of the amount specified in the Special Regulations and which bid bond shall be a full part of his bid.

17.2 The bid bond must conform to the model presented in the Tender File; other models may be authorised subject to the prior approval of the Contracting Authority. The bid bond will remain valid for thirty (30) days beyond the original date set for the validity of bids or any other validity time-limit  requested by the Contracting Authority and accepted by the bidder, in accordance with the provisions of article 16 (2) of the General Regulations.

17.3   Any bid without an acceptable bid bond shall be rejected by the Tenders Board as not in conformity. The bid bond of associated enterprises must be established in the name of the group submitting the bid and mention each member of the associated grouping.

17.4    The bid bonds of bidders who are not retained shall be returned within fifteen (15) days after Publication of the award result.

17.5   The bid bond of the successful bidder shall be released as soon as the latter would have signed the Contract and furnished the required final bond.

17.6    The bid bond may be seized: 
	(a)if the bidder withdraws his bid during the period of validity; 
	(b)  if the retained bidder: 
		 i) fails in his obligation to register the Contract in application of  article 38 of the General 		Regulations;

20

ii)fails in his obligation to furnish the required final bond in application of article 38 of the General 	Regulations; 
iii)Refuses to receive notification of the Administrative Order to commence execution.

Article 18: Varying proposals of bidders 
18.1 Where the works can be executed within variable deadlines, the Special Regulations shall specify these deadlines and shall indicate the method retained for the evaluation of the completion deadline proposed by the bidder within the specified deadlines. Bids that propose deadlines beyond those specified shall be considered as not being in conformity.

18.2 Except in the case mentioned in article 18(3) below, bidders wishing to offer technical variants must first assess the basic solution of the Contracting Authority as described in the Tender File and furnish in addition all the information which the Contracting Authority needs for a complete evaluation of the proposed variant, including the plans, calculations, technical specifications, sub-details of prices and proposed construction methods and all other useful information. If necessary, the Contracting Authority will examine only the technical variants of the bidder whose bid is in compliance with the basic solution has been evaluated as the lowest bid.

18.3 When according to the Special Regulations the bidders are authorised to directly submit the technical variants for certain parts of the works, these parts of the works must be described in the technical specifications. Such variants shall be evaluated on their own merit in accordance with the provisions of article 31(2) (g) of the General Regulations.

Article 19: Preparatory meeting to the establishment of bids 
19.1   Except otherwise stipulated in the Special Regulations, a bidder may be invited to take part in a preparatory meeting which will hold at the date and place indicated in the Special Regulations.

19.2 The subject of the preparatory meeting shall be to furnish clarifications and answer any questions which may be raised at this stage.

19.3    As much as possible, the bidder is requested to submit any question in a way as to reach the Contracting Authority at least one week before the meeting. The Contracting Authority may not reply to questions received too late. In this case, the questions and answers shall be transmitted according to the methods set in article 19(4) below.

19.4    The minutes of the meeting, including the text of the questions asked and the replies given, including questions prepared after the meeting, shall be forwarded immediately to everyone who bought the Tender File. Any modification of documents of the Tender File listed in article 8 of the General Regulations which may prove to be necessary at the end of the preparatory meeting shall be done by the Contracting Authority by publishing an addendum in accordance with the provisions of article 10 of the General Regulations and not through the minutes of the preparatory meeting.

19.5 The fact that a bidder does not attend a preparatory meeting for the establishment of bids shall not be a reason for disqualification.

Article 20: Form and signature of bid 
20.1 The bidder shall prepare an original of the constituent documents described in article 13 of the General 	Regulations in a volume clearly indicated “ORIGINAL”. In addition, the bidder shall submit the 	number required in the General Regulations, bearing “COPY”. In case of discrepancy, the original shall 	be considered as authentic.

20.2  The original and copies of the bid must be typed or written in indelible ink (photocopies shall be accepted in the case of copies) and shall be signed by the person(s) duly empowered to sign on behalf of the bidder, in accordance with article 6(1a) or 6(2c) of the General Regulations, as the case may be. All the pages of the bid containing alterations or changes must be initialled by the signatory (ies) of the bid.

20.3 The bid shall be bear no modification, suppression or alteration unless such corrections are initialled by 	the signatory (ies) of the bid.

21

D.  SUBMISSION OF BIDS

Article 21:  Sealing and marking of bids

The Tender must be submitted by the Tenderer on the COLEPS Platform not later than __/__/2026 at 10:00am. A backup copy of the Tender saved In a USB key or a CD/DVD must be sent in a sealed envelope with a clear and legible indication “backup copy” bearing the afore-mentioned label, within the time limit.

File Size and Format: 
	For online bidding, the maximum sizez of the documents that will be uploaded on the platform and constituting the bidder’s offer shall be; 
		5 Mb for Administrative offers; -
	-	15 Mb for the Technical offers; 
	-	5 Mb for the financial offers.

Supported formats shall include: 
	-	PDF formats for texts documents; 
	-	JPEG formats for images.

The Tenderer shall use a compression software to reduce the size of the file to be submitted.

Article 22: Date and time-limit for submission of bids 
22.1 The bids must be received by the Contracting Authority at the address specified in article 21(2) of the 	Special Regulations not later than the date and time stated in the Special Regulations.

22.2 The Contracting Authority may, at his discretion, postpone the deadline set for the submission of the bids by publishing an addendum in accordance with the provisions of article 10 of the General Regulations. In this case, all the rights and obligations of the Contracting Authority and bidders previously governed by the initial date will henceforth be governed by the new date.

Article 23: Late bids 
Any bid received by the Contracting Authority beyond the deadline for the submission of bids in accordance with article 22 of the General Regulations shall be declared late and consequently rejected.

Article 24: Modification, substitution and withdrawal of bids 
24.1 A bidder may modify or withdraw his bid after submitting it, on condition that the written notification of 	the modification or withdrawal is received by the Contracting Authority prior to the end of the time-limit 	prescribed for the submission of the bids. The said notification must be signed by an authorised 	representative in application of article 20(2) of the General Regulations. The modification or the 	corresponding replacement bid must be attached to the written notification. As the case may be, the bids 	must bear the inscription “WITHDRAWAL”, and “REPLACEMENT BID” or “MODIFICATION”. 24.2 Notification of modification, replacement or withdrawal of the bid by the bidder should be prepared, 	sealed, marked and forwarded in accordance with the provisions of article 21 of the General Regulations.

Withdrawal may equally be notified by telex but should in this case be confirmed by a duly signed written notification whose date, post mark being authentic, shall not be posterior to the time-limit set for the submission of bids.

24.3 In application of article 24(1), bids being requested to be withdrawn by bidders shall be returned to them 	unopened.

24.4 No bid may be withdrawn during the interval between the submission of bids and the expiry of the validity of bids specified by the model tender. The withdrawal of a bid by a bidder during this interval may lead to the confiscation of the bid bond in accordance with the provisions of article 17(6) of the General Regulations.

22

E.  OPENING AND EVALUATION OF BIDS

Article 25: Opening and petitions 
25.1 The Internal Tenders Board shall open the bids in single or double phases and in the presence of the 		representatives of bidders who wish to attend at the date, time and address specified in the Special 		Regulations. Representatives of bidders shall sign a register attesting to their presence.

25.2 Firstly, bids marked “withdrawal” shall be opened and the contents announced to the hearing of everyone, while the envelope containing the corresponding bid shall be returned to the bidder un opened. Withdrawal shall be allowed only if the corresponding notification contains a valid empowerment of the signatory to request this withdrawal and if this notification is read to the hearing of everyone. Then the bids marked “Replacement bid” are opened and announced to the hearing of everyone and the new corresponding bid substituted for the preceding one which will be sent to the bidder concerned unopened. The replacement of the bid shall only be allowed if the corresponding notification contains a valid empowerment of the signatory requesting the replacement and read to the hearing of everyone. Lastly, the bids marked “modification” shall be opened and their contents read to the hearing of everyone with the corresponding bid. The modification of the bid shall only be allowed if the corresponding notification contains a valid empowerment of the signatory requesting the modification and read to the hearing of everyone. Only bids which were opened and announced to the hearing of everyone during the opening of bids shall then be evaluated.

25.3 All bids shall be opened successively and the name of the bidder announced aloud as well as the possible modification mentioned, the price offered, including any rebates [in case of opening of financial bids] and any variant, where necessary, the existence of a guarantee of the bid if it is required and any other details which the Contracting Authority deems useful to be mentioned. Only rebates and variants of bids announced to the hearing of everyone during the opening of bids shall be submitted for evaluation.

25.4 Bids (and modifications received in accordance with the provisions of article 24 of the General Regulations) which were not opened and read to the hearing of everyone during the bid- opening session for whatever reason, shall not be submitted for evaluation.

25.5 Bid- opening minutes are recorded on the spot mentioning the admissibility of bids, their administrative regularity, prices, rebates and time-limits as well as the composition of the Evaluation sub-committee. A copy of the said minutes to which is attached the attendance sheet is handed over to all the participants at the end of the session.

25.6 At the end of each bid- opening session, the chairperson of the Tenders Board immediately hands over to the focal point designated by the body in charge of regulation of Public Contracts an initialled copy of the bids presented by bidders.

25.7 In case of petition as provided for by the Public Contracts Code, it should be addressed to the Minister Delegate in charge of Public Contracts with a copies to the body in charge of the regulation of Public Contracts, the head of structure to which is attached the Tenders Board concerned.

It must reach within a maximum deadline of three (3) working days after the opening of bids in the form of a letter to which is obligatorily attached a sheet of the petition form duly signed by the petitioner and possibly by the chairperson of the Tenders Board.

The Independent Observer attaches to his report the sheet that was handed to him, including any related commentaries or observations.

Article 26: Confidential nature of the procedure 
26.1 No information relating to the examination, clarification, evaluation and comparison of bids and 	verification of the qualification of the bidders and the recommendation for the award shall be given to 	bidders or to any person not concerned with the said procedure as long as the preferred bidder has not

23

been made Public, subject to the disqualification of the bid of the bidder and suspension of the authors from all activities in the domain of Public Contracts.

26.2 Any attempt by a bidder to influence the Tenders Board or the Evaluation sub-committee of bids or the 	Contracting Authority in its award decision may lead to the rejection of his bid.

26.3 Notwithstanding the provisions of paragraph 26.2 above, between the opening of bids and the award of the Contract, if a bidder wishes to enter into contact with the Contracting Authority for reasons having to with his bid may do so in writing.

Article 27: Clarifications on the bids and contact with the Contracting Authority 
27.1 To ease the examination, evaluation and comparison of bids, the Tenders Board may, if it so desires, 	request any bidder to give clarifications on his bid. This request for clarification and the response thereto 	are formulated in writing but no change on the amount or content of the bid is sought, offered or 	authorised, except it is necessary to confirm the correction of calculation errors discovered by the 	Evaluation Sub-committee during the evaluation in accordance with the provisions of article 30 of the 	General Regulations.

27.2 Subject to the provisions of paragraph 1 above, bidders shall not contact members of the Tenders Board and the Evaluation Sub-committee for questions related to their bids, between the opening of bids and the award of the Contract.

Article 28: Determination of compliance of bids 
28.1 The Evaluation sub-committee shall carry out a detailed examination of bids to determine if they are 	complete, if the required guarantees are furnished, if the documents were correctly signed and if 	generally the bids are in proper order.

28.2 The Evaluation sub-committee shall determine if the bid is essentially in compliance with the 	conditions fixed in the Tender File based on the content without recourse to external elements of proof.

28.3 A bid that complies with the Tender File shall essentially be a bid that respects all the terms, conditions and specifications of the Tender File, without substantial divergence or reservation.  A substantial divergence or reservation is that:

i)which substantially limits the scope, quality or realisation of the works; 
ii)which substantially limits, contrary to the Tender File, the rights of the Contracting Authority 		or his obligations in relation to the Contract; 
iii)Whose correction would unjustly affect the competitiveness of the other bidders who 		presented bids that essentially complied with the Tender File.

28.4   If a bid is essentially not in compliance, it shall be rejected by the competent Tenders Board and shall not subsequently be rendered in compliance.

28.5   The Contracting Authority reserves the right to accept or reject any modification, divergence or reservation. Modifications, divergences, variants and other factors which are beyond the requirements of the Tender File shall not be considered during the evaluation of bids.

Article 29: Qualification of the bidder 
	 The Evaluation sub-committee shall ensure that the successful bidder retained for having submitted a 	bid substantially in compliance with the provisions of the Tender File, fulfils the qualification criteria 	stipulated in article 6 of the Special Regulations. It is essential to avoid any arbitrariness in 	determining qualification.

Article 30: Correction of errors 
30.1 The Evaluation sub-committee shall verify bids considered essentially in compliance with the Tender File 		to correct the possible calculation errors. The Evaluation sub-committee shall correct the errors in the 		following manner:

24

(a)where there is an incoherence between the unit price and the total obtained by multiplying the unit price by the quantity, the unit price being authentic, the total price shall be corrected, unless the Evaluation sub-committee judges that it is a gross error of decimal point in the unit price in which case the total price as presented shall be authentic and the unit price corrected.

(b)if the total obtained by addition or subtraction of the totals is not exact, the sub totals shall be 	considered authentic and the total corrected.

(c)where there is a difference between the price indicated in letters and in figures, the amount in letters shall be considered authentic, unless the amount is linked to an arithmetical error confirmed by the sub-detail of the said price, in which case the amount in figures shall prevail subject to paragraphs (a) and (b) above.

30.2 The amount featuring in the bid shall be corrected by the Evaluation sub-committee, in accordance with the error correction procedure above and with confirmation by the bidder, the said amount shall be deemed to commit him.

30.3 If the bidder who presented the bid evaluated as the lowest refuses the correction thus carried out, his bid shall be rejected and the bid bond may be seized.

Article 31: Conversion into a single currency 
31.1 To facilitate the evaluation and comparison of bids, the Evaluation sub-committee shall convert the 	prices of bids expressed in various currencies into those in which the bid is payable in CFA francs. 31.2 The conversion shall be done using the selling rate fixed by the Bank of Central African States (BEAC) under the conditions defined by the Special Regulations.

Article 32: Evaluation and comparison of financial bids 
32.1   Only bids considered as being in compliance, as per the provisions of article 28 of the General Regulations, shall be evaluated and compared by the Evaluation sub-committee.

32.2 By evaluating the bids, the Evaluation Sub-committee shall determine for each bid the evaluated amount of the bid by rectifying the amount as follows:

a) By correcting any possible error in accordance with the provisions of article 30.2 of the General 		Regulations; 
b)By excluding projected sums and where necessary provisions for unforeseen occurrences featuring 		in the bill of quantities and estimates but by adding the amount of works done under State 		supervision where they are costed in a competitive manner as specified in the Special Regulations.

c) By converting into a single currency the amount resulting from the rectifications (a) and (b) above, 		in accordance with the provisions of article 31(2) of the General Regulations; 
d)By appropriately adjusting any other modification, divergence or quantifiable reservation on 		technical or financial basis.

e) By taking into consideration the various execution time-limits proposed by the bidders, if they are 		authorised by the Special Regulations; 
f)If need be, in accordance with the provisions of article 13(2) of the General Regulations and the 		Special Regulations by applying the rebates offered by the bidder for the award of more than one 		lot, if this Invitation to Tender is launched simultaneously for several lots.

g) If need be, in accordance with the provisions of article 18(3) of the Special Regulations and the Technical Specifications, the proposed technical variants, if they are permitted, shall be evaluated on their own merit and independently of the fact that the bidder offered or not a price for the technical solution specified by the Contracting Authority in the Special Regulations.

32.3 The estimated effect of price revision formulae featuring in the GAC and SAC applied during the period of execution of the Contract shall not be considered during the evaluation of bids.

32.4 If the bid judged the lowest bid is considered abnormally low or strongly unbalanced in relation to the estimates of the Project Owner for the works to be executed in this Contract, the Tenders Board may, from the sub-details of prices furnished by the bidder for any element or all the elements of the bill of quantities

25

and estimates, verify if these prices are compatible with the construction methods and proposed calendar. In the case where the justifications presented by the bidder are not satisfactory, the Contracting Authority may reject the bid after the technical opinion of the Public Contracts Regulatory Agency.

Article 33: Preference granted national bidders 
National Contractors shall benefit from a margin of national preference during the evaluation of bids as provided for in the Public Contracts Code.

Article 34: Award 
34.1     The Contracting Authority shall award the Contract to the bidder whose bid was judged essentially in compliance with the Tender File and who has the required technical and financial capacities to execute the Contract satisfactorily and whose bid was evaluated as the lowest by including, where necessary, proposed rebates

34.2     If, according to article 13(2) of the General Regulations, the Invitation to Tender comprises several lots, the lowest bid shall be determined by evaluating this Contract with other lots to be awarded concurrently, by taking into account the rebates offered by the bidders in the case of more than one lot.

34.3       Any award of Contract shall be made to the bidder fulfilling the technical and financial capacities 	required resulting from the evaluation criteria and presenting the bid evaluated as the lowest.

Article 35:  The right by the Contracting Authority to declare an Invitation to Tender unsuccessful or 		cancel a procedure 
The Contracting Authority reserves the right to cancel a procedure of Invitation to Tender after the authorisation of the Minister Delegate at the Presidency in charge of Public Contracts where the bids have been opened or to declare an Invitation to Tender unsuccessful after the advice of the competent Tenders Board, without any claims being entertained.

Article 36: Notification of award of the Contract 
 Before the expiry of the validity of the bids set in the Special Regulations, the Contracting Authority shall notify the preferred bidder by telecopy confirmed by registered mail or by any other means that his bid was retained. This letter will indicate the amount the Project Owner will pay the Contractor to execute the works and the execution time-limit.

Article 37: Publication of results of award and petitions 
37.1 The Contracting Authority shall communicate to any bidder or administration concerned, upon request addressed to it within a maximum deadline of five (5) days after Publication of the award results, the Independent Observer’s report as well as the minutes of the award session of the related Contract to which shall be attached the evaluation report of the bids.

37.2 The Contracting Authority is bound to communicate the reasons for the rejection of bids of the bidders concerned who so request.

37.3 After Publication of the award results, bids that are not withdrawn within fifteen (15) days shall be destroyed, without any claims for compensation being entertained. Only the copy destined for the body in charge of regulation shall be kept.

37.4 In case of petition, it should be addressed to the Public Contracts Authority, with copies to the body in charge of the regulation of Public Contracts, the Contracting Authority and the chairperson of the Tenders Board concerned.

It must take place within a maximum deadline of five (5) working days after the Publication of the results.

Article 38: Signing of the Contract 
38.1   After Publication of the results, the draft Contract subscribed by the successful bidder is submitted to the Tenders Board for examination and where applicable, to the Minister in charge of Public Contracts for prior endorsement.

26

38.2 The Contracting Authority has a deadline of seven (7) days to sign the Contract from the date of reception of the draft Contract examined by the competent Tenders Board and subscribed by the successful bidder and where applicable, the endorsement of the Minister in charge of Public Contracts.

38.3    The Contract must be notified to the successful bidder within five (5) days of its date of signature.

Article 39:  Final Bond 
 39.1    Within twenty (20) days of the notification by the Contracting Authority, the Contractor shall furnish the Project Owner with a final bond, to guarantee the complete execution of the works.

39.2    The bond whose rate varies between 2 and 5 percent of the amount of the Contract inclusive of all taxes, may be replaced by a guarantee from a banking establishment approved according to the instruments in force with the Project Owner  as beneficiary or by a joint or several guarantee.

39.3   Small and medium-sized enterprises (SME) constituted of national capital and managed by nationals may, in lieu of the guarantee, provide a statutory lien or a bond issued by a banking establishment or first rate financial institution approved in accordance with the instruments in force.

39.4     Failure to produce the final bond within the prescribed time limit shall likely cause the termination of 	the Contract under the terms laid down in the General Administrative Conditions.

27

Document No. 3

SPECIAL REGULATIONS OF THE

INVITATION TO TENDER

28

SPECIAL REGULATIONS OF THE INVITATION TO TENDER

| References of the General regulations | Description |
| --- | --- |
| 1 | Definition of works: For the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots. Name and address of the Contracting Authority: The President of the North West Regional Assembly Reference of Invitation to Tender: No ___/ONIT/NWRA/NWRAITB/2026 of ____/____/2026 |
| 2 | Execution deadline: Four (04) Months per lot |
| 3 | Source of financing Works which form the subject of this Invitation to Tender shall be financed by the 2026 Public Investment Budget assigned to the North West Regional Assembly |
| 4 | List of pre-qualified candidate. Not applicable |
| 5 | Origin of building materials, equipment, and supplies: The materials will generally be from natural sources in Cameroon or imported. |

6.1 Evaluation criteria 
The bids shall be evaluated according to the main criteria as follows:

C.Eliminatory criteria

1.Absence or non-conformity of an element in the administrative file non regularized within 48 	hours after opening of bids 
2.Execution deadline higher than prescribed in the Tender File; 
3.False declaration or falsified documents; 
4.Absence or insufficient bid bond; 
5.A bid with the external envelope carrying a sign leading to the identification of the bidder; 6.Incomplete financial file; 
7.Non respect of 75% of essential criteria; 
8.Suspended by MINMAP for 2026.

9.Average annual turnover of at least the tendering amount (Average annual turnover calculated as total certified payments received for contracts in progress or completed, within the last five (5) years (from 2021). This should be justified by copies of past contracts (completed or ongoing). Final reception minutes for all completed contracts before 2026 and provisional reception minutes for contracts completed in 2025 should be presented.

10.Failure to provide a backup copy of offers saved in a USB key or a CD/DVD on time; 11.Failure to comply with the format of file type and size for online submission; 
12.Failure to present a CDEC receipt or proof of  deposit of the amount of the bid bond requested 	into the Deposit and Guarantee Fund; 
13.Failure to present a certificate of categorization or receipt of deposit of file for categorisation 	of the enterprise in the “Building and General Equipment” sub-sector of activities.

D.Essential criteria

1-General presentation of the Tender Files;

2- Financial capacity;

3-References of the company in similar achievements visa by the competent administrative 	authority;

4-Quality of the personnel;

5-Technical organization of the works;

29

6-Safety measures on the site;

7-Logistics;

8-Attestation of site visit duly signed on honour by the bidder and report of site visit with pictures;

9-Special Technical Clauses initialed in all the pages, signed and dated at the last page;

10-Special Administrative Clauses completed and initialed in all the pages, signed and dated at the 	last page.

The criteria relating to the qualification of candidates could be indicative on the following: The essential criteria are subjected to minima whose detail is given in the Special Tender Regulation (RPAO).

This evaluation will be done in a purely positive way (yes) or negative (no) with an acceptable minimum from at least 75% of the essential criteria taken in account.

The Contract will be awarded to the bidder who would have proposed the offer with the lowest amount, in conformity with the regulations of the Tender Documents and having satisfied 100% of the eliminatory criteria and at least 75% of the essential criteria. A bidder can bid for more than one lot but can be awarded only one lot.

ARTICLE 6: Language of the bids: 
	 The offer like any correspondence and all documents concerning the tender, exchanged between the tenderer and the Project Owner will be written in French or English. The complementary documents and the printed papers form provided by the Bidder can be written in another language on condition of being accompanied by a precise translation in French or English; in which case and for purposes of interpretation of the offer, the translation will be taken.

7. PRESENTATION OF THE TENDER

ENVELOPE A: ADMINISTRATIVE DOCUMENTS: It shall contain the administrative documents of the enterprise.  These documents shall be original or copies certified by competent authorities   not more than three months.

ADMINISTRATIVE DOCUMENTS.

| DOCUMENT N° | DESCRIPTION |
| --- | --- |
| A.1 | Declaration of intention to tender stamped with the tariff in force (written by the bidder) with a fiscal stamp. |
| A.2 | Certified Copy of the Business Registration, not more than three months old. |
| A.3 | Certificate of non-bankruptcy established by the Court of 1st instance or the Chamber Commerce, Industry and Trade of the place of residence of the bidder, not more than three (03) months. |
| A.4 | Attestation of bank account of the bidder, issued by a first rate-bank approved by the Ministry in charge of Finance. (See list of approved banks on page 103 of this tender file) |
| A.5 | Purchase receipt of Tender File issued by North West Regional Assembly Treasury |
| A.6 | A bid bond issued by a first rate-financial institution approved by the Ministry in charge of Finance in conformity with COBAC conditions and a CDEC receipt or proof of deposit of the amount of the bid bond requested into the Deposit and Guarantee Fund. |
| A.7 | An attestation of non-exclusion from Public Contracts issued by the Public Contracts Regulatory Board (ARMP) |
| A.8 | An Attestation of the National Social Insurance Fund stating that the bidder has met all his obligations vis a vis the Fund; the attestation valid within the given time. |
| A.9 | Tax compliance certificate or Clearance Certificate signed by the chief of Centre of Taxes that the bidder has met all the statutory declarations in issues of taxes in the current financial year; this certificate should be less than three months old. |
| A.10 | Copy of a valid taxpayer’s card, delivered by the chief of center of Taxes. |
| A.11 | A certified copy of categorization certificate by MINMPA or receipt of deposit of file for |

30

|  | categorisation of the enterprise in the “Building and General Equipment” sub-sector of activities |
| --- | --- |
| A.12 | Plan and attestation of location of the Company signed by the bidder on honour |
| A.13 | Power of attorney if necessary |
| A.14 | Group agreement where applicable |
| A.15 | Special Technical Clauses initialed on all the pages and signed, dated and stamped on the last page. |
| A.16 | Special Administrative Clauses completed and initialed on all the pages, signed, dated and stamped on the last page. |

ENVELOPE B:  TECHNICAL DOCUMENT:  It shall contain the following:

| A. General presentation of bids |  |
| --- | --- |
| - Presence of all documents ………………………………………………….. | yes/no |
| - Properly bound…………………………….……............ | yes/no |
| - Table of content ……………………………………..…………… | yes/no |
| - Separators in colour apart from white……………….……………… | yes/no |
| - Order prescribed respected……………………………………. | yes/no |
| - Clearness of the documents……………………………............... | yes/no |
| TOTAL 1 | /6 |
| B. The company references |  |
| References of the company in similar works for the past ten (10) years: |  |
| - 01 certified copy of similar contract visa and legalized by a competent administrative authority equal or above 70 million FCFA ATI (1st and last pages) and PV of final reception for works realized before 2025 and provisional reception for works realized in 2025. | yes/no |
| - 01 certified copy of similar contract visa and legalized by a competent administrative authority equal to or more than 35 million CFA ATI (1st and last pages) and PV of final reception for works realized before 2025 and provisional reception for works realized in 2025. | yes/no |
| - 01 certified copy of similar contract visa and legalized by a competent administrative authority below 35 million and above 17 million (1st and last pages) and PV of final reception for works realized before 2025 and provisional reception for works realized in 2025. | yes/no |
| TOTAL 2 | /3 |
| C. Equipment |  |
| - Proof of ownership or hire of a domp truck ……………………. | yes/no |
| - Proof of ownership or hire of a 4x4 pick-up vehicle in good operating condition ………… | yes/no |
| - Proof of ownership of a vibrator in good operating condition … | yes/no |
| - Proof of ownership or hire of a concrete mixer of at least 0.5m3 volume ………… | Yes/no |
| -Proof of ownership of masonry tool kids …………………….…………………… | yes/no |
| -Proof of ownership of electrical tool kid ……………………………………… | yes/no |
| -Prof of ownership of carpentry tool kids ……………… | yes/no |
| -Proof of ownership or hire of plumbing tool kids …………………… | yes/no |
| TOTAL 3 | /8 |

31

| D. Qualification of site personnel |  |
| --- | --- |
| - Organizational Chart of the enterprise………………… | yes/no |
| - Organizational Chart of site with comments …………….. | yes/no |
| Works Director: Civil Engineer with at least 05 years of working experience |  |
| - Diploma of work Director certified...………………………………………… …. | yes/no |
| - Attestation of presentation of original diploma works director ………… | yes/no |
| - CV signed and dated by works Director………………… | yes/no |
| - Professional experience of works Director above five years…………. | yes/no |
| -Attestation of availability dully signed by the works director ………… | yes/no |
| Site foreman: Senior technician in Civil Engineering with at least 05 years of working experience |  |
| - Certified copy of certificate of site foreman...……… ………… | yes/no |
| -Attestation of presentation of original diploma of site foreman ……… | yes/no |
| - CV signed and dated by site foreman………………… | yes/no |
| - Professional experience of site foreman above five years ……… | yes/no |
| -Attestation of availability of site foreman …………....... | yes/no |
| Chief builder: BAC in Civil Engineering with at least three years of working experience |  |
| - Certified copy of diploma of chief builder……………… | yes/no |
| - Attestation of presentation of original diploma of Chief Builder … | yes/no |
| - CV signed and dated by Chief Builder …………………. | yes/no |
| - Attestation of availability of Chief Builder ……… | Yes/no |
| Chief carpenter: BAC in wood work with at least three years of working experience |  |
| - Certified copy of diploma of chief carpenter……………. | yes/no |
| - Attestation of presentation of original diploma of Chief Carpenter …. | yes/no |
| - CV signed and dated by Chief Carpenter …………………. | yes/no |
| - Attestation of availability of Chief Carpenter ……… | Yes/no |
| Chief Electrician: BAC in Electricity with at least three years of working experience |  |
| - Certified copy of diploma of chief electrician ……………. | yes/no |
| - Attestation of presentation of original diploma of chief electrician ….. | yes/no |
| - CV signed and dated by chief electrician …………………. | yes/no |
| - Attestation of availability of chief electrician ……… | Yes/no |
| Chief Plumber: CAP in plumbing with at least three years of working experience |  |
| - Certified copy of diploma of chief plumber ……………. | yes/no |
| - Attestation of presentation of original diploma of chief plumber.. | yes/no |
| - CV signed and dated by chief plumber …………………. | yes/no |
| - Attestation of availability of chief plumber | Yes/no |
| Chief painter: CAP/trade certificate in painting at least three years |  |
| - Certified copy of diploma of chief painter ……………. | yes/no |

32

| - Attestation of presentation of original diploma of chief painter … | yes/no |
| --- | --- |
| - CV signed and dated by chief painter …………………. | yes/no |
| - Attestation of availability of chief painter ………….. | Yes/no |
| TOTAL 4 | /31 |
| E. The methodology of intervention and execution of work |  |
| - Attestation of site visit signed by the bidder on honour. | yes/no |
| - Site Visit report signed and dated by bidder or dully authorised representative with pictures ……………………... | yes/no |
| - Detailed technical note on the organization and execution of works… | yes/no |
| - Coherence synchronized planning of execution of works……………… | yes/no |
| - Coherence of Individual Protection Plan (IPP) within the building site… | yes/no |
| - Coherence of the General Security and Safety Plan (GSSP) within the building site… | yes/no |
| - Description of the socio - environment measures for site protection….. | yes/no |
| - Coherence in the methodology of execution of works ……………… | yes/no |
| - Coherence in the organization of the site……………………….…………….. | yes/no |
| -Plan of supply of constructional materials and storage conditions …………… | yes/no |
| - CCTP dully initialled on each page, signed and dated on the last page | yes/no |
| TOTAL 4 | /11 |
| F– Pre-financing |  |
| Attestation of credibility shall be at least 80% of the bid price issued by a first rate banking institution............. | yes/no |
| TOTAL | /1 |
| TOTAL = TOTAL1 + TOTAL2+ TOTAL3+ TOTAL4+ TOTAL5 + TOTAL6 | /60 |

ENVELOPE C- FINANCIAL FILE 
The third internal envelope shall be labled and shall contain the following documents:

| No. | DESIGNATION. |
| --- | --- |
| C1 | A submission letter, signed, dated and stamped.(see ANNEX 3) |
| C2 | Completed and signed frame work of unit prices. |
| C3 | Signed Bills of quantities and cost estimates indicating the total amount without taxes (HT) and with taxes (TTC) |
| C4 | Sub details of unit prices |

The bidders will use for this purpose the documents and models envisaged in the Tender Documents, subject to the provisions of Article 12.2 of the General Regulation of the Invitation to Tender (GRIT) concerning the other possible forms of bid bond.

The various parts of the same file must be separated with colour guides from as well in the original as 	in the copies, so as to facilitate its examination

The Tender must be submitted by the Tenderer on the COLEPS Platform not later than __/__/2026 at 10:00am. A backup copy of the Tender saved In a USB key or a CD/DVD must be sent in a sealed envelope with a clear and legible indication “backup copy” within the time limit bearing the label: 
OPEN NATIONAL INVITATION TO TENDER FILE

33

N° ______/ONIT/NWRA/ITB/2026 OF ___ / ___ / 2026 FOR THE CONSTRUCTION OF WORKSHOPS IN SOME GOVERNMENT TECHNICAL HIGH SCHOOLS OF THE NORTH WEST REGION DIVIDED INTO TWO (02) LOTS 
“To be opened only during the bid-opening session”

File Size and Format: 
	For online bidding, the maximum sizez of the documents that will be uploaded on the platform and constituting the bidder’s offer shall be; 
	-	5 Mb for Administrative offers; 
	-	15 Mb for the Technical offers; 
		5 Mb for the financial offers. 
-Supported formats shall include: 
	-	PDF formats for texts documents; 
	-	JPEG formats for images.

The Tenderer shall use a compression software to reduce the size of the file to be submitted.

CONTRACT PRICE

ARTICLE 8: Currency of payment

This National Invitation to tender is awarded on total and Contractual price, inclusive of all taxes, firm and non-revisable for the works defined in the present Invitation to Tender.

The corresponding amount will be calculated inclusive of all taxes and the prices will be obligatorily expressed in francs CFA.

The unit schedule price expressed out in figures and letters and in seven (07) copies will be joined to the offer. In the event of error between the prices in figures and letters, the latter will precede and be used as a basis of calculation of the amount of the offer.

The establishment of the prices will be done on the basis of economic condition into force in Republic of Cameroon at the handover date of the offers.

ARTICLE 9: Transport and delivery

The materials for work must be protected during transportation through packaging whether by air, railway or road according as the case may be. The conditions of storage must be of tropical type.

ARTICLE 10: Guarantee and retention guarantee

10.1 Provisional guarantee 
	The amount of the provisional guarantee or guarantee of tender is fixed as of the table below:

| LOT No. | PROJECT | AMOUNT | AMOUNT OF BID BOND | TENDER FILE FEE |
| --- | --- | --- | --- | --- |
| 01 | Construction of a Building Workshop at GTHS Misaje in Donga/Mantung Division of the North West Region (Lot 1) | 45,179,915 | 903,600 | 79,000 |
| 02 | Construction of a G+1 IT Centre at GTHS Bamendakwe in Mezam Division of the North West Region (Lot 2) | 70,000,000 | 1,400,000 |  |

The time of validity of this guarantee is one hundred and twenty (120) days as from the date of depositing of the offers. It must also have a CDEC receipt or proof of deposit of the amount of the bid bond requested into the Deposit and Guarantee Fund.

10.2 Final Bond 
	The final Bond is fixed at two percent (2%) maximum of the initial amount of the services envisaged in the contract.

34

It could be replaced by a personal guarantee from a banking institution approved by the Ministry of Finances, following COBAC conditions.

It will have to be made up in twenty (20) days following the notification of the signature of the Contract from a bank approved by the Minister in charge of Finances.

It must also have a CDEC receipt or proof of deposit of the amount of the final bond requested into the Deposit and Guarantee Fund.

10.3   Guarantee Retention 
	The Guarantee Retention shall be set at ten percent (10%) of the contract amount inclusive of all 	taxes. The Guarantee Retention can be deducted or cautioned. If cautioned, the guarantee Retention is 	issue by a first rate banking institution or insurance company and must also have a CDEC receipt 	or proof of deposit of the amount of the guarantee Retention requested into the Deposit and 	Guarantee Fund.

ARTICLE 11: Period of validity of the offers

| offers. | The bidder will remain committed to his offer for Ninety (90) days as from the handover date of the |
| --- | --- |

If at the end of this period, the Contract is not notified to him, the bidder will be able, either to cancel his offer, or to ask for a new negotiation of the unit prices.

ARTICLE 12:  Number of copies to be submitted

For Online submission, see article 7 page 34.

ARTICLE 13: Date and latest time of submission of bids 
The backup copy of offers saved in a USB key or a CD/DVD will have to arrive under closed fold and seal latest __/__/2026 at 10:00am, by mail registered with acknowledgement of delivery or by deposit against receipt to the following address: Office of the Director of General Affairs at the North West Regional Assembly, North West (Tel N° 2 33 36 00 92) or submitted online using the address: www.marchespublics.cm. Beyond this time no offer will be received nor accepted.

ARTICLE 14: Opening of the bids 
	The opening of the bids will be carried out in the conference room of The President of the North West Regional Assembly Internal Tenders’ Board on __/__/2026 as from 11: 00am, by the Regional Assembly Internal Tenders’ Board sitting in the presence of the bidders or their mandated representatives having a good knowledge of the file.

AWARD OF THE CONTRACT

ARTICLE 15: Award of the Contract 
	 The Tenders Board will propose to the Contracting Authority to award the Contract to the bidder who will have presented the offer with the lowest amount, essentially conforming to the regulations of the Tender File, having satisfied 100% of all the eliminatory criteria and at least 75% of the essential criteria taken into account. (A Bidder can bid for more than one Lot but can be awarded only one Lot)

The decision carrying attribution of the Contract will be published by way of press release or any other means of Publication of use in the Administration.

If the Contract passed on the basis of technical alternative suggested by the bidder, the Contracting Authority reserves the right to introduce all the provisions there allowing him to guarantee itself against the real overrun costs of the alternative compared to his estimate of origin. In the absence of these last precise details, any additional charge due to an alternative will be inadmissible.

To this end, it is specified that a bidder cannot claim to be compensated, if it is not taken action on his offer.

35

The Contracting Authority reserves the right not to take action on an Invitation to Tender, if it did not obtain a proposal which appears acceptable to him.

ARTICLE 16: SITE INSTALLATION 
	Before the commencement of works, the Contractor must be installed on the site by the following: 		The President of the North West Regional Assembly or his representative (Chairman) 		The Contract Manager 
		The Contract Engineer (Secretary) 
		The Regional Delegate MINMAP North-West or his representative; 
		The Regional Delegate MINEPAT North-West or his representative; 
		Contractor 
		The Beneficiary (Observer) 
		The Commissioner for Education at the North West Regional Assemby (Observer)

36

Document No. 4

SPECIAL ADMINISTRATIVE CONDITIONS (SAC)

37

Table of contents 
Chapter I: General 
Article 1     - Subject of the Contract 
Article 2     - Award procedure 
Article 3     - Definitions and duties (article 2 of GAC supplemented) 
Article 4     - Language, applicable law and regulations 
Article 5     - Constituent documents of the Contract (article 4 of GAC) 
Article 6     - General applicable instruments 
Article 7     - Communication (GAC articles 6 and 10 supplemented) 
Article 8     - Administrative Orders (article 8 of GAC supplemented) 
Article 9     - Contracts with conditional phases (article 15 of GAC) 
Article 10   - Contractor’s personnel (article 15 of GAC supplemented) 
Chapter II: Financial conditions 
Article 11   - Guarantees and bonds (articles 29 and 41 of GAC supplemented) Article 12   - Amount of Contract (articles 18 and 19 supplemented) 
Article 13   - Place and method of payment 
Article 14   - Price variation (article 20 of GAC) 
Article 15   - Price revision formulas 
Article 16   - Price updating formulas (article 21 of GAC) 
Article 17   - Work under State supervision (article 22 of GAC supplemented) Article 18   - Evaluation of works (article 23 supplemented) 
Article 19   - Evaluation of supplies (article 24 of GAC) supplemented) 
Article 20   - Advances (article 28 of GAC) 
Article 21   - Payments for the works (articles 26, 27 and 30 of GAC supplemented) Article 22   - Interests on overdue payments (article 31 of GAC supplemented) Article 23   - Penalties for delay (article 32 of GAC supplemented) 
Article 24   - Payment in case of a group of enterprises (article 33 of GAC) 
Article 25   - Final detailed account (article 35 of GAC) 
Article 26   - General detailed account (article 35 of GAC) 
Article 27   - Tax and customs schedule (article 36 of GAC) 
Article 28   - Stamp duty and registration (article 37 of GAC) 
Chapter III: Execution of the works 
Article 29   - Nature of works 
Article 30   - Obligations of the Project Owner (GAC supplemented) 
Article 31   - Execution deadline of Contract (article 38 of GAC) 
Article 32   - Roles and responsibilities of the Contractor (article 40 of GAC) Article 33   - Making available documents and site (article 42 of GAC) 
Article 34   - Insurance of structures and civil responsibility (article 45 of GAC) Article 35   - Documents to be furnished by the Contractor (article 49 supplemented) Article 36   - Organisation and security of sites (article 50 of GAC) 
Article 37   - Implantation of structures (article 52 of GAC) 
Article 38   - Sub-Contracting (article 54 of GAC) 
Article 39   - Site laboratory and trials (article 55 of GAC) 
Article 40   - Site logbook (article 56 of GAC supplemented) 
Article 41   - Use of explosives (article 60 of GAC) 
Chapter IV: Acceptance 
Article 42   - Provisional acceptance (article 67 of GAC) 
Article 43   - Documents to be furnished after execution (article 68 of GAC) Article 44   - Guarantee time-limit (article 70 of GAC) 
Article 45   - Final acceptance (article 72 of GAC) 
 Chapter V: Miscellaneous provisions 
Article 46   - Termination of the Contract (article 74 of GAC) 
Article 47   - Force majeure (article 75 of GAC) 
Article 48   - Differences and disputes (article 79 of GAC) 
Article 49   - Drafting and dissemination of this Contract 
Article 50 and last: Entry into force of the Contract

38

CHAPTER I: GENERAL

Article 1:  Subject of Contract 
The subject of this Contract shall be for the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots.

Article 2: Contract award procedure 
This Contract is awarded by Open National Invitation to Tender No ________/ONIT/NWRA/ITB/2026 of __/__/2026.

Article 3: Definitions and duties (article 2 of GAC supplemented) 3.1General definitions (cf. Code)

The Contracting Authority shall be The President of the North West Regional Assembly; in this respect he preserves the original documents relating to the contract and transmits copies to the Public Contract Regulatory Agency.

The Contract Manager shall be The Director of General Affairs at the North West Regional Assembly. In this capacity, he shall respect the administrative, technical and financial clauses of this contract.

The Contract Engineer shall be The Regional Delegate of Public Works for the North-West. He shall validate the different crucial phases of work done, from the installation of the Contractor to the Provisional Technical Reception.

The Regional Delegation of MINMAP North-West shall carry out unannounced control for the 	execution of this project

The Divisional/Sub-Divisional Peace and Development Committees (P.D.C) shall carryout Social 	Control and report to the President of the Regional Assembly.
The Contractor shall be [to be specified].

3.2Security 
This Contract may be used as security subject to any form of transfer of the debt.

In this case: 
	-	The authority in charge of ordering payment shall be The President of the North West Regional 			Assembly.

-	The body or official in charge of payment shall beThe Paymaster General North West Region.-	The official competent to furnish information within the context of execution of this Contract shall be 		The Director of General Affairs at the North West Regional Assembly.

-	The authority in charge of clearance shall be The Specialised Finance Controller of the North 		West Regional Assembly.

3.3   Duties of the Control Mission, Project Manager (Not applicable) 3.3.1Control Missions[to be specified].

Article 4: Language, law and regulation applicable 
1.1The language to be used shall be [English and/or French].

1.2The Contractor shall be bound to observe the law, regulations and ordinances in force in Cameroon both 	within his own organization and in the execution of the Contract.

If the laws and regulations in force at the date of signature of this Contract are amended after the signature of the Contract, the possible direct resulting costs shall be taken into account without gain or loss for either party.

Article 5:Constituent documents of the Contract (Article 4 of GAC) The constituent Contractual documents of this Contract are in order of priority: 1)  The tender or commitment letter;

2)  The bidder’s tender and its annexes in all provisions not contrary to the Special Administrative

Conditions (GAC) and the Special Technical Conditions (STC) hereunder;

39

3)  The Special Administrative Conditions (SAC);

4)  The Special Technical Conditions (STC);

5)  The particular elements necessary for the determination of the Contract price, such as, in order of

priority: the unit price schedule, the statement of all-in prices, detailed estimates, the breakdown of all-

in prices and the sub-details of unit prices;

6)  Plans, calculation notes, trial documents, geotechnical documents;

7)  The General Administrative Conditions applicable on Public works Contracts that went into effect by

Order No. 033/CAB/PM of 13 February 2007;

8)  The General Technical Condition(s) applicable on the services forming the subject of the Contract.

Article 6: General instruments in force 
This Contract shall be governed by the following general instruments: 
	1.Law No 2018/011 of 11 July, 2018 on  the Code of Transparency  and Good Governance in the management 		of Public Finances in Cameroon; 
	2.Law No 2018/012 of July 11, 2018 on the financial regime of the state and other public entities; 
	3.Law No 2019/024 of December 24, 2019 on the General code of Regional and Local Authorities; 
	4.Law No. 96/12 of 5th August 1996 on the management of the environment; 
	5.Law No. 2025/012 of 17 December, 2025 bearing on the Finance Law of the Republic of Cameroon for the 		2026 Financial Year 
	6.Law No. 2019/024 of December, 2019 on the General Code of Decentralized Territorial Communities. 	7.Decree No. 2013/159 of 15 May, 2013 putting in place a special regime on Administrative Control of Public 		Finances 
	8.Law No 2016/017 of 14 December 2016 instituting the Mining Code; 
	9.Decree No. 2018/366 of 20th June 2018 to institute the Public Contracts Code and its texts of application; 	10.Decree No. 2018/4992/PM of 21 June, 2018 putting in place the General Rules regulating the maturation of 		Public Investment projects; 
	11.Decree No. 2020/375 of 07 July, 2020 on the General Regulations of Public Accounting.

12.Instruments governing the various professional bodies; 
13.Decree No. 2001/048 of 23rd February 2001 relating to the Setting up, Organization and Functioning of the 	Public Contracts Regulatory Agency 
14.Decree No. 2003/651/PM of 16th April 2003 to lay down the Procedure for Implementing the Tax and 	Customs System applicable to Public Contracts; 
15.Decree No. 2012/075 of 8th March 2012 to organise the Ministry in charge of Public Contracts; 
16.Order No 212/A/MINMAP of September 28, 2021 organizing the operation of internal structures for the 	administrative management of Public contracts; 
17.Order No. 000007/MINMAP of 01 January….. laying down the procedures for awarding and executing 	framework agreements 
18.Order No. 168/A/MINMAP of August 11, 2021 setting the terms and conditions for the award and execution 	of design-build contracts; 
19.Circular Letter No. 000010/LC/MINMAP/CAB of 22 September 2020, the clarifying the payment documents 	of the Administrative co-contractors to be submitted for visa prior to the Ministry in charge of Public 	Procurement 
20.Order No. 001/CAB/PR of 19th June 2012 relating to the Award and Control of Execution of Public Contracts; 21.Letter No 00006/LC/PR/MINMAP/CAB of 17 August, 2021 clarifying the control of public procurement and 	specifying the procedures for its exercise to project owners and delegated project owners circular.

22.Law No 2023/019 of 19/DEC/2023 instituting the 2026 Financnial Law of the Republic of Cameroon 23.Circular No. 00001877/C/MINFI of 31st  December, 2025 on instructions relating to the execution of finance 	laws, the monitoring and control of the execution of the budget of the state and other public entities, for the 	2026 financial year; 
24.Circular No. 0001/PR/MINMAP/CAB of 25 April, 2022 relating to the application of the Public Procurement 	Code 
25.Press Release No. 000024/R/MINMAP/CAB/CT2 of 5 August, 2025 announcing the presentation of the 	categorization certificate in the award process of public contracts.

26.The  MINCOMMERCE Decree setting the Price List O

40

27.Order No 402/A/MINMAP/CAP of 21 October 2019 setting the nature and threshold of contracts reserved for 	craftsmen, mall and medium-sized enterprises, grassroots communities and civil society organisations, and the 	modalities of their application; 
28.Order No 000333/O/MINMAP/CAB of 27 December 2024 to set the schedule for the migration to exclusive 	award of public contracts electronically.

29.Circular No 0000014/C/MINMAP/CAB of 23rd July, 2025 on the conditions for constitution, guarantee, 	preservation, release, restitution and realization of guarantees in public conracts, 
30.Circular letter No. 00000002/LC/MINMAP/CAB of 12 May 2022 relating to the continuity of the public 	procurement service in the event of a sanction by a Project Owner or Delegated Project Owners or members of 	a commission public procurement in accordance with the provision of articles 195 of the code of public 	contracts.

31.Unified Technical Documents (DTU) for building works; 
32.Applicable standards; 
33.Other instruments specific to the domain concerned with the Contract.

Article 7:Communication (Articles 6 and 10 supplemented) 
	7.1 All notifications and written communication within the framework of this Contract shall be sent to

the following address:

a)In the case where the contractor is the addressed: beyond the time-limit of 15 days fixed in Article 6

(1) of  the GAC to make his domicile known to the Contract Manager and immediately after

completion of the works, correspondences shall be validly address to council where the Contractor

Resides.

b)In case where the Contracting Authority is the addressee: correspondences shall be addressed to:

The President of the North West Regional Assembly with copies addressed to the Contract Manager,

the Engineer and the Regional Delegation of Public Contract North West.

7.2The contractor shall address all written notifications or correspondences to the Engineer with a copy

to the Contract Manager and the Regional Delegation of Public Contract North West.

Article 8:Administrative Orders (Article 8 of GAC) 
The various Administrative Orders shall be established and notified as follows: 
8.1 	The Administrative Order to start execution of works shall be signed by the Contracting Authority 	and notified to the Contractor by the Contract Manager with a copy to the Contracting Authority, the 	Regional Delegation of Public Contract North West, the Contract Engineer and the Paying Body, 	where applicable.

8.2 	Upon proposal by the Contract Manager, Administrative Orders with an incidence on the objective, 	the amount and execution deadline shall be signed by Contracting Authority and notified by the 	Contract Manager to the Contractor with a copy to the Contracting Authority, the Regional 	Delegation of Public Contract North West, the Contract Engineer, and the Paying Body. The prior 	endorsement of the Paying Body shall possibly be required before the signature of those that have an 	incidence on the amount.

8.3 	Administrative Orders of a technical nature linked to the normal progress of the work and without 	financial incidence shall be signed directly by Contract Manager and notified to the Contractor by the 	Contract Engineer or Project Manager  (where applicable) with a copy to the Contracting Authority, 	the Regional Delegation of Public Contract North West and Contract Manager.

8.4 	Administrative Orders serving as warnings shall be signed by the Contracting Authority and notified 	to the Contractor by the Contract Engineer with a copy to the Contract Manager, the Regional 	Delegation of Public Contract North West.

8.5 	Administrative Orders for suspension or resumption of work as a result of the weather or any other 	case of force majeure shall be signed by the Contracting Authority and notified by the Contract 	Engineer to the Contractor with a copy to the Contract Manager the Regional Delegation of Public 	Contract North West.

41

8.6 	Administrative Orders prescribing works necessary to remedy disorders which could appear on 	structures during the guarantee period and not related to normal usage shall be signed by the Contract 	Manager upon the proposal of the Contract Engineer and notified to the Contractor by the Contract 	Engineer.

8.7 	The Contractor has a time-limit of fifteen (15) days to issue reservations on any Administrative Order 	received. Having reservations shall not free the enterprise of executing the Administrative Orders 	received.

8.8 	Concerning Administrative Order signed by the Contracting Authority and notified by the Contract 	Manager, the notification must be done within a maximum of 30 days from the date of transmission 	by the Contracting Authority to the Contract Manager. Beyond this deadline, the Contracting 	Authority shall establish the default of the Contract Manager, take over from him and carry 	out the said notification.

Article 9: Contracts with conditional phases (Article 9 of GAC) (Not applicable) 
9.1	 This Contract has only one phase for 2026 financial year. At the end of phase one, the Project Owner 	shall carry out the acceptance of the works and issue an attestation of proper execution to the 	Contractor. This attestation shall condition the start of the following conditional phase.

9.2   The time-limit granted for notification of the Administrative Order to start execution of a conditional 	phase shall be five (5) days.

Article 10: Contractor’s equipment and personnel (Article 15 of GAC supplemented) 
10.1 	Any modification, even partial, made on the technical bid shall only occur after the written approval

of the Contract Manager. In case of modification, the personnel replaced shall be a member of staff

of equal competence (qualifications and experiences).

10.2 	In any case, the lists of supervisory staff to be used shall be subject to the approval of the Project

Owner in the days following notification of the Administrative Order to start execution. The contract

Manager has 5 (five) days to notify his opinion in writing with a copy sent to the Contract Engineer.

Beyond this time-limit, the staff list shall be considered as approved.

10.3 	Any unilateral modification on the supervisory staff made in the technical bid prior to and during the 	works shall be a reason for termination of the Contract as mentioned in article 45 below or the 	application of penalties.

CHAPTER II: FINANCIAL CONDITIONS

Article 11 Guarantees and bonds (Articles 29 and 41 of GAC) 
	11.1 Final bond 
The final bond shall be set at 2 % of the amount of the Contract, inclusive of all taxes.

It is constituted and transmitted to the Contract Manager within a maximum deadline of twenty (20) days of the notification of the Contract. It must also have a CDEC receipt or proof of  deposit of the amount of the final bond requested into the Deposit and Guarantee Fund.

The bond shall be returned or the guarantee released within one month following the date of provisional acceptance of the works, following a release issued by the Contracting Authority upon request by the Contractor.

11.2 Performance bond 
The retention fund shall be set at 10 % of the amount of the Contract, inclusive of all taxes.

The return or release of the retention fund or security shall be done within one month after final acceptance by release issued by the Contracting Authority upon request by the Contractor.

If cautioned, the Performance bond must also have a CDEC receipt or proof of deposit of the amount of the Performance bond into the Deposit and Guarantee Fund

42

11.3Guarantee of start-off advance 
The contractor may be granted a start off amount of 20% of the contract amount (inclusive of taxes) upon request.

The start-off payment shall be guaranteed at 100% by a Cameroonian bank recognized by the Ministry in charge of Finance.

The Guarantee of start-off advance must have a CDEC receipt showing the deposit of the amount of the Guarantee of start-off advance into the Deposit and Guarantee Fund.

Article 12: Amount of the Contract (Articles 18 and 19 of GAC supplemented)

The amount of this Contract as indicated by the attached [detail or estimates] is_______ (in figures)_______(in letters) CFA francs Inclusive of All Taxes; that is:

| - - - - | Amount exclusive of VAT: _________(_______) CFA F Amount of VAT: __________(______) CFA F. Amount of TSR and/or _____________CFA F Net to be paid= EVAT-TSR and/or AIR |
| --- | --- |

Article 13: Place and method of payment 
The Project Owner shall release the sums due in the following manner:

a.For payments in CFA francs (amount in figures and letters exclusive of taxes) by credit to 	account No._________ opened in the name of the Contractor in the ___________bank.

b.For payments in foreign currencies (amount in figures and letters exclusive of taxes) by credit to 	account No._________ opened in the name of the Contractor in ________bank.

Article 14: Price variation (Article 20 of GAC) 
	33.1Prices shall be firm.

a.Payments on account made to the Contractor as advances shall not be revisable.

b.Revision shall be “frozen” upon expiry of the Contractual time-limit, except in the case of price 	reductions.

33.2  Price updating modalities (Not applicable)

Article 15: Price revision formulae (article 21 of GAC) (Not applicable)

Article 16: Price updating formulae (article 21 of the GAC) (Not applicable)

Article 17: Works under State supervision (Article 22 of GAC supplemented) 
17.1The percentage of works under State supervision shall not exceed 2% of the amount of the Contract and its additional clauses, where applicable.

17.2In the case where the Contractor were invited to execute works under State supervision, the submitted and duly justified expenditures shall be reimbursed to him under the following conditions: 
-	The quantities considered shall be the hours used or the quantities of building materials and 		materials used that was the subject of joint job cost sheets; 
-	The remunerations and salaries effectively paid to local labour shall be increased by forty percent 		(40 %) to take account of  social benefits; 
-	The hours put in by the heavy equipment shall be counted at the rate featuring in the sub-detail of 		prices; 
-	building materials and materials shall be reimbursed at cost price duly justified at the place of use, 		marked up by ten percent for loss, stocking and handling; 
			The amount for services thus calculated, including the hours put by heavy equipment shall be marked up by 25 % to take into account the overheads, profits and the Contractor’s unforeseen.

43

Article 18: Evaluation of works (article 23 of the GAC) The work done shall be evaluated using the unit price.

Article 19: Evaluation of supplies (article 24 of the GAC supplemented) 19.1 	[Indicate, where applicable, the modalities for payment of supplies]. 19.2 	No security shall be requested for payments on account on supplies.

Article 20: Advances (article 28 of the GAC) 
20.1The Contracting Authority may grant a start-off advance equal to 20 % of the amount of the Contract. 20.2 This advance whose value cannot exceed twenty (20) percent of the initial amount inclusive of all taxes shall be guaranteed at one hundred (100) percent by a financial establishment governed by Cameroon law or a first-rate financial institution in accordance with the instruments in force and reimbursed by deduction of the payments on accounts to be paid to the Contractor during the execution of the Contract according to the modalities laid down in the Special Administrative Conditions.

20.3 The total amount of the advance must be reimbursed not later than when the value in basic price of the works reaches eighty (80) percent of the amount of the Contract.

20.4 As the reimbursement advances, the Project Owner shall issue the release of the corresponding part of the guarantee upon the express request by the Contractor.

20.5The possibility of granting start-off advance or advance for supplies must be expressly stipulated in the Tender File.

Article 21: Payment for works (articles 26, 27 and 30 of the GAC supplemented) 
21.1Establishment of works executed 
Before the 30th of each month, the Contractor and the Project Manager shall jointly establish a job cost sheet which summarises and fixes the quantities executed and established for each item on the schedule during the month and capable of giving entitlement to payment.

21.2Monthly detailed account 
No later than the fifth (5th) of the month following the month of the services, the Contractor shall hand over to the Project Manager two draft provisional monthly detailed accounts in seven copies (one detailed account exclusive of VAT and the other inclusive of taxes), according to the agreed model and establishing the total amount of the sums to which he may lay claim as a result of the execution of the Contract since the start of the Contract.

Only the detailed account exclusive of VAT shall be paid to the Contractor. The detailed account of the amount of the taxes shall be the subject of an entry into the budgets of the Ministry in charge of Finance Only the amount exclusive of VAT shall be paid to the Contractor as follows: 
	-	100-2.2 or 5.5% paid directly into the account of the Contractor; 
	-	2.2 Or 5.5 % paid to the Public treasury as AIR due by the Contractor.

The amount of payment on account shall not exceed the value of the technical execution phases carried out. Payment on account may be spread over the duration of the execution of the Contract according to technical execution phases as defined in the Contract.

Payment on account shall take place within thirty (30) days from the date of transmission to the competent accounting officer, of the documents giving entitlement to payment.

The contractor shall transmit seven (7) copies of the partial invoices to the Engineer for approval before the 5th of the month following the works executed.

The Engineer shall within a time-limit of seven (7) days forward the approved partial invoices to the Chief of Service.

The Chief of Service has a maximum time-limit of twenty-one (21) days to sign the partial invoice and to produce the documents giving entitlement to payment on account and transmit same to the competent accounting officer.

21.3Detailed account of start-off account (specify).

44

Article 22: Interest on overdue payments (Article 31 of the GAC) 
Possible interests on overdue payments are paid by statement of sums due in accordance with Decree No. 2018/366 of 20 June 2018 to institute the Public Contracts Code.

Article 23: Penalties (Article 32 of the GAC supplemented)

A.Penalties for delay

23.1 The amount set for penalties for delays shall be set as follows:

a)One two thousandth (1/2000th) of the initial Contract amount all taxes inclusive per calendar day 	of delay from the first to the 30th day beyond the Contractual time-limit;

b)One thousandth (1/1000th) of the initial amount of the Contract inclusive of all taxes per calendar 	day beyond the 30th day.

| 23.2 | The cumulated amounts of penalties for delay shall be limited to ten percent (10 %) of the initial Contract inclusive of all taxes. |
| --- | --- |

B.Specific penalties

| 23.3 | Independently of penalties for overrun of Contractual time-limit, the Contractor shall be liable for the following special penalties for the non-observation of the provisions of the Contract, especially: |
| --- | --- |

-Late submission of final bond; 
-Late submission of insurances, shall be one five thousandth (1/5000th) of the initial Contract 	amount all taxes inclusive per calendar day of delay from the first to the 30th day beyond the 	Contractual time-limit; 
-Late submission of the draft execution schedule if the lateness is caused by the Contractor shall be 	one five thousandth (1/5000th) of the initial Contract amount all taxes inclusive per calendar day 	of delay from the first to the 30th day beyond the Contractual time-limit;

Article 24: Payment in case of a group of enterprises (article 33 of the GAC)

1.In the case of a group of enterprises, indicate the method of payment of co- and sub-Contractors, 	where need be.

2.Indicate the method of payment of sub-Contractors, where need be.

Article 25: Final detailed account (article 34 of the GAC) 
25.1 	After completion of the works and within a maximum time-limit of fourteen (14) days after the date 	of provisional acceptance, the Contractor shall establish, based on joint reports, the draft final detailed 	account of works executed and which detailed account summarises the total sums to which the 	Contractor may be entitled as a result of the execution of the whole Contract.

25.2	 The Contract Engineer has up to thirty (30) days to notify the corrected and approved draft to the

Project owner.

25.3 	The Contractor has up to thirty (30) days to return the corrected and approved final detailed account

to the competent accounting officer.

Article 26: General and final detailed account (article 35 of the GAC) 
26.1The Contract Manager or the Project Manager has up to thirty (30) days to establish the general

detailed account and forward to the Contractor after final acceptance.

At the end of the guarantee period which results in the final acceptance of the works, the Authorising Officer draws up the general and final detailed accounts of the Contract which he had signed jointly by the Contractor and the Contracting Authority. This detailed account includes: 
	-	the final detailed account, 
	-	the balance 
	-	the summary of monthly payments on account.

The signing of the general and final detailed account without reservation by the Contractor definitely binds the two parties, puts an end to the Contract, except with regard to interest on overdue payments.

26.2TheContractor has up to thirty (30) days to return the signed final detailed account.

45

Article 27: Tax and customs regulations (article 36 of the GAC) 
Decree No. 2003/651/PM of 16 April 2003 lays down the Terms and Conditions for Implementing the Tax regulations and Customs Procedures applicable to Public Contracts. The taxes applicable to this Contract include notably: 
-	Taxes and dues relating to industrial and commercial profits, including the IAR which is a deduction on 	company taxes; 
-
	Registration dues in accordance with the Tax Code; -	Dues and taxes attached to the execution of services provided for in the Contract; 
		oDuties and taxes of entry into Cameroonian territory (customs duties, VAT, computer tax); 		oCouncil dues and taxes; 
		oDues and taxes relating to the extraction of building materials and water.

These elements must be included in the costs which the undertaking imputes on its running costs and constitute one of the elements of the sub-details of prices exclusive of taxes. 
All taxes inclusive prices means VAT included.

Article 28: Stamp duty and registration of Contracts (article 37 of GAC) 
Seven (7) original copies of the Contract shall be stamped by and at the cost of the Contractor, in accordance with the applicable regulations.

CHAPTER III: EXECUTION OF WORKS

Article 29: Nature of the works (article 46 of GAC) 
The works shall include especially: (position or volume of works) (cf. Special Technical Conditions)

Article 30: Roles and responsibilities of the Project Owner (GAC supplemented) 
30.1 The Project Owner shall be bound to furnish the Contractor with information necessary for the execution of his mission and to guarantee, at the cost of the Contractor, access to sites of projects.

30.2 The Project Owner shall ensure the Contractor of protection against threats, insults, violence, assault and battery, slander or defamation of which he could be victim by reason of or during the exercise of his mission.

Article 31: Execution time-limit of the Contract (article 38 of the GAC) 
31.1 The time-limit for the execution of the works forming the subject of this Contract shall be Four (04) Months.

31.2   This time-limit shall run from the date of notification of the Administrative Order to commence execution of the works.

Article 32: Roles and responsibilities of the Contractor (article 40 of the CAG) 
The detailed and general plan of progress of the works shall be communicated to the Contract Engineer in five (05) copies at the beginning of each.

Article 33: Provision of documents and site (article 42 of the GAC) 
A reproducible copy of the plans featuring in the Tender File shall be submitted by the Contract Engineer. The Project Owner shall make available the site and access ways to the Contractor at the appropriate time as the works progress.

Article 34: Insurance of structures and civil liabilities (article 45 of GAC) 
The Contractor shall take out a third party risk insurance concerning persons, property or liabilities from an insurance company governed by the “CIMA” insurance code.

Article 35: Documentsto be furnished by the Contractor (Article 49 of the GAC supplemented) 35.1Programme of works, Quality Assurance Plan and pegging map.

a)Within a maximum deadline of fifteen (15) days from the date of notification of the Administrative Order to commence execution, the Contractor shall submit in six (6) copies for the approval of project owner

46

after the endorsement of the Contact Engineer the execution programme of the works, his supply calendar, his draft Quality Assurance Plan and the Environment Management Plan, where applicable and the electricity network pegging map at scale 1/2500.

This programme shall be exclusively presented according to the furnished models.

Two (2) copies of these documents will be returned to him within a deadline of fifteen (15) days from the date of reception with: 
	-	Either the indication “GOOD FOR EXECUTION”; 
	-	Or the indication of their rejection including the reasons for the said rejection.

The Contractor has eight (8) days to present a new draft. The Contract Manager or the Project Manager then has a deadline of five (5) days to give his approval or possibly make comments. Delay in approving the draft execution schedule shall stay the execution deadline.

The approval given by the Project Owner does not in any way release the Contractor of his responsibilities. Meanwhile, works executed before the approval of the programme shall neither be ascertained nor paid for. The updated and approved schedule will become the Contractual schedule.

The Contractor shall constantly update on site, a schedule that will take account of real progress of the site. Significant modifications may only be made on the Contractual programme upon receiving the approval of the Project engineer. After approval of the execution schedule by the Contract Manager, the latter shall transmit it within five (5) days to the Contracting Authority without staying its execution. However, if important modifications alter the objective of the Contract or the nature of the works, the Contracting Authority shall return the execution schedule accompanied by reservations to be lifted within fifteen (15) days of the date of reception.

a)The Environment Management Plan should bring out notably the choice technical conditions of the site and basic life, conditions of the backfill of the extraction sites and conditions for reinstating the works and installation sites.

b)The Contractor shall indicate in this schedule the equipment and methods which he intends to use as 	well as the personnel he intends to employ.

c)The approval granted by the Contract Engineer shall in no way diminish the responsibility of the Contractor with regard to the harmful consequences which their implementation may cause both towards third parties and the respect of clauses of the Contract.

35.2 Execution draft 
	a) The execution plan documents (calculations and drawings) necessary for the realisation of all the parts of the structure must be submitted for the endorsement of the Contract Engineer at most fifteen (15) days prior to the date provided for the commencement of execution of the corresponding part of the structure.

b)The Contract Engineer has a deadline of five (05) days to examine and make known his observations.

The Contractor then has a deadline of (04) four days to present a new file including the said observations.

35.3   In case of the non-observance of the approval deadlines of the above documents by the Administration, these documents shall be deemed to have been approved.

Article 36: Organisation and safety of sites (article 50 of the GAC) 
36.1 Signboards at the beginning and end of each section must be placed within a maximum deadline of fifteen days after the notification of the Administrative Order to commence work. It must have the following characteristics: Height = 2.80m, width=1.20m, board thickness=2.5cm at 1.20m above the ground level. The Contract Engineer shall put at the Contractors’ disposal the text to be used.

36.2 The services to inform in case of interruption of traffic or along the deviated itinerary: [To be specified

in accordance with article 50(2) of the GAC].

36.3 Indicate the special measures demanded of the Contractor, other than those provided for in the GAC, for rules of hygiene and safety and for circulation around or in the site.

Article 37: Implantation of structures 
The Project Owner shall notify within [five] days following the date of notification of the Administrative Order to commence work, the basic points and levels of the project.

47

Article 38: Sub-Contracting (article 54 of the GAC) 
The part of the works to be sub-Contracted shall not exceed 30 % of the initial amount of the Contract and its additional clauses.

Article 39: Site laboratory and trials (article 55 of GAC) 
39.1Indicate if necessary the modalities for carrying out the trials and geotechnical studies provided for in the Special Technical Conditions.

39.2The Contract Manager has a deadline of three days to approve the Contractor’s personnel and laboratory as soon as the request is made.

Article 40: Site logbook (article 56 of the GAC supplemented) 
40.1 The Site logbook must be systematically jointly signed by the Project Manager or Engineer, where need be and the Contractor’s representative each day.

40.2 It is a joint document in a single copy. Its pages must be numbered and initialled. No page should be removed. The erased or cancelled parts must be mentioned on the margin for validation.

Article 41: Use of explosives (article 60 of the GAC) (specify)

CHAPTER IV : ACCEPTANCE

Article 42: PROVISIONAL ACCEPTANCE

42.1 PRE-ACCEPTANCE OPERATIONS 
	Before the acceptance of the works the Contractor shall ask in writing to the Contract Engineer, to organize a technical visit for pre-acceptance. This visit shall include the following operations.

Qualitative and quantitative evaluations of the different works that have been executed. Findings and statement of the unexecuted task envisaged in the present contract.

Findings relative to the completion of the work 
Findings on the quantity of works that have been effectively realized

These operations shall be subject to a site report drawn up on the field, signed by the following.

-Contract Engineer; 
- The Contract Manager 
- RD/MINMAP/NW (Observer); 
- The Principal of the concerned school; 
- Contractor.

During this pre-reception, the Engineer shall eventually specify the reserves to be lifted and the corresponding works to be effected before the reception. The Engineer shall fix the reception date in collaboration with the Contract Manager.

42.2 Acceptance The acceptance commission shall comprise: 1-The President of the North West Regional Assembly or his representative ………………(Chairman) 2-The Contract Manager or his representative…..…….......................................................… (Member) 3-The Contract Engineer......................................................................................................... (Secretary) 4-The Stores Accountant of North West Regional Assembly................................................. (Member) 5-The RD MINMAP/NW or his representative…..………………………………..…..…… (Observer) 6-The Beneficiary ……………………. ……………………………….…………………… (Observer) 7-The Commissioner for Education, Sports and Cultural Development at the North West Regional Assemby ……………………………………………………………………………(Observer) 8-The Contractor or his Representative...............................................................................… (Observer) The commission shall examine the report of the pre-acceptance including a video from the Contractor showing the stages of works executed. This shall proceed with the acceptance. An acceptance report (process - verbal) of the works shall be prepared by the Contract Engineer and signed by at least 2/3 of the commission members.

48

ARTICLE 43: DOCUMENTS TO BE FURNISHED AFTER EXECUTION 
43.1 	The contractor shall furnish within one (1) month after completion of the works five (5) copies of all working documents and drawings as executed, especially those relevant to the exploitation and maintenance of the works.

43.2 	A penalty of 30% of the guarantee retention shall be retained in the event where the contractor fails to comply with Article 43.1 above.

Article 44: GUARANTEE PERIOD.

The guarantee period is one (01) year from the date of the provisional acceptance.

Article 45: Final acceptance (article 72 of the GAC) 
Final acceptance shall take place within a maximum deadline of fifteen (15) days from the date of expiry of the guarantee.

The procedure for final acceptance shall be the same as for provisional acceptance

CHAPTER V: SUNDRY PROVISIONS

Article 46: Termination of the Contract (article 74 of the GAC) 
The Contract may be terminated as provided for in Decree No. 2018/366 of 20 June 2018 and equally under the conditions laid down in articles 74, 75 and 76 of the GAC especially in one of the following cases: 	-	Delay of more than fifteen (15) calendar days in the execution of an Administrative Order or 		unjustified stoppage of more than seven (7) calendar days; 
	-	Delay in work resulting in penalties of more than 10 % of the amount of the works; 
	-	Refusal to repeat poorly executed works; 
	-	Default by the Contractor; 
	-	Persistent non-payment for services.

Article 47: Case of force majeure (article 75 of the GAC) 
If the Contractor were to raise the issue of force majeure, the thresholds below which claims shall not be admitted are: 
	-	Rainfall: 200 millimetres in 24 hours; 
	-	Wind: 40 metres per second; 
	-	Flood: decennial flood frequency.

Article 48: Disagreements and disputes (article 79 of the GAC) 
Disagreements and disputes resulting from the execution of this Contract may be settled amicably. Where no amicable solution can be found for a disagreement, it is brought before the competent court in the

North-West Region of the Republic of Cameroon.

Article 49: Production and dissemination of this Contract 
Twenty (20)] copies of this Contract shall be produced at the cost of the Contractor and furnished to the Contract Manager.

Article 50 and last: Entry into force of the Contract 
This Contract shall be final only upon its signature by the Contracting Authority. It shall enter into force as soon as it is notified to the Contractor by the Contracting Authority.

49

Document No. 5

SPECIAL TECHNICAL CONDITIONS (STC)

50

TECHNICAL SPECIFICATIONS

SUMMARY (STC/CCTP)

For the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots

Works to be done consists of

100 : PRELIMINARY WORKS 
200: FOUNDATION 
300 : GROUND FLOOR ELEVATION 
400 : GROUND FLOOR DECKING 
500 : RAMP 
600 : FIRSTFLOOR ELEVAION 
700 : ROOFING 
800 : CARPENTRY AND WOOD WORKS 
900 : ALLUMINIUM AND METALLIC WORK 
1000: PLUMBING 
 1100: ELECTRICITY AND FIRE PROTECTION 
 1200: RETAINING WALL 
 1300: FINISHING 
 1400: LANDSCAPING AND TREE PLANTING

DESCRIPTIVE NOTES FOR THE CONSTRUCTION OF WORKSHOPS IN SOME 
GOVERNMENT TECHNICAL HIGH SCHOOLS OF THE NORTH WEST REGION DIVIDED INTO TWO (02) LOTS

TECHNICAL SPECIFICATIONS

GENERALITIES

GTHS Mesaje:

These descriptive notes and technical specifications are drawn up for the purpose of Construction of a

workshop to horst Building Construction, Public Works, Tilling and Plumbing practical’s in GTHS

Misaje, Donga Mantung Division of the North West Region of Cameroon. This handbook is for those to

execute, supervise and the authorising officer, to direct and guide them towards quality choice of materials,

method of job execution and conditions of   realization in order to achieve the highly desired goal. Building

materials to be used are those that are generally permitted in the construction industry in Cameroon and only

qualified technicians must be employed to transform same into the structure clearly shown on the working

drawings. The structural, functional and aesthetical value of these buildings depends very much on the

professional manipulation of chosen personnel’s and materials.

51

The contractor or builders charged with the execution of this project must carefully study the working

documents, visit the site and bring up points not understood to the Architect or the control Engineer or the

site supervisor (as may be necessary) for clarification before making shop drawings and implementation at

all stages of the realization of this project.

The contractor shall proceed with a careful study of the project, and as the need arises, make observations

and suggestions; and receive feedback from the Architect before continuing with work. All supplementary

tasks must be verified and signed by the supervisor after obtaining the consent of the Architect on the

technical aspects and the Project owner if such tasks have financial incidence on the total cost of the project.

Careful structural studies must be done to determine characteristics of the soil, hence the depth and type of

foundation necessary to safely bear and transmit both the dead and live loads of buildings.

PRELIMINARY WORKS

Building Site Installations

The contractor shall clear the site of all debris and set up temporary structures and facilities needed to execute the works, such as: 
	-	Offices of the Contractor equipped with   tables, chairs and lock-up

cupboards.

-	Building site toilet facility (as necessary)

-	Storage for building materials, etc.

Connection to Utility Networks

Water : 
Connect to the CDE water supply network, where possible, or any other solution acceptable to the supervisor, if the CDE network is not available. The Contractor shall be responsible for the constant supply of sufficient water to the project site. He shall not, under any circumstance, use the excuse that those supplying him with water or that CDE have failed in their assignment to justify delays in the execution of the contract. The water used must be of an acceptable quality for the works, especially from other sources available.

Sanitation

The contractor shall ensure the availability and use of toilet facilities at the work site for his workers and those providing ancillary services on the site.

WORKS TO BE EXECUTED

Earth Works

Demolition, clearance of debris and trench excavation works shall be done manually and /or mechanically with due care taken not to cause damage to adjoining property.  Trenches large enough for workers to operate in shall be dug to receive pad foundation and appropriately located footings for pillars which shall be linked by ground beams. These operations shall be done under the close supervision of the control Engineer. The foundation width and depth will be done strictly to the detailed structural drawings and calculation table specifically prepared for that purpose.

Blinding Concrete.

A 5cm thick lean concrete mix of 150kg/m3 (cpj 42.5) shall be laid under

52

pad foundations and pillar footings.

Mass Concrete

The ground floors and outdoor pavements of this building   shall be of mass

concrete dosed at 300kg/m3 in conformity with the rules and regulations regarding pavements, and with

finishes as required by the design.

Reinforced concrete

The skeleton (framework) of   this building consists of R.C beams and pillars, which must be cast in-situ and in accordance with the rules of CP 110 and batching done according to trial batches or Dreux method, by weight and or volume, closely supervised by the Engineer in charge.  Mixing, transportation, placing and vibration of all concrete works shall be done manually and or mechanically. Reinforced concrete for pillars, beams, lintels, ribs to upper floors, and the ring beam shall be dosed at 350kg/m3.

Based on the structural analysis to be done by a qualified structural Engineer, the magnitude of the dead and live loads shall be determined to permit a safe structural design of the buildings.

The ground floors shall receive 10cm thick mass concrete dosed at 300kg/m3, laid on a layer of hardcore the thickness of which shall be determined and approved by the control Engineer.

The coarse aggregates shall be of class 15/25 and   free from organic impurities and   any substances that may adversely affect the strength and workability of the concrete. Cast concrete shall be cured as required by the art to permit it achieve maximum strength.

Reception for Reinforcements

Before concrete is cast, the Contractor must inform the supervisor that work has been completed in the

assembling of reinforcements so that they can be approved. The Control Engineer shall indicate “Good for concreting” on the building site log, after reception, thereby authorizing the Contractor to proceed.

Formwork

All foundation concrete structures shall be made inside ordinary concrete forms, unless otherwise specified by the supervisor and should meet the following requirements: 
	a)If the concrete box is made with timber that has simply been assembled, the boards must be of

the same level and properly jointed. The maximum space between the joints should be 2 mm.

The maximum difference in level between two jointed planks should be 3 mm.

b)If the ordinary form is made with fibreboard or plywood, the sides must be properly jointed

and be at the same level. The tolerated space between joints should be same as those between

sawn timbers.

c)Formwork for Reservations or recasses

Recesses intended for masonry fittings or other uses should be made using appropriate forms. Such forms should be put together in such a way that their parts can be removed without damage to the  structure.

Pre-casting Preparations

a)Cleanliness of forms

The form must be free from hydrocarbon products such as grease, etc or rust. If there are any stains, these must be thoroughly cleaned up.

b)Cleaning

Before concreting, the concrete boxes must be carefully cleaned to remove all dust and debris. Compressed air should be used to finish the cleaning.

c)Watering

Timber forms must be sufficiently watered before concreting. They should be watered several times to make the wood as wet as possible, causing it to swell and close any gaps in the joint.

53

The wet surfaces must not, however, be dripping with water. Excess water shall be blown out using compressed air.

d)Coating with oil

The following shall be oiled before concreting: 
-Worked moulds of plywood or fibreboard and all moulds for fine dressing

-Excess oil in the moulds must be drained before concreting. The oils used should be special

stripping oils.

-The oil used must not touch the reinforcement rods.

Maintenance

If the moulds   are to be used more than once they should be properly cleaned, and if necessary, repaired before reuse.

Safety of Workers and Others on site

Nails and bolts should immediately be removed from used forms if they are to be used again. Otherwise, the forms should be burnt immediately or stored at a distance from the building site, in a place that is not accessible to the public. Stability/firmness of formwork should be assured.

Constituent Materials of Reinforced Concrete

Crushed Aggregate

All crushed aggregate on the building site should be stored in the compartments intended for this purpose. The only aggregates authorized on the building site are the following:

Crushed 0/5 gravel (river sand)

Crushed 5/15 fine gravel

Crushed 15/25 coarse gravel

Natural or crushed sand 0/5 (the quantity retained on a 5 mm sieve must be less than 10 %.

Crushed aggregate supplied to the site shall be subject to prior approval of the supervisor. The latter must approve the origin of the aggregate. The aggregate should come from rivers, quarries or crushed stable igneous rocks, free impurities, organic matter, dust, mud and clay; and should not stick to grip.

With respect to particle distribution, the following shall apply:

Sand (Fine Aggregate)

Sand shall have the characteristics specified in the tables of approved tests. Sand must be fine, clean, hard, and sharp and must not stick to the hand. It must be free of any soil or limestone, clay, debris and organic particles.

It should (if need be) be sieved and washed. The sand must come from approved quarries or from rivers. It must not contain more than 5% weight of grit passing through a sieve with 900 meshes per cm2 and must not contain particles, whose biggest dimensions exceed the following limits: For mortar      0/2 mm

For reinforced concrete    0/5 mm

For mass concrete    10/5 mm



Cleanliness: The sand must have sand equivalent (SE) higher than 75.

Cement 
Cement shall be true Portland of standard brand and manufacture, i.e. CPA 45 or CPJ 35 type or equivalent.

The cement used should be artificial Portland cement 215.325 P.15.302 Standard. It should be supplied to the building site in six ply paper bags. Any humid cement shall be rejected and immediately removed from the building site.

54

The Contractor must inform the supervisor that he has received his supplies for immediate inspection and approval.

Random samples could be taken from each lot and tested in an approved laboratory using the AFNOR P.15.301 Standard, at the contractor’s expense.

Those that do not meet the standards must be removed from the stock and taken away from the building site.

The bags must be in good shape, at the time they reach the site, and should be stored in a covered and completely dry place, and on a raised plank surface that is at least 20 cm above the ground.

Reinforcements

All reinforcing bars or mesh must comply with BAEL 91 specifications. Iron rods must have French AFNOR 35.001 standard characteristics or similar. All reinforcing bars used in the building project must be of the Fe E240 grade for smooth bars and the Fe E400 grade for high bond rods. The rods must be cut with shears.

The rod should be bent cold, either manually or mechanically. Hot bending may be allowed for high adhesive rods of a diameter equal to or larger than 32 mm, on condition that a control apparatus is used to avoid overheating, and upon the approval of the Control Engineer.

The diameter of the tube benders used for bending must comply with BAEL 91 rules and approval records. Anchor tabs shall be normal 45-degree elbows at right angle or double knee anchoring. The metal used shall be clean and free from calamine. Bars with defects such as blisters, cracks or hairlines that can affect tensile strength shall be rejected.

Concrete reinforcements shall be assembled to the exact dimensions indicated in the drawings provided by the structural Engineer or the Contractor.

Reinforcements must be assembled in the workshop at the building site. They should never be assembled inside the form box if the check boards have already been put in place.

The space between the walls of the formwork and reinforcements should be at least 2.3 cm for elevation concrete and 4 cm for foundation concrete. These spaces should be obtained using prefabricated concrete or plastic shims or spacers, whose dimension should match the results to be obtained.

The concrete shims should have wires to be used in tying them to the reinforcements. There should be enough shims and mounting bars to prevent the reinforcements from being deformed during handling and concreting.

If there are any doubts as to the quality of the iron rods supplied to the project site, the control Engineer or site supervisor shall request for tensile strength tests on the samples taken from the batch. Such tests shall be done at the contractor’s expense. The tests shall be carried out by a competent and approved body. For floor ribs, all measures shall be taken to keep the bars raised and properly positioned around the supports. Enough vertical stirrups should be used to prevent any deformation. All overlaps should comply with BAEL 91 prescriptions.

Frames with traces of non-adhesive rust should be thoroughly brushed off before being placed in the forms.

The reinforcing bars, whether assembled or not, should be stored on boards and not on bare ground. The iron rods used must be supplied by a reputable and approved manufacturer with guaranteed and stamped production quality. The 6 mm diameter iron rods could be used for circles with diameters of 200: Ø. The iron rods supplied must be at least 11 m long.

Placing concrete 
The concrete should be placed before its initial setting time, and never after it has contained its water content for more than thirty minutes; storing it in containers for subsequent use after adding water is strictly prohibited. All concrete pouring shall be accompanied by thorough vibration using a mechanical (hand) vibrator.

All reinforcing bars shall be placed in such a way that concrete can be poured from the top of the structure in question. The Contractor shall take all measures to trim and position the reinforcing bars to prevent them from being jabbed or displaced during concreting. He should also add braces (sleeves, tubes, pipes, angle blocks, pre-frames, etc) to keep the structures firmly set up.

55

Concrete should be transported from the place where it is mixed to the place of use in concrete buckets, wheelbarrows

or head pans.

Before concreting construction joints, the surface of the old concrete must be thoroughly cleaned of any particles using compressed air, and repeatedly to reveal gravels, thus eliminating deposits of dirt; this surface should then be washed and scrubbed with an iron brush and thoroughly soaked. If necessary, admixtures for

construction joints can be used, but these must comply with producers’ instructions.

The formwork should never be removed earlier than 21 to 28 days, time to allow the concrete acquired its maximum strength.

MASONRY

The foundation walls shall be done either in igneous (black stones) rocks either shaped or not as the need may be or hollow sandcrete foundation blocks of 20x20x40cm filled with concrete mixed at 150kg/m3 using cement mortar dosed at 350/m3. The walls shall be erected with hollow sandcrete blocks of 15x20x40cm as shown on the working drawings using cement mortar dosed at 350/m3.

PLASTERING

The bearing surface shall be cleaned, free from any trace of dust or products resulting from the removal of the formwork. Two base coats of plaster, respectively 1.5cm thick and a finished coat of 0.5cm thick shall be applied on the walls using cement mortar dosed at 400kg/m3.

CARPENTRY AND JOINERY

Timber shall be obtained locally. It shall be well seasoned to at most 20% moisture content and shall be free from shakes, defects, insect attacks and dry rot. All door frames shall be made with hardwood. Roofing timber shall be recommended sections of mature eucalyptus well sawn and trimmed to sizes.

OPENINGS

Metallic Openings

All the doors and windows shall be of high quality glass and metal (aluminium) properly finished and in conformity with the dimensions on the working drawings especially in the offices. They shall be the subject of approval of the control Engineer on the site before fitting is carried out.

PAINTING

The   contractor must carefully examine the surface to be painted before work starts.  The external wall

surfaces shall be done in advancing hues while the internal surfaces shall be done in receding hues. Color

pigments, lighting systems and their intensities shall be chosen such as to enhance the illumination of the

spaces. The first or primary coat shall be done in weak glue (white wash) and shall be applied to receive the

final or finishing coat.

Internal   surface shall be done in pantex type 800 whereas pantex 1300 shall be used on external walls.

Paints shall be in water and oil base for walls, ceilings, frames etc.

Metallic surfaces shall be carefully brushed and washed before applying oil paint.

ROOF COVERING

All the timber for the roof truss shall be mature wellseasoned eucalyptus, and shall be of straight grains,

without defects and treated against insects attack with carbonyl. Most of the roof truss shall be triangular. The

rafters shall be of 2”x6” (5x15cm) and the purlins2”x4” (5x8cm.)  Oblique, horizontal and vertical wind braces

shall be done to secure the truss from possible up heave due to wind pressures. The roof shall be tied to the

building by diameter 6mm extended reinforcement bars. The roof slope, fall direction etc. is chosen in

accordance with the manufacturers (AUBAC) specification, atmospheric conditions aesthetic and longevity. The

56

sheathing shall be 6/10 semi-circular corrugated three (3) m long aluminium sheets. They shall be screwed or

nailed to the purlins by carefully chosen qualified and skillful technicians under the close supervision of the

Architect. The fascia boards shall be of metal sheets with a finish hue to be determined by the Architect in close

collaboration with the client.

CEILING

The ceiling shall be executed with 4mm hard (red) plywood fixed on solidly nailed preserved noggins and painted as mentioned above.

ELECTRICITY

| - - - - | Cable sleeves: They shall consist of orange insulation tubes, diameter of 16mm embedded into the block work. Cable: They shall be of 2.5 mm2 (of type TH ) single shall be run inside 11mm plastic coNWAit pipes for power outlets and switches that shall be embedded in walls. As a general rule, the following sections shall be taken, that is, 1.5 mm² for lighting circuits and 2.5 mm² for outlet circuits. Lighting equipment: It will consist of) fluorescent lamps of 1.20m or modern energy saving light bulbs, fitted inside each of the business, living or circulation spaces and at the rear ends of the buildings to act as security lamps. Model of good lamps shall be Philip, Mazda, Turbo, etc. Switches: A two way two gang fuse box has to be provided at the supply inlet for connection to the necessary network. A master’s switch shall be put above the main black board to control the sockets. The two building shall be separately and properly earthed. |
| --- | --- |

NB:Generally, electrical installations should be carried out in conformity with the rules and regulations of ENEO

Mitigating the risks on the environment

These standard clauses constitute the Environmental Regulations relating to the construction works to be carried out in the realization of this project.

The contractor selected to execute the works shall have to implement not only measures aimed at mitigating the socio-environmental impacts of the projects but also environmental and social clauses outlined below. It should be stressed that these clauses apply to all types of projects, the main contractor as well as all sub-contractors or dealers.

These measures include: 
-  A reduction in the raising of dust particles at the work site in order to protect the health of the 	beneficiary population and site workers, by regular watering of the site, or the adoption of an appropriate 	calendar; 
-  AReduction in sound (noise) effects due to the movements of the equipment and machines within the 	construction site; 
-  Non obstruction of the existing natural drainage ways, or the deposit of waste in the stream channels; -  Putting in place of a management plan for oils, fuel, lubricants and other dangerous products during 	construction and running of the project. This plan will have to include the recuperation of the above 	mentioned products and their transfer to specialized companies for treatment; 
-  Automatic stop of works in the event of discovery of an archaeological or historical artefact, and to 	report immediately to the local services of the Ministry of Culture; 
-	Prohibition to transport or drive out game, hunting  and non timber forest products by the personnel

working on  the site;

-  Put at the disposal of the personnel working on the site adequate equipment for potable water and use of 	domestic water; 
-  Priority for recruitment of local labour, as well as the use of local materials;

57

-  Putting  of warningSigns ( sign boards) at building site during and after work; putting speed limits 	warning signs as well in order to promote the safety and health of the resident population and of site 	workers; 
-  The wearing of appropriate equipment & attire (e.g work clothes) by site workers.

-  Restoring (putting back to its original nature) gradually the installations on building site at the end of 	works; 
-   Organizing information and sensitization campaigns for site workers and the beneficiary populations, on 	health risks, risks of accidents, and on the impacts of poaching.

According to the various phases of the work, under the control of contracting authority-The Fon of Lewoh assisted by the local representatives of the MINTP, the provisions here-in will have to be considered or implemented by the contractor.

Starting of works and sensitization of stakeholders

Before the effective start of execution of the works, the company or enterprise must prepare an environmental action plan specifying all the environmental measures to be implemented, as well as rules of procedures mentioning in a specific way the safety requirements and in particular, the wearing of appropriate equipment ( work clothes)  and  speed limit warning signs. Furthermore, these internal rules and regulations will have to prescribe the prohibition of alcohol consumption during working hours, to transport or hunt game, to abusively use wood for fuel, as well as the sensitization of the personnel on the dangers of the STI/SIDA, the respect of the customs and habits of the people of Douala Town. These rules must be pasted at visible locations within the construction site.

On the other hand, an information and sensitization campaign of the personnel and residents will have thus to be organized beforehand and their attention drawn to all these aspects, including the calendar of execution and the employment opportunities. This sensitization campaign will have to continue during the execution phase of the works.

Setting up a building site

a)  Localization 
The importance of setting up a site is determined by the volume and the nature of works to be realized, the number of workmen or labourers, the number and the type of machines. The plan of setting up a building site will have to take into account management and protection measures.

b)  Equipment 
The area for the office and housing for personnel (if necessary) on the site must be equipped with sanitary facilities (latrines, septic tanks, absorbing wells, wash-hand basins and showers) in accordance with the work force. The water tanks (reservoir) shall be installed and the quantity of water must be adequate to the need.  Adequate drainage shall be provided to the installations.

c) Management of solid waste and liquids 
Receptacles (containers) to receive waste are to be installed near the various installations. These receptacles are to be emptied periodically and the waste deposited in a garbage can for recuperation by the Council or in a dump pit.  At the end of work the pit is to be filled (restored) with soil up to the level of the original soil.

Recruitment of the site workers, health and safety

The contractor shall make use (in the most part) of the local labour force except for skilled labour, when not locally available then shall labour be brought from outside of Douala town.

Apart from the training and  information for the personnel on the aspects mentioned above (point 1), the contractor must provide his workmen with the adequate safety equipment, in conformity with the assigned duties – masks to protect against dust particles, anti-noise helmet, safety shoes, boots, gloves, goggles etc. During the works, mobile and fixed signs or notices shall be put installed at strategic locations to ensure the safety of staff and the resident population. The company or enterprise shall carry out routine watering of the site in order to limit air-borne dust particles. He shall also take care to limit the speed of the various vehicles

58

and machines to at most 40 Km/h. In the same way, he shall ensure that all the temporary deviations are identified in collaboration with the resident population, and that they do not affect the sensitive zones.

b) Bringing back the site to initial or original state (Restoration of the site) & withdrawal from the site

At the end of the works, the site shall be restored to its initial or original state. In this regard, installations not necessary thereafter shall have to be taken off the site: 
- The levelling of the site and in particular, the top soil in order to facilitate the infiltration of water, re-planting of grasses and trees as the case may be, 
-  Restoration of the natural flows, 
- Removal of the dilapidated aspects of the site, 
- Filling up (either through re-filling) of pits in order to avoid the erosion of the 
	 degraded soil,  
- Restoration of the pit and recuperation of surface waters and conservation of the slope, etc.

The contractor shall remove all his materials & machines. He is not supposed to abandon any equipment nor materials on the site, or the surroundings, without prior consent of the controller. Restoration of the site includes all the deviations and contours (e.g. foot paths etc) set up during the works.

Management of water Resources

The contractor will have to avoid any conflict which can result from either the use of water resources or damage to the latter.

Compensation for the damages caused to third parties

It can happen that the company hurts an individual in a deliberate or accidental manner (destruction of plants, habitat, etc). If this wrong is not taken into account by the project owner, it shall be absorbed by the contractor to the satisfaction of the injured party.  On the other hand, he shall issue a certificate of compensation to the beneficiary, to avoid any subsequent complaints.

1.12.7    SITE SECURITY 
For the administration of the first medical care in case of any accident on the site, we will have a pharmacy box (first aid) on the site.

The site facilities that are compliant to norms of security will be distributed to workers (like helmets, gloves, boots etc) arrangements will be made to maintain good circulation at all time on the site. All underlying of materials will be kept in places that will help to prevent falling form a height while working. Two guards shall be employed to take guard of the site during and after work hours THUS: 
-To sensitise works on the danger of electricity 
-	Two night watchmen shall be employed to take guard on the site after working hours.

-	A day watch shall be employed to guard the site during working hours.

-	Sign post shall also be prepared and mounted at entrances to indicate that work is underway. They

shall contain information as indicated in the CCT.

We shall do everything possible to ensure that traffic is not obstructed by providing deviations and in places where this is inevitable; we will seek the opinion of the local Authorities for the traffic obstruction or a given period.

1.12.8   SECURITY OF PERSONNEL AND SITE 
PROTECTION OF PERSONNEL: 
Personnel on site shall be protected from accidents through; 	-	Vigorous respect of construction norms on the site

-	The provision of Helmets

-	The provision of steel cap shoes

-	The provision of rain coats

-	The provision of gloves for those doing concreting and metal works

59

| - - - - - | Keeping of underlying materials like off cuts in place Scaffoldings will be well fixed to avoid failing form a height. The provision standby vehicle shall be on site to evacuate workers to a nearby hospital in case of accident Provision of sign post to indicate that work is underway. Educating of workers about the dangers of HIV AIDS and means of prevention. |
| --- | --- |

1.12.9 SANITATION AT SITE 
Our enterprise will put and implement sanitation by improving cleanliness in and around the project site by observing the following.

1.Dig a pit toilet for the workers to be using when at work so that they will not be littering the site and

making it uncomfortable for people as well as well as the neighbourhood.

2.To always have health educational talks with the workers and also teaching them from what they

need to do in order to avoid cholera and other diseases.

3.To connect a good potable water as for the workers to be drinking.

4.To always keep the project site clean and free form standing thirty water that can lead to mosquito

bids

5.Paste notices of warning to those dirtying the site.

All the sanitary measure that this enterprise will do will be of great help to the workers.

TECHNICAL SPECIFICATIONS

SPECIFICATIONS FOR THE CONSTRUCTION OF THE G+1 IT BLOCK

A1. DESCRIPTION OF WORK: the work embodied in this project is the construction of an it centre for GTHS Bamendankwe. The ground floor comprises of one computer hall, an office, a store and a toilet, while the upper floor comprises of computer classrooms,and an office.

The structure is to be constructed on a stone masonry foundation inter-spaced with r.c.

kickers. The walls are of 15cm sundry blocks laid in cement mortar. The roof is to be of wooden trusses covered with 3m corrugated aluminium sheets. The floors are solid concrete floors with a tile finish. A2 . LOCATION OF PROJECT: The project is located at TAHGEH, MANKON as seen on the situation plan.

A3. INSPECTION OF SITE: By submitting a tender, the contractor will be deemed to have inspected the site and its immediate surroundings and to have satisfied himself as to the conditions appertaining thereto.

A4. CONTROL OF WORK: The work shall commence and proceed with the satisfaction of the architect on the level of preparedness, and should it be deemed necessary to suspend the progress of the work, the architect shall be at liberty to direct the inspection and duration thereof. In the same manner, any written variation issued in accordance with the provision of the contract shall be carried out by the inspector.

BEARTH WORK 
B1 EXCAVATION: All trenches and footings shall be excavated to depths as indicated on the plans or to an acceptable bearing stratum as shall be deemed suitable by the architect.

B1 SUPPORT:  All excavations more than 1. 5m shall boarded and sufficiently braced to prevent the sides from collapsing.

CCONCRETE WORKS

60

C1 FORMWORK; All formwork must rest on sole plates placed on well ramped ground to avoid sagging.NB. Any Saggingg floors and beams shall lead to the disqualification of the said piece of work. Formwork to soffits of beams and especially must not be removed before 21 days from the day of concreting.

C2. CEMENT:  All cement used for concreting structural members and ground floor slab shall be cement Dangote 42.5MPa.

C3. AGGREGATES:  the coarse aggregates used shall be of particle size 15/20. The fine aggregates used must not be of high clay contain the sand equivalence must be more than 80%.

C4: DOSAGE: all concrete for structural parts shall be dosed at 350kg/m3 and with 400litres sand and 800litres of gravel per cubic meter for mechanical mixing and 500litres of sand and 700litresof gravel for manual mixing.

C5. MIXING: If mixing is done manually it must be done on a concreted surface or similar.

C6: TRANSPORTATION: the runway for the concrete must not be long or rough 
C7: FORMWORK: The wood used for formwork shall be planed wood or metallic forms and must be dampened before any concrete is poured there in.

C8: HYDRATED CONCRETE AND POURING: The maximum time interval from when concrete gets in contact with water to when it is put in place shall be 15 mins.

C9: VIBRATION: All concrete work shall just be sufficiently as over or under vibration will leave the finished work with combs.

DREINFORCEMENT

D1 DIAMETERS: All reinforcement diameters shall be done as per the structural details and calculations. The r.c pillars at the foundation retaining earth shall be sufficiently reinforced and chained at the top into the building by a beam.

D2 CONCRETE COVER: The minimum concrete cover shall be 2.5cm.

D3 STORAGE: no steel for reinforcements shall be stacked in contact with the ground.

EMASONRY

E1 BATCHES: The dosage for moulding blocks, mixing of mortar and plastering shall be 1part of cement: to 3 parts of sand by volume.

E2 BONDING: the bonds for block and stone work shall be stretcher bonds.

FCARPENTARY AND WOODWORK

F1. WOOD The type of wood used for door and window, frames as well as roofing shall be hard wood. F2. JOINTS: Where nails are used for jointing, it must ensured that the length embedded into the second member is deep enough to hold element together under a shock.

F3. WORKMANSHIP: the expertise of a skilled wood worker shall be required for all wood workers.

GALUMINIUM METALLIC AND GLAZING WORKS

G1MATERIAL: All metal work shall be of the best quality of metals found in the market.

G2 GLAZING: all aluminium glazed windows shall be well embedded into a layer of mastic or putty to ensure perfect water tightness. The glass used on veranda handrails shall be tinted glass.

G3 CORROSION: all welded window protectors and handrails shall receive an anti corrosive coat of paint.

HPLUMBING

| I | H1 Water supply: The types of pipes used for water supply are galvanised pipes of 35mm. each apartment shall have an independent meter to record its consumption. H2 DRAINAGE: the type of pipes used for drainage shall be p.v.c pipes of 8cm diameter. The drainage system shall be as separate as possible. H3 JOINTS: all piping joints shall be air and water tight H3 TESTING: the method of testing shall be as decided upon by the architect. ELECTRIFICATION |
| --- | --- |

61

I 	1CABLES: the diameter of cables used for the supply of appliances shall be industrial cables 4mm

I2 POWER SUPPLY AND VOLTAGE CONTROL: every section of the house shall have its own circuit controllers and fuses to permit maintenance without interference in other apartments

PAINTING 
J1 QUALITY: the quality of paint used here shall be pantex 800. The colour of the finished painted work shall be as decided upon by the architect 
J2 SURFACES: No wet or dusty surfaces shall receive any paint 
J3 COATS: The paint shall be applied in two coats 
J4 WORKMANSHIP: The expertise of a skilled tiles man shall be required.

| J | TILING K1 TYPE: The quality of tiles for floors must be ceramic. No porcelain tiles shall be applied to floors. K2 SIZES : The sizes of tiles for toilet floors shall be 10x10cm while other floors shall receive tiles of 30 x30 cm. |
| --- | --- |

62

Document No. 6

SCHEDULE OF UNIT PRICES

63

UNIT PRICE LIST FOR THE PROJECT

| UNIT PRICE SCHEDULE FOR THE CONSTRUCTION OF A CIVIL ENGINEERING WORKSHOP IN GTHS MISAJE, DONGA MANTUNG DIVISION, NORTH WEST REGION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No | DESCRIPTION | UNIT | QTY | U.P in Figures | U.P. in Words |
|  | LOT100: TRAVAUX PREPARATOIRE-ETUDES |  |  |  |  |
| 101 | Installation du chantier | ff | 1 |  |  |
| 103 | Nettoyage du site | ff | 1 |  |  |
|  | SOUS TOTAL 100 |  |  |  |  |
|  | LOT200: TERRASSEMENT+IMPLANTATION |  |  |  |  |
| 201 | Nivellement de surface | m2 | 650 |  |  |
| 202 | Implantation des ouvrages | m2 | 321 |  |  |
| 203 | Fouilles en puits et en rigoles | m3 | 56 |  |  |
| 204 | Remblai de terre | m3 | 135 |  |  |
|  | SOUS TOTAL 200 |  |  |  |  |
|  | LOT 300: FONDATIONS |  |  |  |  |
| 301 | Fourniture et mise en ouvre du beton de proprete y compris toutes sujetions | m3 | 3.9 |  |  |
| 302 | Fourniture et mise en oeuvre de la maconnerie en agglos de 20*20*40 bourrea y compris toutes sujetions | m2 | 76 |  |  |
| 303 | Fourniture et mise en oeuvre du beton arme pour semelles, chainage, armorces poteau y compris toutes sujetions | m3 | 9 |  |  |
| 304 | Fourniture et mise en oeuvre d'un dallage (ep 8cm) y compris toutes sujetions | m2 | 321 |  |  |
|  | SOUS TOTAL 300 |  |  |  |  |
|  | LOT 400: MACONNERIE - ELEVATION |  |  |  |  |
| 401 | Fourniture et mise en oeuvre de la maconnerie en agglomere creux de 20*20*40 + etancheite a la premiere assise y compris toutes sujetions | m2 | 7.8 |  |  |
| 402 | Fourniture et mise en oeuvre de la maconnerie en agglomere creux de 15*20*40 + etancheite a la premiere assise y compris toutes sujetions | m2 | 350 |  |  |
| 403 | Fourniture et mise en oeuvre de l'enduit au mortier de ciment des murs y compris toutes sujetions | m2 | 715 |  |  |

64

| 404 | Fourniture et mise en oeuvre de beton arme dose a 350kg/m3 pour poteaux, linteaux et chainnage haut y compris toutes sujetions | m3 | 10 |  |  |
| --- | --- | --- | --- | --- | --- |
| 405 | Fourniture et realization du tableau mural y compris toutes sujetions | u | 2 |  |  |
| 406 | Fournitures et mise en oeuvre de la chape lissee sur dallage y compris toutes sujetions | m2 | 130 |  |  |
| 407 | Fourniture et realisation d'une estrade y compris toutes sujetions | u | 1 |  |  |
| 408 | Fourniture et realisation des rampes d'acces pour personnes a mobilite reduite y compris toutes sujetions | u | 2 |  |  |
|  | SOUS TOTAL 400 |  |  |  |  |
|  | LOT 500: CHARPENTE - COUVERTURE |  |  |  |  |
| 501 | Fourniture et assemblage et pose de bois prelablement traite pour fermes doublee y compris toutes sujetions | m3 | 6 |  |  |
| 502 | Fourniture et fixation du bois dur prealablement traites pour pannes et lattes de rive de pignon y compris toutes sujetions | m3 | 3.6 |  |  |
| 503 | Fourniture et realisation du plafond en contre plaque prealablement triate y compris solivage et toutes sujetions | m2 | 130 |  |  |
| 504 | Fourniture et realisation du plafond exterieur en tole lise y compris solivage et toutes sujetions | m2 | 56 |  |  |
| 505 | Fourniture et pose des planches de rive 30 cm y compris et toutes sujetions | ml | 95 |  |  |
| 506 | Fourniture et fixation de tole bac 6/10, des gouttieres et naissances en alu et des descentes en PVC protegees par des caisons en beton arme y compris et toutes sujetions | m2 | 450 |  |  |
| 507 | Fourniture et fixation de tole fatieres de 50cm de larger y compris et toutes sujetions | ml | 27 |  |  |
|  | SOUS TOTAL 500 |  |  |  |  |
|  | LOT 600: MENUISERIE METALLIQUE |  |  |  |  |
| 601 | Fourniture et fixation de portes metallique coulissante de 300x250 cm2 y compris et toutes sujetions | u | 2 |  |  |
| 602 | Fourniture et scellement de grilles antivol (motif barres droites espacees de 8cm) en tube de 30 mm y compris et toutes sujetions | m2 | 50 |  |  |
|  | SOUS TOTAL 600 |  |  |  |  |

65

|  | LOT 700: MENUISERIE BOIS, ALLUMINIUM ET VITRERIE |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 701 | Fourniture et pose des portes en bois isoplane de 100*220cm2 sur cadre en bois dur y compris et toutes sujetions | u | 3 |  |  |
| 702 | Fourniture et pose des portes en bois massif de 180*220cm2 sur cadre en bois dur y compris et toutes sujetions | u | 2 |  |  |
| 703 | Fourniture et pose des portes en bois massif de 100*220cm2 sur cadre en bois dur y compris et toutes sujetions | u | 1 |  |  |
| 704 | Fourniture et pose des fenetres collissantes en aluminium vitree y compris et toutes sujetions | m2 | 3 |  |  |
|  | SOUS TOTAL 700 |  |  |  |  |
|  | LOT 800: ELECTRICITE ET PROTECTION CONTRE L'INCENDI |  |  |  |  |
| 801 | Fourniture et encastrement de gains annelees y compris toutes sujetions | ml | 100 |  |  |
| 802 | Fourniture et pose des gains IRL y compris toutes sujetions | ml | 600 |  |  |
| 803 | Fourniture et installation de cables TH 1,5mm2 y compris toutes sujetions | ml | 700 |  |  |
| 804 | Fourniture et installation de cables TH 2,5mm2 y compris toutes sujetions | ml | 800 |  |  |
| 805 | Fourniture et installation de cables U1000R2V 4mm2 y compris toutes sujetions | ml | 500 |  |  |
| 806 | Fourniture et installation de cables U1000R2V 5/6mm2 y compris toutes sujetions | ml | 300 |  |  |
| 807 | Fourniture et pose de reglettes avec tube fluorescent de 1,20m y compris toutes sujetions | u | 24 |  |  |
| 808 | Fourniture et pose des interupteurs et prises de courant encastre y compris toutes sujetions | u | 10 |  |  |
| 809 | Fourniture et pose des interupteurs et prises de courant apparent y compris toutes sujetions | u | 15 |  |  |
| 810 | Fourniture et installation du cables en cuivre de 29mm2 de section pour la mise a la terres y compris toutes sujetions | u | 1 |  |  |
| 811 | Fourniture et installation du tableau general electrique de commande du circuit des pris avec protection des circuit a l'aide des disjointeurs differentielles et parafoudre | ens | 1 |  |  |
| 812 | Fourniture et installation des attaches, dominos, boitieres, boite de derivation, y compris toutes sujetions avec raccordement au reaseaux existant | ens | 1 |  |  |

66

| 813 | Fourniture et pose d'intincteurs d'iincendie eau + additif 9 litres y compris toutes sujetions | u | 1 |  |  |
| --- | --- | --- | --- | --- | --- |
|  | SOUS TOTAL 800 |  |  |  |  |
|  | LOT 900: PEINTURE |  |  |  |  |
| 901 | Preparation des surfaces | m2 | 715 |  |  |
| 902 | Fourniture et applications de deux couches de peinture acrylique de type pantex 800 pour le plafond y compris toutes sujetions | m2 | 130 |  |  |
| 903 | Fourniture et applications de deux couches de peinture acrylique de type pantex 1300 pour murs exterieurs y compris toutes sujetions | m2 | 275 |  |  |
| 904 | Fourniture et applications de deux couches de peinture acrylique de type pantex 800 pour murs interieurs y compris toutes sujetions | m2 | 440 |  |  |
| 905 | Fourniture et applications de deux couches de peinture glycerophtalique de type email A pour menuiseries bois et metallique y compris toutes sujetions | m2 | 80 |  |  |
|  | SOUS TOTAL 900 |  |  |  |  |
|  | LOT 1000: PLOMBERIE ET REVETEMENT |  |  |  |  |
| 1001 | Fourniture et construction de la fosse septique de capacite 25m3 et les regards de visite y compris toutes sujetions | ens | 1.0 |  |  |
| 1002 | Fourniture et construction du puisard y compris toutes sujetions | u | 1 |  |  |
| 1003 | Fourniture et installation de la tuyauterie d'evacuation des eaux vannes et des euax usees y compris toutes sujetions | ml | 100 |  |  |
| 1004 | Fourniture et installation de la tuyauterie d'alimentation y compris toutes sujetions | ml | 100 |  |  |
| 1005 | Fourniture et pose de WC de marque PARMA y compris toutes sujetions | u | 1 |  |  |
| 1006 | Fourniture et pose de WC pour les personnes a mobilite reduite y compris toutes sujetions | u | 1 |  |  |
| 1007 | Fourniture et pose de lavabo avec console y compris toutes sujetions | u | 1 |  |  |
| 1008 | Fourniture et revetement du sol des toilettes en carreaux gres ceramique antiderapant de 30x30cm2 y compris toutes sujetions | m2 | 7.5 |  |  |
| 1009 | Fourniture et revetement du murs des toilettes en carreaux faience de 20x30cm2 y compris toutes sujetions | m2 | 30 |  |  |
| 1010 | 1010 Fourniture et pose du couler dans l'atelier | u | 2 |  |  |

67

| 1011 | 1011 Fourniture et pose du robinet dans l'atelier | u | 3 |  |  |
| --- | --- | --- | --- | --- | --- |
| 1012 | Fourniture et pose du cintres pour papier toilet dans l'atelier | u | 2 |  |  |
| 1013 | 1013 Fourniture et pose des mirroir | u | 1 |  |  |
| 1014 | Fourniture et installation des acessoires pour raccordements diverses y compris toutes sujetions | Ens | 1 |  |  |
|  | SOUS TOTAL 1000 |  |  |  |  |
|  | LOT 1100: VRD ET AMENAGEMENT EXTERIEUR |  |  |  |  |
| 1101 | Fourniture et construction ds caniveaux en beton arme en forme de U de largeur 40cm, de profondeur minimale de 30cm, des parois d'epaisseur 8cm et de pente minimale de 2% y compris toutes sujetions | ml | 88.0 |  |  |
| 1102 | Fourniture et pose du dallettes de longeur 56cm de largeur 40cm, et d'epaisseur 8cm. | ml | 35 |  |  |
| 1103 | Fourniture et mise en ouvres d'un dallage en beton aux alentours du batiment y compris toutes sujetions | m2 | 84 |  |  |
|  | SOUS TOTAL 1100 |  |  |  |  |

| UNIT PRICE SCHEDULE FOR THE CONSTRUCTION OF A G+1 IT CENTRE FOR GTHS BAMENDANKWE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ITEM | DESIGNATION | UNIT ARY W |  | U.P. in Figures | Unit Price in Words |
|  | 100- PRELIMIN ARY W ORKS |  |  |  |  |
| 101 | Site clearance | m² | 394 |  |  |
| 102 | Hoarding and work posts | ml | 107 |  |  |
| 103 | Levelling (excavation) and provision of access way | m3 | 819 |  |  |
|  | PRELIMINARY WORKS TOTAL | OUN D |  |  |  |
|  | 200- FOUN DATIO N |  |  |  |  |
| 201 | Setting out of foundation | u | 1 |  |  |
| 202 | Excavation of footings | m3 | 30 |  |  |
| 202 | Excavation of trenches | m3 | 83.39 |  |  |
| 203 | Lean concrete of dossage 150kg/m3 | m3 | 1.48 |  |  |
| 204 | R C concrete of 350kg/m3 for Footings 1.3x 1.3 | m3 | 10.65 |  |  |
| 205 | R C concrete of 350kg/m3 pillars | m3 | 1.16 |  |  |
| 206 | R C concrete of 350kg/m3 for Ground beams | m3 | 5.46 |  |  |
| 208 | Block work 20 x 40 filled with plain concrete | m2 | 91 |  |  |
| 209 | Volume of backfill upto 45cm height | m3 | 40 |  |  |
|  | FOUNDATION TOTAL |  |  |  |  |

68

|  | 300-GROUND FLO OR ELEVATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 301 | Masonry ( 15 x 20 x 40 cm Sandcrete blocks ) | m² | 180 |  |  |
| 302 | R C concrete of 350kg/m3 for Pillars, , Lintels | m3 | 5.55 |  |  |
| 303 | R C concrete of 350kg/m3 for half beam | m3 | 5 |  |  |
| 304 | R C concrete gutters around GFL 40 x 40 in to in | m2 | 7.3 |  |  |
|  | GROUND FLOOR ELEVATION TOTAL | OOR D |  |  |  |
|  | 400- GROUND FL OOR DE CKING |  |  |  |  |
| 401 | Decking blocks | m2 | 140 |  |  |
| 402 | R C concrete of 350kg/m3 for Rib-beams | m3 | 5.8 |  |  |
| 403 | R C concrete of 350kg/m3 for Slab | m3 | 7.4 |  |  |
| 404 | R C concrete of 350kg/m3 to complete 1/2beams | m3 | 3.8 |  |  |
| 405 | R C concrete of 350kg/m3 for Stairs | m3 | 1.52 |  |  |
|  | DECKING TOTAL |  |  |  |  |
|  | 500- RA MP |  |  |  |  |
| 502 | R C concrete of 350kg/m3 for Footings and pillars | m3 | 3.5 |  |  |
| 503 | R C concrete of 350kg/m3 for Slab and side beams | m3 | 13.85 |  |  |
| 504 | Wooden props to carry ramp covering | m3 | 0.3 |  |  |
| 505 | Stucco Tiling to ramp floor | m2 | 58 |  |  |
| 505 | Framing and alu tol bac 40 covering | m2 | 60.5 |  |  |
|  | DECKING TOTAL | ELEV |  |  |  |
|  | 600- FIRST FLOOR ELEVATION |  |  |  |  |
| 601 | Block Walls 15 x 20 x 40 | m2 | 190.5 |  |  |
| 602 | Concreting of Pillars 20 x 30 and 20 x 40 | m3 | 4 |  |  |
| 603 | Lintels 15x20 | m3 | 3.8 |  |  |
| 604 | Tie beam internal 15x20 | m3 | 1 |  |  |
| 604 | External tie beam 15x30 | m3 | 2.8 |  |  |
| 604 | Parapet upper and lower beams 15x20 | m3 | 3.6 |  |  |
| 604 | Parapet Block work | m2 | 25 |  |  |
|  | FIRST FLOOR ELEVATION TOTAL | ROO F |  |  |  |
|  | 700- ROO FING |  |  |  |  |
| 701 | Timber for Rafters | m3 | 4.41 |  |  |
| 702 | Timber for Purlins 5cm x5cm | m3 | 0.98 |  |  |
| 704 | Tole bac sheets in alumunium 5/10 (bordeaux) | m2 | 209 |  |  |
| 705 | Hip ridges | ml | 36.86 |  |  |
| 706 | Rain water gutter | ml | 55 |  |  |
| 707 | Down pipes 80mm | ml | 68 |  |  |
| 708 | down pipe funnels | ml | 8 |  |  |
| 709 | 45 o elbows | ml | 16 |  |  |
| 710 | 90 o elbows | ml | 8 |  |  |
| 711 | Nails and other accessories | ls | 1 |  |  |
|  | ROOFING TOTAL | WO |  |  |  |
|  | 800- CARPENTRY AN D WO OD WORK |  |  |  |  |
| 801 | Complete door frames and shutters 90x210 | u | 3 |  |  |

69

| 802 | Complete door frames and panel shutters 70x210 | u | 1 |  |  |
| --- | --- | --- | --- | --- | --- |
|  | CARPENTRY WORK TOTAL | ETA L |  |  |  |
|  | 900- ALUMINIUM AND META LLIC WORK |  |  |  |  |
| 901 | Complete door frames and panel shutters ext doors 100x210 | u | 6 |  |  |
| 902 | Guard rails to blaconies and stairs | ml | 22 |  |  |
| 903 | Provision and fittiing of Aluminium glider windows including glass 1.4 x 1.3 | m2 | 29.5 |  |  |
| 903 | Provision and fittiing of Aluminium glider windows including glass 60 x 60 | m2 | 1.2 |  |  |
| 904 | Provision and fitting of Iron protectors for all windows | m2 | 33.32 |  |  |
|  | ALU/METALLIC WORK TOTAL | UMBI |  |  |  |
|  | 1000- PLUMBING |  |  |  |  |
|  | Piping |  |  |  |  |
| 1001 | Inspection chambers | u | 2 |  |  |
| 1002 | Septic tank & | u | 1 |  |  |
| 1003 | Soakaway pit | u | 1 |  |  |
| 1004 | Water Supply pipes 3/4 inch | ml | 15 |  |  |
| 1005 | Drainage pipes ϕ 100 | ml | 15 |  |  |
| 1006 | Drainage pipes ϕ 60 | ml | 80 |  |  |
| 1007 | 90o elbow ϕ 100 | u | 8 |  |  |
| 1008 | 90o elbow ϕ 60 | u | 8 |  |  |
| 1009 | Gully trap elbow ϕ 100 | u | 1 |  |  |
| 1010 | 90o elbow 3/4 inch | u | 3 |  |  |
| 1011 | T-junction connector 3/4 inch | u | 2 |  |  |
| 1012 | Stopcork valve 3/4 inch | u | 2 |  |  |
|  | Installation |  |  |  |  |
| 1013 | Faucet taps | u | 1 |  |  |
| 1014 | Wash-hand basins | u | 1 |  |  |
|  | PLUMBING TOTAL | C TRI |  |  |  |
|  | 1100- ELEC TRICIT Y |  |  |  |  |
| 1101 | PIPING |  |  |  |  |
| 1102 | Lightening Conductor(22mm) | m | 30 |  |  |
| 1103 | Earth Rod | u | 1 |  |  |
| 1104 | Rubber Plastic Cups for switches and sockets | u | 57 |  |  |
| 1105 | Plastic Junction Boxes 8cm | u | 10 |  |  |
| 1106 | Plastic Junction Boxes 5cm | u | 10 |  |  |
| 1107 | Conduit Pipe 13mm | Roll | 20 |  |  |
| 1108 | Conduit Pipe 16mm | Roll | 10 |  |  |
| 1109 | line seperator box | u | 2 |  |  |
| 1110 | Main switch boxes | u | 1 |  |  |
|  | SUBTOTAL |  |  |  |  |
|  | CABLING & WIRING |  |  |  |  |

70

| 1402 | Provision of treated and planting electric poles to connect power from current administrative block | u | 3 |  |  |
| --- | --- | --- | --- | --- | --- |
| 1112 | Three phase power supply tendons | roll | 3 |  |  |
| 1112 | Industrial Cable for heavy appliances 4mm | Roll | 4 |  |  |
| 1113 | 2.5mm Single Cable -roll | Roll | 2 |  |  |
| 1114 | 1.5mm Single Cable -roll | Roll | 2 |  |  |
| 1115 | Internet cable | Roll | 2 |  |  |
| 1116 | Earth Cable 4mm | Roll | 1 |  |  |
|  | SUBTOTAL |  |  |  |  |
|  | FITTINGS |  |  |  |  |
| 1118 | Energy saving Incandescent (Ø 15cm) High luminar | u | 27 |  |  |
| 1119 | Lamp holders | u | 27 |  |  |
| 1120 | Switches | u | 35 |  |  |
| 1121 | Sockets | u | 18 |  |  |
| 1122 | Installation of cicuit breakers Coupe-circuit selectionable SP 51 3P+N 14 X 51 LEGR | u | 1 |  |  |
| 1123 | Internet Plugs | u | 14 |  |  |
|  | SUBTOTAL |  |  |  |  |
|  | ELECTRICITY TOTAL | G W A |  |  |  |
|  | 1200- RETAIN ING W ALL |  |  |  |  |
| 1201 | Setting out of foundation | u | 1 |  |  |
| 1202 | Excavation of strip footings 60x50 | m3 | 13.8 |  |  |
| 1203 | Lean concrete of dossage 150kg/m3 | m3 | 1.48 |  |  |
| 1204 | Stone strip footing 40 x 60 | m3 | 11.04 |  |  |
| 1205 | R C concrete of 350kg/m3 pillars 20 X 30 interspaced @ 3.5m c/c | m3 | 2 |  |  |
| 1206 | R C concrete of 350kg/m3 for chaining beams at the base on stone base 30 x 30 | m3 | 4.4 |  |  |
| 1207 | Stone masonry retaining wall 30cm x 2.60m high x 46.5ml | m2 | 35.88 |  |  |
| 1208 | R C concrete of 350kg/m3 for middle belt beams 20 x 30 | m3 | 2.76 |  |  |
| 1209 | R C concrete of 350kg/m3 for tie beams 30 x 30 | m3 | 4.4 |  |  |
| 1210 | Volume of backfill upto height | m3 | 36 |  |  |
| 1211 | Provision and planting of metallic of guard rails over retaining wall | ml | 42 |  |  |
| 1211 | Provision of steps 1.5m width between retaining wall to connect to upper existing blocks | m3 | 1.3 |  |  |
|  | RETAINING WALL TOTAL | FINIS |  |  |  |
|  | 1300 - FINISHING |  |  |  |  |
| 1301 | Floor screed to ground floor (8cm) | m3 | 9.95 |  |  |
| 1302 | Plastering to walls | m² | 735 |  |  |
| 1303 | Plastering of the soffit | m² | 130 |  |  |
| 1304 | Dressing of window and door edges and angles | m² | 20.35 |  |  |

71

| 1305 | Framing and plywood 1st floor ceiling | m2 | 140 |  |  |
| --- | --- | --- | --- | --- | --- |
| 1306 | Porcelian vitrified tiles to all floors corridor, halls offices, stairs | m2 | 276 |  |  |
| 1307 | Tilling to toilet floors | m2 | 3.6 |  |  |
| 1308 | Tiles to toilet walls | m2 | 18 |  |  |
| 1309 | White wash to all walls | m² | 735 |  |  |
| 1310 | Painting pantex 800 to all walls (walls yellow + pillars ash gray and ox blood skirting | m² | 735 |  |  |
| 1310 | Painting pantex 800 to ceiling white | m² | 280 |  |  |
| 1311 | Oil paint to iron and wooden doors | ls | 1 |  |  |
|  | FINISHING TOTAL | TR EE | PLANTIN G |  |  |
|  | 1400 - LANDSCAPING A ND TR EE PLANTIN G |  |  |  |  |
| 1401 | Grading of surface to planes for lawn 43 x6 | m2 | 190 |  |  |
| 1402 | Planting of lawn | m² | 190 |  |  |
| 1403 | Planting of trees | u | 30 |  |  |
|  | SUB-TOTAL 1400 |  |  |  |  |

72

Document No. 7

BILL OF QUANTITIES AND ESTIMATES

73

| BILL OF QUANTITIES AND ESTIMATES FOR THE CONSTRUCTION OF A CIVIL ENGINEERING WORKSHOP IN GTHS MISAJE, DONGA MANTUNG DIVISION, NORTH WEST REGION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No | DESCRIPTION | UNIT | QTY | U.P | AMOUNT |
|  | LOT100: TRAVAUX PREPARATOIRE-ETUDES |  |  |  |  |
| 101 | Installation du chantier | ff | 1 |  |  |
| 103 | Nettoyage du site | ff | 1 |  |  |
|  | SOUS TOTAL 100 |  |  |  |  |
|  | LOT200: TERRASSEMENT+IMPLANTATION |  |  |  |  |
| 201 | Nivellement de surface | m2 | 650 |  |  |
| 202 | Implantation des ouvrages | m2 | 321 |  |  |
| 203 | Fouilles en puits et en rigoles | m3 | 56 |  |  |
| 204 | Remblai de terre | m3 | 135 |  |  |
|  | SOUS TOTAL 200 |  |  |  |  |
|  | LOT 300: FONDATIONS |  |  |  |  |
| 301 | Fourniture et mise en ouvre du beton de proprete y compris toutes sujetions | m3 | 3.9 |  |  |
| 302 | Fourniture et mise en oeuvre de la maconnerie en agglos de 20*20*40 bourrea y compris toutes sujetions | m2 | 76 |  |  |
| 303 | Fourniture et mise en oeuvre du beton arme pour semelles, chainage, armorces poteau y compris toutes sujetions | m3 | 9 |  |  |
| 304 | Fourniture et mise en oeuvre d'un dallage (ep 8cm) y compris toutes sujetions | m2 | 321 |  |  |
|  | SOUS TOTAL 300 |  |  |  |  |
|  | LOT 400: MACONNERIE - ELEVATION |  |  |  |  |
| 401 | Fourniture et mise en oeuvre de la maconnerie en agglomere creux de 20*20*40 + etancheite a la premiere assise y compris toutes sujetions | m2 | 7.8 |  |  |
| 402 | Fourniture et mise en oeuvre de la maconnerie en agglomere creux de 15*20*40 + etancheite a la premiere assise y compris toutes sujetions | m2 | 350 |  |  |
| 403 | Fourniture et mise en oeuvre de l'enduit au mortier de ciment des murs y compris toutes sujetions | m2 | 715 |  |  |
| 404 | Fourniture et mise en oeuvre de beton arme dose a 350kg/m3 pour poteaux, linteaux et chainnage haut y compris toutes sujetions | m3 | 10 |  |  |
| 405 | Fourniture et realization du tableau mural y compris toutes sujetions | u | 2 |  |  |

74

| 406 | Fournitures et mise en oeuvre de la chape lissee sur dallage y compris toutes sujetions | m2 | 130 |  |  |
| --- | --- | --- | --- | --- | --- |
| 407 | Fourniture et realisation d'une estrade y compris toutes sujetions | u | 1 |  |  |
| 408 | Fourniture et realisation des rampes d'acces pour personnes a mobilite reduite y compris toutes sujetions | u | 2 |  |  |
|  | SOUS TOTAL 400 |  |  |  |  |
|  | LOT 500: CHARPENTE - COUVERTURE |  |  |  |  |
| 501 | Fourniture et assemblage et pose de bois prelablement traite pour fermes doublee y compris toutes sujetions | m3 | 6 |  |  |
| 502 | Fourniture et fixation du bois dur prealablement traites pour pannes et lattes de rive de pignon y compris toutes sujetions | m3 | 3.6 |  |  |
| 503 | Fourniture et realisation du plafond en contre plaque prealablement triate y compris solivage et toutes sujetions | m2 | 130 |  |  |
| 504 | Fourniture et realisation du plafond exterieur en tole lise y compris solivage et toutes sujetions | m2 | 56 |  |  |
| 505 | Fourniture et pose des planches de rive 30 cm y compris et toutes sujetions | ml | 95 |  |  |
| 506 | Fourniture et fixation de tole bac 6/10, des gouttieres et naissances en alu et des descentes en PVC protegees par des caisons en beton arme y compris et toutes sujetions | m2 | 450 |  |  |
| 507 | Fourniture et fixation de tole fatieres de 50cm de larger y compris et toutes sujetions | ml | 27 |  |  |
|  | SOUS TOTAL 500 |  |  |  |  |
|  | LOT 600: MENUISERIE METALLIQUE |  |  |  |  |
| 601 | Fourniture et fixation de portes metallique coulissante de 300x250 cm2 y compris et toutes sujetions | u | 2 |  |  |
| 602 | Fourniture et scellement de grilles antivol (motif barres droites espacees de 8cm) en tube de 30 mm y compris et toutes sujetions | m2 | 50 |  |  |
|  | SOUS TOTAL 600 |  |  |  |  |
|  | LOT 700: MENUISERIE BOIS, ALLUMINIUM ET VITRERIE |  |  |  |  |
| 701 | Fourniture et pose des portes en bois isoplane de 100*220cm2 sur cadre en bois dur y compris et toutes sujetions | u | 3 |  |  |

75

| 702 | Fourniture et pose des portes en bois massif de 180*220cm2 sur cadre en bois dur y compris et toutes sujetions | u | 2 |  |  |
| --- | --- | --- | --- | --- | --- |
| 703 | Fourniture et pose des portes en bois massif de 100*220cm2 sur cadre en bois dur y compris et toutes sujetions | u | 1 |  |  |
| 704 | Fourniture et pose des fenetres collissantes en aluminium vitree y compris et toutes sujetions | m2 | 3 |  |  |
|  | SOUS TOTAL 700 |  |  |  |  |
|  | LOT 800: ELECTRICITE ET PROTECTION CONTRE L'INCENDI |  |  |  |  |
| 801 | Fourniture et encastrement de gains annelees y compris toutes sujetions | ml | 100 |  |  |
| 802 | Fourniture et pose des gains IRL y compris toutes sujetions | ml | 600 |  |  |
| 803 | Fourniture et installation de cables TH 1,5mm2 y compris toutes sujetions | ml | 700 |  |  |
| 804 | Fourniture et installation de cables TH 2,5mm2 y compris toutes sujetions | ml | 800 |  |  |
| 805 | Fourniture et installation de cables U1000R2V 4mm2 y compris toutes sujetions | ml | 500 |  |  |
| 806 | Fourniture et installation de cables U1000R2V 5/6mm2 y compris toutes sujetions | ml | 300 |  |  |
| 807 | Fourniture et pose de reglettes avec tube fluorescent de 1,20m y compris toutes sujetions | u | 24 |  |  |
| 808 | Fourniture et pose des interupteurs et prises de courant encastre y compris toutes sujetions | u | 10 |  |  |
| 809 | Fourniture et pose des interupteurs et prises de courant apparent y compris toutes sujetions | u | 15 |  |  |
| 810 | Fourniture et installation du cables en cuivre de 29mm2 de section pour la mise a la terres y compris toutes sujetions | u | 1 |  |  |
| 811 | Fourniture et installation du tableau general electrique de commande du circuit des pris avec protection des circuit a l'aide des disjointeurs differentielles et parafoudre | ens | 1 |  |  |
| 812 | Fourniture et installation des attaches, dominos, boitieres, boite de derivation, y compris toutes sujetions avec raccordement au reaseaux existant | ens | 1 |  |  |
| 813 | Fourniture et pose d'intincteurs d'iincendie eau + additif 9 litres y compris toutes sujetions | u | 1 |  |  |
|  | SOUS TOTAL 800 |  |  |  |  |
|  | LOT 900: PEINTURE |  |  |  |  |
| 901 | Preparation des surfaces | m2 | 715 |  |  |

76

| 902 | Fourniture et applications de deux couches de peinture acrylique de type pantex 800 pour le plafond y compris toutes sujetions | m2 | 130 |  |  |
| --- | --- | --- | --- | --- | --- |
| 903 | Fourniture et applications de deux couches de peinture acrylique de type pantex 1300 pour murs exterieurs y compris toutes sujetions | m2 | 275 |  |  |
| 904 | Fourniture et applications de deux couches de peinture acrylique de type pantex 800 pour murs interieurs y compris toutes sujetions | m2 | 440 |  |  |
| 905 | Fourniture et applications de deux couches de peinture glycerophtalique de type email A pour menuiseries bois et metallique y compris toutes sujetions | m2 | 80 |  |  |
|  | SOUS TOTAL 900 |  |  |  |  |
|  | LOT 1000: PLOMBERIE ET REVETEMENT |  |  |  |  |
| 1001 | Fourniture et construction de la fosse septique de capacite 25m3 et les regards de visite y compris toutes sujetions | ens | 1.0 |  |  |
| 1002 | Fourniture et construction du puisard y compris toutes sujetions | u | 1 |  |  |
| 1003 | Fourniture et installation de la tuyauterie d'evacuation des eaux vannes et des euax usees y compris toutes sujetions | ml | 100 |  |  |
| 1004 | Fourniture et installation de la tuyauterie d'alimentation y compris toutes sujetions | ml | 100 |  |  |
| 1005 | Fourniture et pose de WC de marque PARMA y compris toutes sujetions | u | 1 |  |  |
| 1006 | Fourniture et pose de WC pour les personnes a mobilite reduite y compris toutes sujetions | u | 1 |  |  |
| 1007 | Fourniture et pose de lavabo avec console y compris toutes sujetions | u | 1 |  |  |
| 1008 | Fourniture et revetement du sol des toilettes en carreaux gres ceramique antiderapant de 30x30cm2 y compris toutes sujetions | m2 | 7.5 |  |  |
| 1009 | Fourniture et revetement du murs des toilettes en carreaux faience de 20x30cm2 y compris toutes sujetions | m2 | 30 |  |  |
| 1010 | 1010 Fourniture et pose du couler dans l'atelier | u | 2 |  |  |
| 1011 | 1011 Fourniture et pose du robinet dans l'atelier | u | 3 |  |  |
| 1012 | Fourniture et pose du cintres pour papier toilet dans l'atelier | u | 2 |  |  |
| 1013 | 1013 Fourniture et pose des mirroir | u | 1 |  |  |
| 1014 | Fourniture et installation des acessoires pour raccordements diverses y compris toutes sujetions | Ens | 1 |  |  |

77

|  | SOUS TOTAL 1000 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | LOT 1100: VRD ET AMENAGEMENT EXTERIEUR |  |  |  |  |
| 1101 | Fourniture et construction ds caniveaux en beton arme en forme de U de largeur 40cm, de profondeur minimale de 30cm, des parois d'epaisseur 8cm et de pente minimale de 2% y compris toutes sujetions | ml | 88.0 |  |  |
| 1102 | Fourniture et pose du dallettes de longeur 56cm de largeur 40cm, et d'epaisseur 8cm. | ml | 35 |  |  |
| 1103 | Fourniture et mise en ouvres d'un dallage en beton aux alentours du batiment y compris toutes sujetions | m2 | 84 |  |  |
|  | SOUS TOTAL 1100 |  |  |  |  |
|  | TOTAL WITHOUT TAXES |  |  |  |  |
|  | AIR(2.2%) |  |  | 2.20% |  |
|  | VAT (19.25%) |  |  | 19.25% |  |
|  | TOTAL WITH TAXES INCLUSIVE |  |  |  |  |
|  | NET AMOUNT TO BE PAID |  |  |  |  |

| BILL OF QUANTITIES AND ESTIMATES FOR THE CONSTRUCTION OF A G+1 IT CENTRE FOR GTHS BAMENDANKWE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ITEM | DESIGNATION | UNIT ARY |  | UNIT COST | AMOUNT |
|  | 100- PRELIMIN ARY W ORKS |  |  |  |  |
| 101 | Site clearance | m² | 394 |  |  |
| 102 | Hoarding and work posts | ml | 107 |  |  |
| 103 | Levelling (excavation) and provision of access way | m3 | 819 |  |  |
|  | PRELIMINARY WORKS TOTAL | OUN D |  |  |  |
|  | 200- FOUN DATIO N |  |  |  |  |
| 201 | Setting out of foundation | u | 1 |  |  |
| 202 | Excavation of footings | m3 | 30 |  |  |
| 202 | Excavation of trenches | m3 | 83.39 |  |  |
| 203 | Lean concrete of dossage 150kg/m3 | m3 | 1.48 |  |  |
| 204 | R C concrete of 350kg/m3 for Footings 1.3x 1.3 | m3 | 10.65 |  |  |
| 205 | R C concrete of 350kg/m3 pillars | m3 | 1.16 |  |  |
| 206 | R C concrete of 350kg/m3 for Ground beams | m3 | 5.46 |  |  |
| 208 | Block work 20 x 40 filled with plain concrete | m2 | 91 |  |  |
| 209 | Volume of backfill upto 45cm height | m3 | 40 |  |  |
|  | FOUNDATION TOTAL | OR E |  |  |  |
|  | 300-GROUND FLO OR ELEVATION |  |  |  |  |

78

| 301 | Masonry ( 15 x 20 x 40 cm Sandcrete blocks ) | m² | 180 |  |  |
| --- | --- | --- | --- | --- | --- |
| 302 | R C concrete of 350kg/m3 for Pillars, , Lintels | m3 | 5.55 |  |  |
| 303 | R C concrete of 350kg/m3 for half beam | m3 | 5 |  |  |
| 304 | R C concrete gutters around GFL 40 x 40 in to in | m2 | 7.3 |  |  |
|  | GROUND FLOOR ELEVATION TOTAL | OOR D |  |  |  |
|  | 400- GROUND FL OOR DE CKING |  |  |  |  |
| 401 | Decking blocks | m2 | 140 |  |  |
| 402 | R C concrete of 350kg/m3 for Rib-beams | m3 | 5.8 |  |  |
| 403 | R C concrete of 350kg/m3 for Slab | m3 | 7.4 |  |  |
| 404 | R C concrete of 350kg/m3 to complete 1/2beams | m3 | 3.8 |  |  |
| 405 | R C concrete of 350kg/m3 for Stairs | m3 | 1.52 |  |  |
|  | DECKING TOTAL |  |  |  |  |
|  | 500- RA MP |  |  |  |  |
| 502 | R C concrete of 350kg/m3 for Footings and pillars | m3 | 3.5 |  |  |
| 503 | R C concrete of 350kg/m3 for Slab and side beams | m3 | 13.85 |  |  |
| 504 | Wooden props to carry ramp covering | m3 | 0.3 |  |  |
| 505 | Stucco Tiling to ramp floor | m2 | 58 |  |  |
| 505 | Framing and alu tol bac 40 covering | m2 | 60.5 |  |  |
|  | DECKING TOTAL | ELEV |  |  |  |
|  | 600- FIRST FLOOR ELEVATION |  |  |  |  |
| 601 | Block Walls 15 x 20 x 40 | m2 | 190.5 |  |  |
| 602 | Concreting of Pillars 20 x 30 and 20 x 40 | m3 | 4 |  |  |
| 603 | Lintels 15x20 | m3 | 3.8 |  |  |
| 604 | Tie beam internal 15x20 | m3 | 1 |  |  |
| 604 | External tie beam 15x30 | m3 | 2.8 |  |  |
| 604 | Parapet upper and lower beams 15x20 | m3 | 3.6 |  |  |
| 604 | Parapet Block work | m2 | 25 |  |  |
|  | FIRST FLOOR ELEVATION TOTAL | ROO F |  |  |  |
|  | 700- ROO FING |  |  |  |  |
| 701 | Timber for Rafters | m3 | 4.41 |  |  |
| 702 | Timber for Purlins 5cm x5cm | m3 | 0.98 |  |  |
| 704 | Tole bac sheets in alumunium 5/10 (bordeaux) | m2 | 209 |  |  |
| 705 | Hip ridges | ml | 36.86 |  |  |
| 706 | Rain water gutter | ml | 55 |  |  |
| 707 | Down pipes 80mm | ml | 68 |  |  |
| 708 | down pipe funnels | ml | 8 |  |  |
| 709 | 45 o elbows | ml | 16 |  |  |
| 710 | 90 o elbows | ml | 8 |  |  |
| 711 | Nails and other accessories | ls | 1 |  |  |
|  | ROOFING TOTAL | D WO |  |  |  |
|  | 800- CARPENTRY AN D WO OD WORK |  |  |  |  |
| 801 | Complete door frames and shutters 90x210 | u | 3 |  |  |
| 802 | Complete door frames and panel shutters 70x210 | u | 1 |  |  |

79

|  | CARPENTRY WORK TOTAL | META |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 900- ALUMINIUM AND META LLIC WORK |  |  |  |  |
| 901 | Complete door frames and panel shutters ext doors 100x210 | u | 6 |  |  |
| 902 | Guard rails to blaconies and stairs | ml | 22 |  |  |
| 903 | Provision and fittiing of Aluminium glider windows including glass 1.4 x 1.3 | m2 | 29.5 |  |  |
| 903 | Provision and fittiing of Aluminium glider windows including glass 60 x 60 | m2 | 1.2 |  |  |
| 904 | Provision and fitting of Iron protectors for all windows | m2 | 33.32 |  |  |
|  | ALU/METALLIC WORK TOTAL | UMBI |  |  |  |
|  | 1000- PLUMBING |  |  |  |  |
|  | Piping |  |  |  |  |
| 1001 | Inspection chambers | u | 2 |  |  |
| 1002 | Septic tank & | u | 1 |  |  |
| 1003 | Soakaway pit | u | 1 |  |  |
| 1004 | Water Supply pipes 3/4 inch | ml | 15 |  |  |
| 1005 | Drainage pipes ϕ 100 | ml | 15 |  |  |
| 1006 | Drainage pipes ϕ 60 | ml | 80 |  |  |
| 1007 | 90o elbow ϕ 100 | u | 8 |  |  |
| 1008 | 90o elbow ϕ 60 | u | 8 |  |  |
| 1009 | Gully trap elbow ϕ 100 | u | 1 |  |  |
| 1010 | 90o elbow 3/4 inch | u | 3 |  |  |
| 1011 | T-junction connector 3/4 inch | u | 2 |  |  |
| 1012 | Stopcork valve 3/4 inch | u | 2 |  |  |
|  | Installation |  |  |  |  |
| 1013 | Faucet taps | u | 1 |  |  |
| 1014 | Wash-hand basins | u | 1 |  |  |
|  | PLUMBING TOTAL | C TRI |  |  |  |
|  | 1100- ELEC TRICIT Y |  |  |  |  |
| 1101 | PIPING |  |  |  |  |
| 1102 | Lightening Conductor(22mm) | m | 30 |  |  |
| 1103 | Earth Rod | u | 1 |  |  |
| 1104 | Rubber Plastic Cups for switches and sockets | u | 57 |  |  |
| 1105 | Plastic Junction Boxes 8cm | u | 10 |  |  |
| 1106 | Plastic Junction Boxes 5cm | u | 10 |  |  |
| 1107 | Conduit Pipe 13mm | Roll | 20 |  |  |
| 1108 | Conduit Pipe 16mm | Roll | 10 |  |  |
| 1109 | line seperator box | u | 2 |  |  |
| 1110 | Main switch boxes | u | 1 |  |  |
|  | SUBTOTAL |  |  |  |  |
|  | CABLING & WIRING |  |  |  |  |
| 1402 | Provision of treated and planting electric poles to connect power from current administrative block | u | 3 |  |  |

80

| 1112 | Three phase power supply tendons | roll | 3 |  |  |
| --- | --- | --- | --- | --- | --- |
| 1112 | Industrial Cable for heavy appliances 4mm | Roll | 4 |  |  |
| 1113 | 2.5mm Single Cable -roll | Roll | 2 |  |  |
| 1114 | 1.5mm Single Cable -roll | Roll | 2 |  |  |
| 1115 | Internet cable | Roll | 2 |  |  |
| 1116 | Earth Cable 4mm | Roll | 1 |  |  |
|  | SUBTOTAL |  |  |  |  |
|  | FITTINGS |  |  |  |  |
| 1118 | Energy saving Incandescent (Ø 15cm) High luminar | u | 27 |  |  |
| 1119 | Lamp holders | u | 27 |  |  |
| 1120 | Switches | u | 35 |  |  |
| 1121 | Sockets | u | 18 |  |  |
| 1122 | Installation of cicuit breakers Coupe-circuit selectionable SP 51 3P+N 14 X 51 LEGR | u | 1 |  |  |
| 1123 | Internet Plugs | u | 14 |  |  |
|  | SUBTOTAL |  |  |  |  |
|  | ELECTRICITY TOTAL | G W A |  |  |  |
|  | 1200- RETAIN ING W ALL |  |  |  |  |
| 1201 | Setting out of foundation | u | 1 |  |  |
| 1202 | Excavation of strip footings 60x50 | m3 | 13.8 |  |  |
| 1203 | Lean concrete of dossage 150kg/m3 | m3 | 1.48 |  |  |
| 1204 | Stone strip footing 40 x 60 | m3 | 11.04 |  |  |
| 1205 | R C concrete of 350kg/m3 pillars 20 X 30 interspaced @ 3.5m c/c | m3 | 2 |  |  |
| 1206 | R C concrete of 350kg/m3 for chaining beams at the base on stone base 30 x 30 | m3 | 4.4 |  |  |
| 1207 | Stone masonry retaining wall 30cm x 2.60m high x 46.5ml | m2 | 35.88 |  |  |
| 1208 | R C concrete of 350kg/m3 for middle belt beams 20 x 30 | m3 | 2.76 |  |  |
| 1209 | R C concrete of 350kg/m3 for tie beams 30 x 30 | m3 | 4.4 |  |  |
| 1210 | Volume of backfill upto height | m3 | 36 |  |  |
| 1211 | Provision and planting of metallic of guard rails over retaining wall | ml | 42 |  |  |
| 1211 | Provision of steps 1.5m width between retaining wall to connect to upper existing blocks | m3 | 1.3 |  |  |
|  | RETAINING WALL TOTAL | FINIS |  |  |  |
|  | 1300 - FINISHING |  |  |  |  |
| 1301 | Floor screed to ground floor (8cm) | m3 | 9.95 |  |  |
| 1302 | Plastering to walls | m² | 735 |  |  |
| 1303 | Plastering of the soffit | m² | 130 |  |  |
| 1304 | Dressing of window and door edges and angles | m² | 20.35 |  |  |
| 1305 | Framing and plywood 1st floor ceiling | m2 | 140 |  |  |

81

| 1306 | Porcelian vitrified tiles to all floors corridor, halls offices, stairs | m2 | 276 |  |  |
| --- | --- | --- | --- | --- | --- |
| 1307 | Tilling to toilet floors | m2 | 3.6 |  |  |
| 1308 | Tiles to toilet walls | m2 | 18 |  |  |
| 1309 | White wash to all walls | m² | 735 |  |  |
| 1310 | Painting pantex 800 to all walls (walls yellow + pillars ash gray and ox blood skirting | m² | 735 |  |  |
| 1310 | Painting pantex 800 to ceiling white | m² | 280 |  |  |
| 1311 | Oil paint to iron and wooden doors | ls | 1 |  |  |
|  | FINISHING TOTAL | TR E | E PLANTIN G |  |  |
|  | 1400 - LANDSCAPING A ND TR EE PLANTIN G |  |  |  |  |
| 1401 | Grading of surface to planes for lawn 43 x6 | m2 | 190 |  |  |
| 1402 | Planting of lawn | m² | 190 |  |  |
| 1403 | Planting of trees | u | 30 |  |  |
|  | SUB-TOTAL 1400 |  |  |  |  |
|  | GRAND TOTAL WTHOUT TAXES (TWT) |  |  |  |  |
|  | AIR(2.2%) |  |  |  |  |
|  | TVA(19.25%) |  |  |  |  |
|  | TOTAL TWAT |  |  |  |  |

82

Document No. 8

SUB-DETAIL OF PRICES

83

SUBDETAILS OF PRICES 
Price N° ………………………………………………………………………………………… Designation of work…………………………………………………………………………… Unit ……………………………………………………………………………………………. Quantity ………………………………………………………………………………………. Daily output …………………………………………………………………………………… Duration of execution …………………………………………………………………………

| DESIGNATION : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No | Daily out put |  | Total quantity | Unit | Duration of activity |
|  |  | No |  |  |  |
| WORKMAN SHIP | Category |  | Daily wage | Days break up | Amount |
|  | TOTAL A |  |  |  |  |
| EQUIPMENT /MECHINES | Type | No | Daily rate | Days break up | Amount |
|  | TOTAL B |  |  |  |  |
| MATERIAL AND MISCELLANOUS | Type | Un it | Unit cost | Quantity | Amount |
|  | TOTAL C |  |  |  |  |
| D | DIRECT TOTAL COST |  |  | A+B+C |  |
| E | GENERAL SITE EXPENESES |  |  | Dx% |  |
| F | GENERAL OFFICE EXPENSES |  |  | Dx% |  |
| G | NET COST |  |  | D+E+F |  |
| H | RISK + BENEFITS |  |  | Gx% |  |
| P | TOTAL COST (HT) |  |  | G+H |  |
| V | UNIT COST (HT) |  |  | P/Q’TY |  |

84

Document No. 9

MODEL CONTRACT

85

| REPUBLIC OF CAMEROON Peace-Work-Fatherland …………….. NORTH-WEST REGIONAL ASSEMBLY …………….. REGIONAL EXECUTIVE ASSEMBLY …………….. PEACE-JUSTICE-UNITY-HARD WORK- SOLIDARITY …………….. |  | REPUBLIQUE DU CAMEROUN Paix-Travail-Patrie …………….. ASSEMBLEE REGIONALE DU NORD-OUEST …………….. CONSEIL EXECUTIF REGIONAL …………….. PAIX-JUSTICE-UNITE-TRAVAIL-SOLIDARITE …………….. |
| --- | --- | --- |

JOBBING ORDER NO___________ JO/MINDEVEL/NWRA/ITB/2026 OF ........2026 
AWARDED AFTER OPEN NATIONAL INVITATION TO TENDER  NO ________ 
/ONIT/NWRA/ITB/2026 OF ___/__/2026 FOR THE CONSTRUCTION OF WORKSHOPS IN SOME GOVERNMENT TECHNICAL HIGH SCHOOLS OF THE NORTH WEST REGION DIVIDED INTO TWO (02) LOTS

Project Owner: THE PRESIDENT OF THE NORTH WEST REGIONAL ASSEMBLY

HOLDER :

P.O. Box_________, Tel:_________Fax: ____________

Business Registry No.___________at 
Taxpayer’s No._____________

SUBJECT: Execution of ______________works;

PLACE 	: _____________________________

EXECUTION DEADLINE: _____________________ (_______) months

AMOUNT IN CFA F:

| IAT |  |
| --- | --- |
| EVAT |  |
| VAT (19.25%) |  |
| AIR (Income tax) (2.2%) |  |
| Net to be paid |  |

| FINANCING BUDGET HEAD | : [indicate the source of financing] : [to be completed] |
| --- | --- |

SUBSCRIBED ON: ________________ 
SIGNED ON: _____________________ 
NOTIFIED ON: ___________________ 
REGISTERED ON: _________________

Between:

86

The Government of the Republic of Cameroon, represented by The President of the North West Regional Assembly hereinafter referred to the “Contracting Authority”

On the one hand,

And

______________________(enterprise) 
P.O. Box________Tel:_________Fax:_________ 
Business Registry No. ___________ 
Taxpayer’s No. ___________________

Represented by M _________________, its General Manager, hereinafter referred to as the “Contractor”

On the other hand,

Agree on the following:

87

Summary

Part I:    Special AdministrativeConditions (SAC)

Part II:   Special Technical Conditions (STC)

Part III:  Schedule of Unit Prices (SUP)

Part IV:  Details or Estimates

88

Page_______ and last of Jobbing Order No______________ JO/MINDEVEL/NWRA/ITB/2026 OF .......................2026 AWARDED AFTER OPEN NATIONAL INVITATION TO TENDER No ___/ONIT/NWRA/ITB/2026 of __/__/2026 FOR THE CONSTRUCTION OF WORKSHOPS IN SOME GOVERNMENT TECHNICAL HIGH SCHOOLS OF THE NORTH WEST REGION DIVIDED INTO TWO (02) LOTS

With __________,

For the execution of _______________works

EXECUTION DEADLINE____________ (______) months

Amount of Contract in CFA F:

| IAT |  |
| --- | --- |
| EVAT |  |
| VAT (19.25) |  |
| AIR (2.2 or 5.5 %) |  |
| Net to be paid |  |

Read and accepted by the Contractor (place of signature)__________(date)

Signature of Contracting Authority (place of signature)__________(date)

Registration

89

Document No. 10

FORMS AND MODELS TO BE USED BY BIDDERS

90

TABLE OF MODELS

Annex N° 1: Model of declaration to Tender 
Annex N° 2: Model Bid 
Annex N° 3: Model Bid Bond 
Annex N° 4: Model Final Bond 
Annex N° 5: Model Retention fund (Guarantee Retention) Annex N° 6: Schedule framework 
Annex N° 7:    Model attestation of site visit 
Annex N° 8:   Model site visit report 
Annex N° 9:   Model table of reference 
Annex N° 10:  Model table of equipment

91

Annex N° 1: MODEL OF DECLARATION TO TENDER

DECLARATION OF THE INTENTION TO TENDER

I the undersigned, ……………………………………….……..(indicate the name and capacity of signatory), Nationality …………………………….Representing the …………………….……………. company or

enterprise or group with head office at …………….…………………………..... registered in the trade register of ………………………. Under the number ……………… 
In my capacity as ……………………………..of …………………………………………………………… PO box……………………, hereby acknowledge receipt of the file for Open National Invitation to Tender N0 ………………………… for the …………………………………………………………………

And hereby declare my intention to tender for the said contract.

Done at …………………………..

Signature of ………………………….

In the capacity of …………………… 
Duly authorized to sign the tenders on behalf of …………………………….

92

Annex N° 2: MODEL BID

I the undersigned, ……………………………..(indicate the name and capacity of signatory) 
Representing the ………………………………………. company or enterprise or group with head office at ………..….. registered in the trade register of ………………………. Under the number ………………

Having taken cognizance of all the documents featured or mentioned in the Tender file: Open National Invitation to Tender No ___/ONIT/NWRA/ITB/2026 of __/__/2026 for the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots after having personally taking account of the situation of the site and evaluated from my point of view and under my responsibility, the nature and difficulty of the works to be carried out;

Hereby submit, bearing my signature, the schedule of unit prices as well as the quotations in 	accordance with the structure featuring in the Tender File; 
Submit and commit myself to execute the works in accordance with the Tender File, in return for the 	prices which I myself establish for each type of structure which prices reveal the amount of the 	tender at …………………….. (in figures and words) CFAF exclusive of VAT and at 	………………….. ( in figures and in words) CFAF inclusive of all taxes.

I pledge to execute the works within a deadline of ………………..months.

I pledge to maintain my offer for a duration of Ninety (90) days from the deadline of submission of 		tenders; 
The Contracting Authority shall pay the sums due for this Contract by crediting Account N°:……………. opened in …………………. Bank ……………… Branch.

Prior to the signing of the Contract, this tender accepted by you shall constitute an agreement between us.

Done at …………………………..

Signature of ………………………….

In the capacity of …………………… 
Duly authorized to sign the tenders on behalf of ……………………………..

93

Annex N° 3: MODEL BID BOND

Bank: 
Reference No. …………………………..

Addressed to the Contracting Authority: The President of the North West Regional Assembly

Whereas the undertaking …………………………. Hereinafter referred to as the “bidder” has submitted his tender on …………….. for Open National Invitation to Tender No ___/ONIT/NWRA/ITB/2026 of __/__/2026 for the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots, hereinafter referred to as “the tender” and to which must be attached a bid bond equivalent to …………………CFAF.

We …………….. (name and address of the bank), represented by …………………………. (names of signatories), hereinafter referred to as “the Bank” hereby declare to guarantee payment to the Contracting Authority of the maximum sum of ……………………………….., that the bank pledges to pay in full to the Contracting Authority, bidding itself, its successors and assignees.

The conditions of this commitment are as follows: 
If the Bidder withdraws his offer during the validity period specified by the Bidder in the tender; or If the Bidder, having been notified of the award of the contract by the Contracting Authority during the period of Bid validity:

Fails or refuses to sign the contract, even though required to do so; 
	Fails or refuses to furnish the final bond for the contract (final bond) as provided for by the contract. We undertake to pay the Contracting Authority an amount up to the maximum of the sum referred to above upon receipt of his first written demand, without the Contracting Authority having to substantiate his demand, provided that in its demand the Contracting Authority shall note that the amount claimed by him is due, because one or the other or both of the above condition(s) has (have) been fulfilled and he shall specify which condition(s) took effect.

This bond shall enter into force from the date of signature and from the date set by the Contracting Authority for the submission of tenders.  It shall remain valid up till the thirtieth day inclusive following the end of the deadline for the validity of tenders.  Any request by the Contracting Authority to cause it to take effect should reach the bank by registered mail with an acknowledgement of receipt before the end of this period of validity.

This bond shall, for purposes of its interpretation, be submitted to Cameroon law.  Cameroon courts shall be the only jurisdictions competent to rule on this commitment and its consequences.

Signed and authenticated by the bank 
at ………………………, on ……………………..

(Bank’s signature

94

Annex N° 4: MODEL FINAL BOND

Bank: ……………………..

Reference of the Bond No: …………………………………..

Addressed to The President of the North West Regional Assembly “Contracting Authority”

Whereas ……………………. (Name and address of Contractor) hereinafter referred to “the Contractor”, pledge, in execution of the Contract, to carry out the works: Open National Invitation to Tender No ___/ONIT/NWRA/ITB/2026  of __/__/2026 for the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots.

Whereas it is stipulated in the Contract that the Contractor shall furnish the Contracting Authority a final

bond of two percent (2%) of the amount of the Contract as security for compliance with the Contractor’s performance obligations in accordance with the Contract.

Whereas we have agreed to provide the Contractor with this guarantee; 
We, ………………………………………………….. (name and address of bank),

Represented by …………………………………… (name of signatories) 
hereinafter referred to as “the Bank”, and we pledge to pay to the Contracting Authority within a maximum deadline of eight (8) weeks upon his simple written request declaring that the Contractor has not fulfilled his contractual obligations, without being able to defer the payment nor raise any contest for whatever reason, the sum of …………………….. …………………………………… (in letters and in words).

We hereby agree that no change or addendum or any other amendment shall release us of any obligation incumbent onus by virtue of this bond and we hereby derogate by the present to the notification of any amendment, addendum or change.

This bond shall enter into force upon signature.  It shall be released within thirty (30) days from the date of the Provisional Reception of the works.

After this date the caution shall no longer be valid and shall be returned to us without any request on our part.

Any request for payment formulated by the Contracting Authority by virtue of this bond should be done by registered mail with acknowledgement of receipt to reach the bank during the period of validity of this commitment.

This bond shall, for purposes of its interpretation and execution, be subject to Cameroon law.  Cameroon courts shall be the only jurisdictions competent to rule on this pledge and its consequences.

Signed and authenticated by the bank at ………………… on …………………… 	[signature of the bank]

95

Annex N° 5: MODEL OF PERFORMANCE BOND (GUARANTEE RETENTION)

Bank: ……………………..

Reference of the Bond No: …………………………………..

Addressed to: The President of the North West Regional Assembly Hereinafter referred to as “The Contracting Authority”

Whereas ……………………. (name and address of Contractor) hereinafter referred to “the Contractor”, pledge , in execution of the Contract, to carry out the works for the Construction of Workshops in some Government Technical High Schools of the North West Region Divided into Two (02) Lots 
Whereas it is stipulated in the Contract that the Guarantee Retention fixed at ten percent (10%) of the amount of the Contract may be replaced by a joint guarantee;

Whereas we have agreed to provide the Contractor with this guarantee; 
We, ………………………………………………….. (name and address of bank),

Represented by …………………………………… (name of signatories) and hereinafter referred to as “the Bank”;

Hence, we hereby affirm that on behalf of the Contractor, we guarantee and are responsible to the Contracting Authority for a maximum amount of  …………………………. (in figures and in letters) corresponding to ten percent (10%) of the Contract amount.

And we pledge to pay to the Contracting Authority within a maximum deadline of eight (8) weeks upon his simple written request declaring that the contractor has not fulfilled his contractual obligations or is indebted to the Contracting Authority within the meaning of the contract, amended where need be, by its additional clauses, without being able to defer the payment nor raise any contest for whatever reason, any sum(s) within the limits of the amount equal to ten percent (10%) of the total amount of the works featuring in the final detailed account, without the Contracting Authority having to prove or give the reasons nor the motive for the amount of the sum indicated above.

We hereby agree that no change or addendum or any other amendment shall release us of any obligation incumbent onus by virtue of this bond and we hereby derogate by the present to the notification of any amendment, addendum or change.

This bond shall enter into force upon signature.  It shall be released within thirty (30) days from the date of the final acceptance of the works and upon released issued by the Contracting Authority.

Any request for payment formulated by the Contracting Authority by virtue of this bond should be done by registered mail with acknowledgement of receipt to reach the bank during the period of validity of this commitment.

This bond shall, for purposes of its interpretation and execution, be subject to Cameroon law.  Cameroon courts shall be the only jurisdictions competent to rule on this pledge and its consequences.

Signed and authenticated by the bank at ………………… on …………………… 	[signature of the bank]

96

ANNEX N° 6: SCHEDULE FRAMEWORK

Note on the presentation of schedules

The quantities, daily outputs, the duration of execution of works and the slowdowns or even the due interruptions must be clearly brought out in the schedules.

The financial schedules resulting from the schedules of works must indicate month by month, the estimated amounts of the detailed accounts of works by item and cumulatively by taking into account the incidence of rainy seasons for the basic solution and possibly variant solution.

97

Annex N° 7: MODEL ATTESTATION OF SITE VISIT

LETTER HEAD HERE

TO WHOM IT MAY CONCERN

ATTESTATION OF SITE VISIT

This is to testify that Mr …………………………………………………………………………….………. Manager/Technical Director/Engineer of ……………………………………………………………………. Has effectively visited the site for ……………………………………………………………………………..

…………………………………………………………………………………………………………………………………. in view to tender for the said project.

This attestation is issued to serve the purpose for which it is intended for.

98

Annex N° 8: MODEL SITE VISIT REPORT

I)INTRODUCTION 
TENDER N0……………………………………….. NAME OF THE ENTERPRISE: ……………………….. DATE: ………………………….

II)COMMENTARY 
1-Nature of the project site:

2-Accessibility to the project site:

3-Vegetation:

4-Topography of the site:

III) AVAILABILITY OF SERVICES

IV) AVAILABILITY OF MATERIALS

V)DIFFICULTIES

VI) CONCLUSION

99

Annex N° 9: MODEL TABLE OF REFERENCE

LIST OF PROJECTS EXECUTED BY THE COMPANY

| NO | YEAR | NAME OF THE PROJECT | NAME OF THE PROJECT OWNER AND TELEPHONE NUMBER | CONTRACT AMOUNT | CONTRACT DURATION | DATE OF ACCEPTANC E |
| --- | --- | --- | --- | --- | --- | --- |

DONE ON ……………………………….AT …........................... By……………………………………………………………………. SIGNATURE ………………………………………………………….

100

Annex N° 10: MODEL TABLE OF EQUIPMENT

LIST OF EQUIPMENT AND MATERIALS AVAILABLE FOR THE (project name) ……………………………..

| NO | DESIGNATION OF THE EQUIPMENT | DESCRIPTION, MARK | AGE AND STATE | NUMBER AVAILABLE | OWNER OR NOT |
| --- | --- | --- | --- | --- | --- |

DONE ON ……………………………….AT …........................... By……………………………………………………………………. SIGNATURE ………………………………………………………….

101

ANNEX No. 6: Framework of schedules

| DESIGNATION : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No | Daily out put |  | Total quantity | Unit | Duration of activity |
|  |  | No |  |  |  |
| WORKMAN SHIP | Category |  | Daily wage | Days break up | Amount |
|  | TOTAL A |  |  |  |  |
| EQUIPMENT/MACHIN ES | Type | No | Daily rate | Days break up | Amount |
|  | TOTAL B |  |  |  |  |
| MATERIAL AND MISCELLANOUS | Type | Unit | Unit cost | Quantity | Amount |
|  | TOTAL C |  |  |  |  |
| D | DIRECT TOTAL COST |  |  | A+B+C |  |
| E | GENERAL SITE EXPENSES |  |  | Dx% |  |
| F | GENERAL OFFICE EXPENSES |  |  | Dx% |  |
| G | NET COST |  |  | D+E+F |  |
| H | RISK + BENEFITS |  |  | Gx% |  |
| P | TOTAL COST (HT) |  |  | G+H |  |
| V | UNIT COST (HT) |  |  | P/Q’TY |  |

102

Document No. 11

PRELIMINARY STUDIES

103

Note on preliminary studies

In accordance with the Public Contracts Code, the Project Owner or Delegated Project Owner must, prior to commencing the procedure to award Contracts or refer to the competent Tenders Board, ensure that draft Tender Files are prepared based on preliminary studies.

These studies must be required during the examination of the Tender File (TF) by the Tenders Board.

The Project Owner is bound to fill the questionnaire in annex 1 accompanied by justifications of the said studies.

Annex No. 7: Justification of preliminary studies

1.Attach the preliminary studies.

2.Indicate 
	2.1. 	The date studies were carried out; 
	2.2. 	The name of the Public or private Project Manager 
	2.3. 	References of the Contract, if Private Manager  carried it out;

2.4.If  maintenance works 
	2.4.1 Description of the studies; 
2.4.2Attach the outline of the itinerary bringing out readings of degradations as well as the 			approved programming documents.

2.5Rehabilitation or new works 
2.5.1Are quantities in the quotations the same as those of the studies?

2.5.2Description of studies: Draft Preliminary Study, Detailed Preliminary Study; 2.5.3Attach the said studies.

N.B.  For services of less scope, the Project Owner may furnish a justification of calculation of quantities of the Tender File.

-The chairperson of the Tenders Board may, before taking a decision, seek expert advice on the quality of 	the studies.

104

Document No.12

LIST OF BANKING ESTABLISHMENTS AND FINANCIAL BODIES AUTHORISED TO ISSUE BONDS FOR PUBLIC CONTRACTS

105

I- BANK

1. 	Afriland  First   Bank (First bank), B.P 11 834, Yaoundé;

2. 	Banque Atlantique Cameroun (BACM), B.P. 2 933, Douala;

3. 	Banque Camerounaise des Petites et Moyennes Entreprises (BC-PME), B.P. 12 962, Yaoundé;

4. 	Banque Gabonaise pour le Financement International (BGFI BANK), B.P. 600  Douala ;

5. 	Banque International du Cameroun pour l’Epargne  et le Crédit  (BICEC) B.P. 1 925, Douala ;

6. 	Bank Of Africa Cameroun (BOA  Cameroun), B.P. 4 593, Douala ;

7. 	CitiBank Cameroun (CITIGROUP), B.P. 4 571, Douala ;

8. 	Commercial  Bank  - Cameroon  (CBC), B.P 4 004, Douala;

9. 	Ecobank Cameroun (ECOBANK), B.P 582, Douala;

10. 	National Financial Credit Bank (NFC-Bank), B.P. 6 578, Yaoundé ;

11. 	Société Commerciale de Banques-Cameroun (SCB-Cameroun), B.P 300, Douala ;

12. 	Société  Générale  Cameroun (SGC), B.P. 4 042, Douala ;

13. 	Standard Chartered  Bank Cameroon (SCBC) B.P. 1784, Douala ;

14. 	Union Bank of Cameroon (UBC), B.P. 15 569, Douala;

15. 	United Bank for Africa (UBA), B.P. 2 088, Douala.

16. 	crédit communautaire d'afrique-bank (CCA – Bank)

I I - I n s u ra nc e c o mp a ni e s

17. 	Activa Assurances

18. 	AREA Assurances

19. 	Atlantique Assurances S.A.

20. 	Benefical General Insurance S.A.

21. 	Chanas assurances

22. 	CPA S.A.

23. 	NSIA Assurances SA

24. 	PRO-ASSUR S.A.

25. 	SAAR S.A.

26. 	SAHAM Assurances S.A.

27. 	Zenithe Insurance S.A.

106

PLANS

107