## REPUBLIQUE DU CAMEROU   	                                                                                               REPUBLIC OF CAMEROON

# Paix – Travail – Patria                                                                                                                         Peace – Work – Fatherland

MINISTERE DE LA DECENTRALISATION 	                                                                  MINISTRY OF DECENTRALISATION

#### ET DE LA DEVELOPEMENT LOCAL                                                                                             AND    LOCAL DEVELOPMENT

# RÉGION DU NORD-OUEST		                                                                                                      NORTH WEST REGION

# COMMUNE DE JAKIRI	                                                                                                                             JAKIRI COUNCIL

## TEL: (237) 652939462				                                                                             TEL: (237) 652939462

### BP. 2, JAKIRI  			                                                                                                                   P.O. BOX 2 JAKIRI

### Email: jakirimunicipality@yahoo.com                                                                                                  www: jakiricouncil.org

JAKIRI COUNCIL INTERNAL TENDERS BOARD

TENDER FILE

OPEN NATIONAL INVITATION TO TENDER N° 06/ONIT/JAKIRI COUNCIL/JCITB/2026 OF 23/01/2026 FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

##### FUNDING: MINEE 2026 BUDGET

JANUARY 2026

## T A B L E OF ABBREVIATIONS

ARMP : Public Contracts Regulatory Agency

UPS : Unit Price Schedule

BOQ : Bill of Quantities and Cost Estimates

MINMAP : Ministry of Public Contracts

PO/DPO: Project Owner/Delegated Project Owner

UPB : Unit Price Breakdown

CIPM : Internal Tenders Board Commission

CCCM : Central Commission for the Control of Public Contracts

CSPM : Special Tenders Board Commission

CDPM : Divisional Tenders Board Commission

DTAO : Typical Tender Document

DAO : Tender Document

## T A B L E D E S SI G L E S

ARMP : Agence de Régulation des Marchés Publics

BPU : Bordereau des Prix Unitaires

DQE : Devis Quantitatif et Estimatif

MINMAP : Ministère des Marchés Publics

MO/MOD : Maître d’Ouvrage/Maître d’Ouvrage Délégué

SDPU : Sous-Détail des Prix Unitaires

CIPM : Commission Interne de Passation des Marchés

CCCM : Commission Centrale de Contrôles des Marchés Publics

CSPM : Commission Spéciale de Passation de Marchés Publics

CDPM : Commission Départementale de Passation des Marchés Publics

DTAO : Dossier Type d’Appel d’Offres

DAO : Dossier d’Appels d’Offres

CONTENT OF THE TENDER DOCUMENT (TD)

Doc 1 :	Tender notice (TN) (English and French version)

Doc 2 :         General Rules of the Tender Document (GRTD)

Doc 3 :	Specific Rules of the Tender Document (SRTD)

Doc 4 :	The special Administrative Clause document (CCAP)

Doc 5 :	The Technical Specifications document (CPT)

Doc 6 :	Schedule of Unit Prices (BPU)

Doc 7 :	Schedule of the Bill of Quantities and Cost Estimates (DQE)

Doc 8 :	Frame Work of breakdown of Prices

Document No. 9: Draft Contract

Document No. 10: Model documents to be used by bidders

  - Model of tender letter ;

  - Model of Bid Bond  (Temporary Bank guarantee for tender) ;

  - Model of final bid bond (final bank guarantee) ;

  - Model of bank guarantee for the restitution of start-up advance ;

  - Model of The Attestation of site visit;

  - Model of Information on the proposed key personnel to be deployed ;

  - Recapitulative Model form for the company references ;

  - Model form for power of attorney (in case of joint ventures ) ;

  - Model form of agreement for joint-venture ;

Document No. 11: Noting sheet for the Technical Bid;

Document No. 12: Declaration of social and environmental engagement

Document No. 13: Visa of Maturation or Justifications of studies realized

Document No. 14: List of banking establishments and financial bodies authorised to issue bonds for public contracts.

Document No. 15: Procedure for Online Procurement

Document No. 1:

Tender Notice

Document 1.a

ENGLISH VERSION

| REPUBLIC OF CAMEROON Peace – Work – Fatherland ************ |  | REPUBLIQUE DU CAMEROUN Paix – Travail – Patrie ************ |
| --- | --- | --- |
| MINISTRY OF DECENTRALISATION AND LOCAL DEVELOPMENT ************ |  | MINISTÈRE DE LA DÉCENTRALIZATION ET DEVELOPPEMENT AND LOCAL ************ |
| NORTH WEST REGION ************ |  | REGION DU NORD OUEST ************ |
| BUI DIVISION ************ |  | DEPARTEMENT DU BUI ************ |
| JAKIRI COUNCIL ************ |  | COMMUNE DE JAKIRI ************ |
| JAKIRI COUNCIL INTERNAL TENDERS BOARD ************ |  | COMMISSION INTERNE DE PASSATION DES MARCHE DE LA COMMUNE DE JAKIRI |

OPEN NATIONAL INVITATION TO TENDER N° 06/ONIT/JAKIRI COUNCIL/JCITB/2026 OF 23/01/2026 FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

##### FUNDING: minee 2026 BUDGET

The Lord Mayor Jakiri Council; CONTRACTING AUTHORITY, initiates on the behalf of the Republic of Cameroon, an Open National Invitation to tender for the realization of the operation mentioned above:

- Subject of the invitation to Tender :

Within the framework of Construction/Reconstruction of Collapsed Engineering Structures, the Project Owner or Owner hereby launches an Open National Invitation to tender for the CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION.

- Nature of Works

Work to be done consists of the CONSTRUCTION OF FAAKUI WATER SCHEME in Jakiri Council Area, Bui Division. The works include the following:

- SITE INSTALLATION

- CATCHMENTS AND CHAMBERS

- DISTRIBUTION NETWORK

- PIPE LINE CONSTRUCTION

- HYDRAULIC ASSESSORIES

- IMPACT ENVIRONEMENTAL

- Tranches/Allotment:

The works are presented in One (01) lot.

- Estimated Cost :

| N° | Project Name | Estimated Cost including (TTC) in Fcfa |
| --- | --- | --- |
| 1 | Construction of Faakui Water Scheme in Jakiri- Council, Bui Division Of The North West Region. | 85,000,000 |

The estimated cost of the operation following preliminary studies is Eighty Five Million, (85,000,000) Francs CFa.

- Estimated execution deadline

The maximum time frame provided for by the Project Owner for the execution of works subject of this open national invitation to tender is Four (04) calendar months. This time frame shall run from the date of notification of the administrative order to commence the services.

- Participation And Origin Of Bidders:

Participation in this invitation to tender is open to all registered and qualified companies or groups of companies based in the Republic of Cameroon.

- FUNDING :

The Works on this tender are funded by 2026 MINEE BUDGET The previewed cost of the entire works of this Open National Invitation to tender is: Eighty Five Million, (85,000,000) Francs CFa all taxes included.

- Bidding Method :

The mode of submission selected for this consultation is offline.

- ADMINISTRATION CHARGED WITH THE SIGNING OF THE CONTRACT

After the examination of the tender documents of the various bidders, and the choice of the successful bidder by the contracting authority, the contract will be signed between the latter and the Contracting Authority who is the Lord Mayor of Jakiri Council.

- TEMPORAL BID BOND (TENDER GUARANTEE) :

The offer must include temporary caution (bid bond) which is valid for ninety (90) days from the date of bid opening and done following the sample indicated in this Tender File and issued by a financial body of first category authorized by the Minister in charge of Finance to issue bonds for public contracts. The amount of the bid bond is indicated in the table below:

| No | Amount in Figures(Fcfa) | Amount in Words (Fcfa) |
| --- | --- | --- |
| 1 | 1,000 ,000 | One million |

To avoid reject, the bid bond has to be an original copy which is less than three months.

The bid bond will released for unsuccessful bidders once the publication of the award is done. In case the bidder is attributed the contract, the bid bond will be released only when the final bond has been produced. Bank cheques (even certified) will not be accepted in place of the bid bond. The Bid bond will be validated by a receipt of deposit at CDEC.

- CONSULTATION OF TENDER FILE :

The hard copy of the file may be consulted free of charge during working hours in the services of the PO/DPO at the JAKIRI Council premises as soon as this notice is published.

- Acquisition Of The Tender File :

This receipt should be able to identify the buyer as the representative of the bidder, wishing to participate in the consultation.

The hard copy of the Tender file may be obtained from the Jakiri Council premises as soon as this notice is published against payment of a non-refundable sum of One Hundred Thousand (100,000) Francs CFA Francs, payable at the Jakiri Council Treasury.

During the acquisition of the tender file, the bidder will fill in the register indicating his complete address (PO Box, Telephone number, fax, Email).

It is equally possible to obtain the electronic version of the Tender File by downloading it free of charge through the addresses indicated above. However, online submission is subject to the payment of Tender File purchase fees.

- PRESENTATION OF THE BIDS

The bid documents will be presented in three envelopes as illustrated bellow:

The Envelope A containing Administrative documents (volume 1);

The Envelope B containing Technical documents (Volume 2);

The Envelope C containing financial documents (Volume 3).

All constituted documents (Envelopes A, B and C), will be put in a big sealed envelope bearing only the title of the Open national invitation to tender.

The various documents in each bid will be numbered in the order of the tender file and with separators of different colors other than white.

- SUBMISSION OF BIDS :

Each bid, prepared in English or in French in (07) seven copies, that is (01) one original and (06) six copies noted as such, shall be forwarded to the contracting authority, notably to the Secretariat of Jakiri Council Tenders board, situated at the JakirI Council latest the : 18/02/2026 at 10:00am local time bearing

OPEN NATIONAL INVITATION TO TENDER

N° 06/ONIT/JAKIRI COUNCIL/JCITB/2026 OF 23/01/2026

FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION To be opened only during session.

- ACCEPTABILITY OF BIDS :

Bids that will be submitted after the date and time mentioned above or those that will not respect the separation model indicated in the different documents in each bid shall not be accepted.

All the bids that are not conform to the prescriptions of this tender file shall not be accepted.

The absence of the stamped bid bond drawn up using the model proposed in the tender file and issued by a bank or an insurance company accredited to issue bonds within the framework of public contracts, valid within Ninety (90) days.

To avoid being rejected, the required Administrative documents will be imperatively produced in original or in certified true copies by the issuing service, in conformity with the stipulation of the rules and regulations of this tender.

These Administrative documents have a validity period of three (03) months. This validity period has to begin after the date of the launching of the tender.

- OPENING OF BIDS :

The opening of bids shall take place on the 18/02/2026 (PUT the date of the opening of bids)   at 11:00Am (time of opening of bids, one hour after that of the deposit), in the conference hall of the JAKIRI Council tender’s Board.

The opening of bids will be done at once and in three stages:

-	Stage 1: Opening of envelope A containing Administrative document (volume 1),

-	Stage 2: Opening of envelope B containing Technical document (volume 2)

-	Stage 3: Opening of envelope C containing financial document (volume 3).

All the bidders can take part in this opening session or can be represented by one person dully mandated (Even in case of joint-venture) who has a perfect mastery of the tender file

To avoid being rejected, the required Administrative documents will be imperatively produced in original or in certified true copies by the issuing service, in conformity with the stipulation of the rules and regulations of this tender. These Administrative documents have a validity period of three (03) months. This validity period has to begin after the date of the launching of the tender.

In case of absence or non-conformity of an administrative document during the opening session, after a deadline of 48 hours given by the commission, the offer will be rejected.

- MAIN CRITERIA OF EVALUATION OF THE BIDS :

17-1- : ELIMINATORY CRITERIA:

A-Administrative Documents

- Absence during bid opening session of original copy of bid bond issued by a first-class financial organization authorized by the Ministry of Finance to issue Bid Bonds within the framework of public Contracts; BACKED BY CDEC RECEIPT

- Non-conformity after a period of 48 hours following the deposit of bids, of at least one Administrative document;

B-Technical Documents

- Absence of the declaration by the bidder attesting that the latter has not abandoned any contract within the last three(03) years, and that he does not future in in the list of non-performant companies established by MINMAP.

- Absence of integrity chart dated and signed.

- Absence of declaration on the engagement to respect environmental clauses;

- Absence of financial capacity drafted with respect to the COBAC model issued by first class bank approved by the Minister of Finance;

| No | Amount in figures Fcfa | Amount in Words Fcfa |
| --- | --- | --- |
| 1 | 1,000,000 | One million |

- Did not validate 2/3 of the essential criteria and obligatorily the equipment criteria;

- Did not have the minimum required equipment

- A dump Truck

- Concrete Mixer

- Concrete Vibrators

- Manual compactors

- A Pick Up 4 x 4

- Absence of attestation of site visit dated, stamped and signed by the bidder;

- Absence of categorization certificate issued by MINMAP

- Proof of acceptance of clauses within the contract

C-Incomplete financial bid for absence of one of the following documents:

- Unit Price breakdown non-conform with that of the tender file ;

- The unit price schedule non-conform with that of the tender file;

- Absence of a quantified price in the financial offer;

- Absence of an element in the financial offer (the tender letter, the Unit Price Schedule, the Bill of Quantities and cost Estimates.

D-General Eliminatory Criteria:

- Absence of the soft copy of the bid or non-respect of the format for the files

- Absence of original copy of bid bond

- False déclaration, falsified documents or non authentic, fraudulent practices

17-2 : Essential criteria :

The technical bids will be evaluated according to the following ten (10) main criteria:

- Key personnel of the enterprise on three (03) criteria ;

- The site equipment to be mobilized on five (05) criteria ;

- The Enterprise references on two (02) criteria.

NB: A civil servant without any justification of secondment from the public service will not be evaluated;

- Award of contract :

The contract will be awarded to the lowest bidder, fulfilling the required administrative, technical, and financial criteria.

The Project Owner has the discretion not to award the contract to a bidder who has an ongoing contract within the zone, having non satisfactory performances (cancelled or abandoned) or a bit satisfactory (Formal notice with evaluation being unsatisfactory or a notified evaluation of noncompliance within six months of award or contract cancellation underway)

- Maximum Number of Lots:

A bidder can be attributed just one (01) lot given that the bid is for a single lot.

- Validity of Bids

The bidders remain engaged to their offer within Ninety (90) days from the submission date of the bids.

- Additional information

Additional information in relation to technical details can be obtained at the office of the contracting authority, notably The Mayor of Jakiri Council. Tel: 676 627, 995

- Fight against Corruption and Malpractices

For all reports on practice, acts of corruption or malpractice, you can contact the National Anti-Corruption Agency on 1517, Authority in charge of Public Contracts(MINMAP) (sms or call) on: (+237) 673 20 57 25 and 699 37 07 48.

Done in Jakiri: 23/01/2026

The Lord Mayor of JAKIRI Council

Copy:

- DD MINTP/MINMAP/NW

- ARMP BAMENDA

- CHAIRPERSON JAKIRI COUNCIL TENDER BOARD

- NOTICE BOARD

- FILE/CHRONO

Document 1.b

FRENCH VERSION

| REPUBLIC OF CAMEROON Peace – Work – Fatherland ************ |  | REPUBLIQUE DU CAMEROUN Paix – Travail – Patrie ************ |
| --- | --- | --- |
| MINISTRY OF DECENTRALISATION AND LOCAL DEVELOPMENT ************ |  | MINISTÈRE DE LA DÉCENTRALIZATION ET DEVELOPPEMENT AND LOCAL ************ |
| NORTH WEST REGION ************ |  | REGION DU NORD OUEST ************ |
| BUI DIVISION ************ |  | DEPARTEMENT DU BUI ************ |
| JAKIRI COUNCIL ************ |  | COMMUNE DE JAKIRI ************ |
| JAKIRI COUNCIL INTERNAL TENDERS BOARD ************ |  | COMMISSION INTERNE DE PASSATION DES MARCHE DE LA COMMUNE DE JAKIRI |

AVIS D’APPEL D’OFFRE NATIONAL OUVERTE

N° 06/AONO/COMMUNE DE JAKIRI/CIPMJ/2026 DU 23/01/2026

POUR L’EXECUTION DES TRAVAUX DE CONSTRUCTION D’UN SYSTEME D’ADDUCTION L’EAU POTABLE  DE FAAKUI DANS LE, COMMUNE DE JAKIRI, DEPARTEMENT DE BUI, REGION DU NORD-OUEST

##### FINANCEMENT: bip 2026 MINEE

Le Maire de la Commune de Jakiri; Autorité Contractante, lance pour l’état du Cameroun, un Appel d’offres National Ouverte pour l’objet mentionnées ci-dessus:

- Objet de l'Appel d'Offres

Dans le cadre de construction/ reconstruction des ouvrages d’art écoulées, le Maître d’Ouvrage ou le Maître d’Ouvrage Délégué lance un Appel d’Offres National Ouverte POUR L’EXECUTION DES TRAVAUX DE CONSTRUCTION D’UN SYSTEME D’ADDUCTION L’EAU POTABLE  DE FAAKUI.

Consistance des travaux

Les prestations du présent marché comprennent les travaux des CONSTRUCTION D’UN SYSTEME D’ADDUCTION L’EAU POTABLE  DE FAAKUI., COMMUNE DE JAKIRI, DEPARTEMENT DE BUI, REGION DU NORD-OUEST dans l’  Arrondissement de Jaki, Département de Bui.,  Les prestations comprennent les opérations suivantes :

- TRAVAUX PRELIMINAIRES ET AUTRES - CONSTRUCTION D’UN BASIN VERSANT - RESEAU DE DISTRIBUTION - PIPE LINE - ACCESSOIRES HYDRAULIC - IMPACT ENVIRONMENTAL

- Tranches/Allotissement

Les travaux sont dans un (01) seul lot.

- Coût prévisionnel

| N° | Désignation du Projet | Cout du Projet (TTC) en Fcfa |
| --- | --- | --- |
| 1 | CONSTRUCTION D’UN SYSTEME D’ADDUCTION L’EAU POTABLE DE FAAKUI. | 85,000,000 |

Le coût prévisionnel de l’opération à l’issue des études préalables est de Quatre-vingt  Millions, FCFA (85, 000,000) comme présentés ci-dessus et seront financés par le budget de MINEE 2026.

- Délai prévisionnel d’exécution

Le délai maximum prévu par le Maître d’Ouvrage ou le Maître d’Ouvrage Délégué pour la réalisation des travaux, objet du présent appel d’offres est de Quartre (04) mois calendaires. Ce délai court à compter de la date de notification de l’ordre de service de commencer les travaux.

- Participation et origine

La participation au présent appel d’offres est ouverte à tous les Entreprises Camerounaise concernées dans le Bâtiment et Travaux Publics.

- Financement

Les travaux objet du présent appel d'offres sont financés par le budget de MINEE 2026.

- Mode de soumission

##### Le mode de soumission est : «en ligne ou hors ligne ».

- Cautionnement de soumission

Les offres devront être accompagnées, d’un cautionnement provisoire (garantie de soumission) d’une durée de validité de Quatre-vingt-dix(90) jours à compter de la date initiale de remise des offres et établi selon le modèle indiqué dans le Dossier d’Appel d’Offres par un établissement financier agrée par le Ministre en charge des finances pour délivrer les cautions dans le cadre des Marchés Publics. Le montant de ladite garantie est indiqué dans le tableau ci-dessous.

| N° | Montant de la caution en chiffres FCFA | Montant de la caution en lettres FCFA |
| --- | --- | --- |
| 1 | 1,000,000 | Un million Francs cfa |

Sous peine de rejet, le cautionnement provisoire devra impérativement être produit en original datant de moins de trois (03) mois.

Le cautionnement provisoire sera libéré d’office dès publication de la Décision d’attribution pour les soumissionnaires n’ayant pas été retenus. Dans le cas où le soumissionnaire est adjudicataire du marché, le cautionnement provisoire sera libéré après constitution du cautionnement définitif. Les chèques bancaires même certifiés ne seront pas acceptés en lieu et place du cautionnement provisoire. Le cautionnement sera valide par un récépissé de dépôts à la CDEC.

- Consultation du Dossier d'Appel d'Offres

Le dossier physique peut être consulté gratuitement aux heures ouvrables à la Commune de Jakiri dès la publication de l’avis et durant les heures ouvrables.

- Acquisition du Dossier d'Appel d'Offres

La version physique du dossier d’Appel d’Offres peut être obtenue aux heures ouvrables à la Commune de Jakiri sur présentation d’une quittance de versement au trésorerie de ladite commune d’une somme non remboursable de Cent Mille (100,000) F CFA au titre des frais d’achat de dossier.

Cette quittance devra identifier l’acheteur comme représentant l’Entreprise désireuse de participer à l’Appel d’Offres.

- Remise des offres

-Pour la soumission hors ligne, l'offre en sept (07) exemplaires dont un (01) original et six (06) copies marquées comme tels, devra parvenir à la commune de Jakiri précisément au Secrétariat de la commission interne de passation du Marche située à ladite commune, au plus tard le 18/02/2026 à 10 :00AM et devra porter la mention :

AVIS D’APPEL D’OFFRE NATIONAL OUVERTE

N° 06/AONO/COMMUNE DE JAKIRI/CIPMJ/2026 DU 23/01/2026

POUR L’EXECUTION DES TRAVAUX DE CONSTRUCTION D’UN SYSTEME D’ADDUCTION L’EAU POTABLE  DE FAAKUI., COMMUNE DE JAKIRI, DEPARTEMENT DE BUI, REGION DU NORD-OUEST

A n'ouvrir qu'en séance de dépouillement"

- -Recevabilité des plis

Les offres parvenues après la date et l’heure de dépôt des offres seront irrecevables.

Toute offre non conforme aux prescriptions du présent Avis et du Dossier d'Appel d'Offres sera déclarée irrecevable. Notamment l'absence de la caution de soumission timbrée établie selon le modèle proposé dans le DAO et délivrée par une banque ou compagnie d’assurance agréée et habilitée à émettre des cautions dans le cadre des Marchés Publics, valable pendant Quatre-vingt-dix(90) jours au-delà du délai de validité des offres.

Sous peine de rejet, les pièces administratives requises devront être impérativement produites en originaux ou en copies certifiées conformes par le service émetteur, conformément aux stipulations du Règlement Particulier de l’Appel d’Offres.

Ces pièces administratives ont une durée de validité de Trois(03) mois, cette date limite de validité des pièces administratives doit être postérieure à la date de lancement de l’Appel d’Offres

- -Ouverture des plis

L’ouverture des plis se fait en un temps et aura lieu le 18/02/26 à 11am heures précises dans la salle de réunions de La commune de Jakiri

Seuls les soumissionnaires peuvent assister à cette séance d'ouverture ou s'y faire représenter par une seule personne de leur choix dûment mandatée même en cas de groupement d’entreprises.

Sous peine de rejet, les pièces du dossier administratif requises doivent être produites en originaux ou en copies certifiées conformes par le service émetteur ou l’autorité administrative compétente, conformément aux dispositions du Règlement Particulier de l’Appel d’Offres. Elles doivent dater de moins de trois (03) mois ou avoir été établies postérieurement à la date de signature de l’avis de D’Appel d’Offres

En cas d’absence ou de non-conformité d’une pièce du dossier administratif lors de l’ouverture des plis, après un délai de 48 heures accordées par la Commission, l'offre sera rejetée.

- Critères d’évaluation

  - Critères éliminatoires

- Pièces Administratives

a) Absence de l’original de la caution de soumission à l’ouverture des plis délivrée par un organisme financier de première catégorie autorisé par le Ministère chargé des Finances à émettre des cautions dans le cadre des marchés publics ; accompagniez par un reçu CDEC

b) Absence (à l’exception de la caution de soumission) après un délai de 48 heures après la notification, d’au moins une des pièces du dossier administratif.

- Offre technique incomplète pour absence de l’une des pièces ci-après :

- Absence de la déclaration sur l’honneur attestant que le soumissionnaire n’a pas abandonné un marché au cours des trois dernières années, et qu’il ne figure pas sur la liste des entreprises défaillantes établies par le MINMAP ;

- Absence d’une capacité de financement (Ligne de crédit disponible) avec un contenu conforme au modèle de la Commission Bancaire de l’Afrique Centrale (COBAC), délivrée par une banque de premier ordre agréé par le Ministre en charge des Finances au Cameroun d’au moins :

| N° | Capacité de financement en chiffres Fcfa | Capacité de financement en lettres Fcfa |
| --- | --- | --- |
| 1 | 85, 000,000 | Quatre-vingt Millions |

- N’avoir pas validé au moins 2/3 des critères essentiels avec obligatoirement le critère matériel ;

- N’avoir pas satisfait au minimum de matériel en propre requis :

- Un Camion Berne

- Betonniere

- Vibreur

- Compacteur manuel

- Un Pick Up 4x4

- Absence de l’attestation de visite des lieux datée, cachetée et signée sur l'honneur par le soumissionnaire ;

- Preuves d’acceptation des clauses du marché

- Offre financière incomplète pour absence de l’une des pièces ci-après :

- Sous-détails de prix unitaires non conformes au modèle de l’offre ;

- Bordereau de prix unitaires non conformes au modèle fourni dans le présent dossier d’Appel d’Offres ;

- Absence dans l’offre financière d’un prix quantifié.

- Absence d’un élément de l’offre financière (la soumission, les BPU, le DQE)

- Critère éliminatoire d’ordre général

- Absence de la copie de sauvegarde ou non-respect du format de fichier des offres.

- Absence de l’origine de la caution de soumission

- Fausse déclaration, documents falsifiés ou non authentique, manœuvres frauduleuses

15.2. Critères essentiels

L’évaluation des offres techniques sera faite sur la base des critères essentiels ci-dessous

- Le personnel d’encadrement ;

- Matériels ;

- Référence et Note méthodologique

NB : Un agent public sans justificatif de sa libération de la fonction publique ne sera pas évalué ;

- Attribution

Le marché sera attribué au soumissionnaire présentant l’offre la moins-disant et remplissant les capacités techniques et administratives requises.

Par ailleurs, le Maitre d’Ouvrages se réserve le droit de ne pas attribuer le marché dans le cadre du présent appel d’offres à un soumissionnaire qui, titulaire d’un contrat en cours dans la zone, a des performances non satisfaisante (résilier ou abandonné) ou peu satisfaisantes (mise en demeure dont l’évaluation a été jugée non satisfaisante ou constate de défaillance notifiée dans les six mois précédent l’attribution ou contrat en cours de résiliation).

- Nombre maximum de lots :

##### Un candidat peut soumissionner pour un seul lot.

- Durée de validité des offres

##### Les soumissionnaires restent engagés par leur offre pendant Quatre-vingt-dix(90) jours à partir de la date limite initiale fixée pour la remise des offres.

- Renseignements complémentaires

##### Les renseignements complémentaires peuvent être obtenus aux heures ouvrables consultées à la Commune de Jakiri à Tél. : 676627995

##### .

- Lutte contre la corruption et les mauvaises pratiques

Pour toute dénonciation pour des pratiques, faits ou actes de corruption ou faits de mauvaises pratiques, bien vouloir appeler la CONAC au numéro 1517, l’Autorité chargée des Marchés Publics (MINMAP) (SMS ou appel) aux numéros : (+237) 673 20 57 25 et 699 37 07 48

Fait à Jakiri : 23/01/2026

Le Maire de la Commune de JAKIRI

Copy:

- DD MINTP/MINMAP/NW

- ARMP BAMENDA

- CHAIRPERSON JAKIRI COUNCIL TENDER BOARD

- NOTICE BOARD

- FILE/CHRONO

Document No. 2:

General Regulations of the Invitation to Tender

CONTENT

A. Generalities. . . . . . ……………………………………………………………………………..

| Article 1 | : The scope of the Tender . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| --- | --- | --- |
| Article 2 | : The Funding . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 3 | : Fraud and corruption . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 4 | : Candidates eligible to tender . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 5 | : Materials, tools, supply, equipments and authorized services . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 6 | : Qualification of the bidder. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 7 | : Works site visit . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |

B. tender Document . . .	………………………………………………………………

| Article 8 | : Content of tender document . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| --- | --- | --- |
| Article 9 | : Clarifications made on the tender document and request . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 10 | : Modification of the tender file . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |

C. Préparation of Bids.	………………………………………………………………

| Article 11 | : Tender fee . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| --- | --- | --- |
| Article 12 | : Language of the bids. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 13 | : The Documents constituting the Bids . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 14 | : Amount of the tender . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 15 | : Currency used for tender and payments . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 16 | : Validity of tender. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 17 | : Bid bond (tender bank guarantee) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 18 | : Various proposal of bidders . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 19 | : Preparatory Meetings towards the establishment of bids. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 20 | : Form and signing of bids . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |

D. Deposit of bids... .	………………………………………………………………………

| Article 21 | : Stamping and noting of bids . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| --- | --- | --- |
| Article 22 | : Latest date and time of deposit of bids . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 23 | : Late deposited bids . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 24 | : Modification, substitution and withdrawal of bids . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |

E. Opening and evaluation of Bids . . .	………………………………………

| Article 25 | : Opening of bids and request if any . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| --- | --- | --- |
| Article 26 | : The confidential nature of the procedure . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 27 | : Clarifications on the Bid and contact with the delegated Contracting Authority . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 28 | : Détermination of the conformity of bids. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 29 | : Qualification of the bidder. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 30 | : Correction of errors . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 31 | : Conversion into a unique currency . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 32 | : Financial Evaluation of bids. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 33 | : Preference given to national bidders . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |

F. Award of Contract.	………………………………………………………………

| Article 34 | : Award of contract . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| --- | --- | --- |
| Article 35 | : The right of the delegated Contracting Authority to declare an invitation to tender, unfruitful or to cancel the procedure |  |
| Article 36 | : Notification of the award of contract . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 37 | : Publication of the result of the award of the contract and request if any . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 38 | : Signing of the contract . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |
| Article 39 | : Final Bid Bond . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |

General Regulations of the invitation to tender

A. General

Article 1: Scope of offer

The Lord Mayor of JAKIRI Council, Contracting Authority, launches on behalf of the Republic of Cameroon, an open national invitation to tender for THE CONSTRUCTION OF A PERMANENT BRIDGE OVER RIVER KILENDZEV LINKING VEKOVI-TARSHEM-TADU-KUMBO IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

FUNDING: BIP MINDDEVEL 2026

  - The bidders retained, must complete the works within the required period as indicated in the specific rules of the tender document (SRTD), except there is a contrary stipulation in the special administrative document that starts from the date of notification of the service order to start works or of that indicated in the service order.

  - The word « Day » in this tender document signifies a calendar day.

Article 2: Financing

The sources of funding of works in this tender document have been indicated in the (SRTD)

Article 3: Fraud and corruption

- The Contracting Authority requires of bidders and their contractors the strict respect of rules of professional ethics during the award and execution of public contracts. By virtue of this principle, the CONTRACTING AUTHORITY:

a) Defines, within the context of this clause, the following expressions in the

Following manner:

- Shall be guilty of “corruption” whoever offers, gives, requests or accepts any advantage in view of influencing the action of a public official during the award or execution of a contract;

- Is involved in “fraudulent manoeuvres” whoever deforms or distorts facts in order to influence the award or execution of a contract;

- “collusive practices” mean any form of agreement between two or among several bidders (whether the Contracting Authority is aware or not) aimed at artificially maintaining the prices of offers at levels not corresponding with those which will result from the forces of competition;

- “coercive practices” mean any form of harm against persons or their property or threats against them in order to influence their action during the award or execution of a contract;

- Conflict of interest shall mean any situation in which the financial or personal interest of an agent or public entity is likely to compromise transparency in the award of public contracts.

- The Contracting Authority shall reject any award proposal if it determines that the proposed successful bidder is directly or through the intermediary of an agent, guilty of corruption or is involved in fraudulent manoeuvres, collusive or coercive practices in the award of this contract.

3.2 The Minister Delegate at the Presidency of the Republic in charge of Public Contracts may, as a temporary measure, take a decision to ban bidding for a period not exceeding two (2) years against any bidder guilty of influence peddling, conflict of interest, insider information, fraud, corruption, or production of non-authentic documents in his offer, without prejudice to legal action that may be taken against him.

Article 4: Candidates allowed competing

4.1 If the invitation to tender is restricted, consultation is addressed to all candidates retained after a pre-qualification procedure.

4.2   Generally, the invitation to tender is addressed to all contractors, subject to the following provisions:

- a bidder (including all members of a group of enterprises and all sub-contractors to the bidder) must be from an eligible country, in accordance with the funding agreement.

(b)a bidder (including all members of a group of enterprises and all sub-contractors to the bidder) must not be in a situation of conflict of interest.

A bidder shall be judged to be in a situation of conflict of interest if he:

- is or was associated in the past in an enterprise (or a subsidiary of this enterprise) which provided consultancy services for the conception, preparation of specifications and other documents used within the scope of contracts awarded for this invitation to tender; or

- Presents more than one bid within the context of this invitation to tender, except authorised variants according to article 17, where need be; meanwhile, this does not prevent the participation of sub-contractors in more than one bid.

- The project owner is not a shareholder of any bidder so as to compromise the process of award of the contract.

(c) The bidder must not have been excluded from bidding for public contracts.

(d)  A Cameroonian public enterprise may participate in the consultation if it can demonstrate that it is (i) legally and financially autonomous, (ii) managed according to commercial laws and (iii) not under the direct or indirect supervisory authority of the Contracting Authority.

Article 5: Supplies and ancillary services meeting the criteria of origin

5.1 All supplies and ancillary services forming the subject of this contract must come from countries meeting the criteria of origin defined in the Special Regulations of the invitation to tender.

5.2 Within the meaning of the clause 5.1, the term “works” shall refer to products, raw materials, machines, equipment and industrial installations; and the term “ancillary services” shall notably refer to services such as insurance, installation, training and initial maintenance.

5.3 The term “originate” shall qualify the country where the supplies are extracted, cultivated, produced, manufactured or transformed; or the country where a manufacturing, transformation or assembly of components process results in the abstention of a commercial article whose basic characteristics are substantially different from those of its components.

Article 6: Qualification of bidder

6.1 As an integral part of their offer, bidders must:

(a)  Submit a power of attorney making the signatory of the bid bound by the offer; and

(b)  furnish all the information (to complete or update the information included in the request for pre-qualification which may have changed in the case where the candidates had to pre-qualify) requested from bidders in the Special Regulations, in order to establish their ability to execute the contract; furnish all the information (or update the information included in their request for pre-qualification which may have changed) requested from the bidders in order to establish their ability to execute the contract.

Information relating to the following points shall be requested, if need be:

- The production of certified balance sheets and recent turnover;

- access to a credit line or availability of other financial resources;

- orders acquired and contracts awarded;

- pending litigations; and

- Availability of indispensable equipment.

6.2   Bids presented by two or more associated undertakings (joint-contracting) must satisfy the following conditions:

- The bids must include all the information listed in article 6(1) above. The Special Regulations must specify the information to be furnished by the group and the information to be furnished by each member of the group;

- The offer and the contract must be signed in a way that is binding on all members of the group;

- The nature of the group (joint or several) must be specified and justified with the production of a joint venture agreement in due form;

- The member of the group designated as the representative shall represent all the undertakings vis à vis the Contracting Authority in the execution of the contract.

- In case of joint co-contracting, the co-contractors shall share the sums which are paid by the Administration into a single account; on the other hand, each undertaking is paid in its own account by the Administration where it is several co-contracting.

6.3 Bidders should equally present sufficiently detailed proposals to demonstrate that they conform to the technical specifications and execution time limits set in the Special Regulations of the invitation to tender.

6.4 Bidders seeking to benefit from a margin of preference must furnish all the information required to prove that they meet the eligibility criteria described in article 35 of the General Regulations.

Article 7: Visit of the work site

7.1. The bidder is advised to visit and inspect the site of works and its surroundings and to obtain by himself, and under his own responsibility, all the information that may be necessary for the preparation of the tender and the work execution. The costs related to the visit of the site are the responsibility of the Bidder.

7.2. the Contracting Authority is obliged to authorize the Bidder who so requests and his employees or agents to enter his premises and grounds for the purpose of the said visit, but only on the express condition that the Bidder, its employees and agents release the Owner, his employees and agents from any liability that may result and compensate them if necessary, and that he remains responsible for fatal or personal accidents, loss or damage to property, costs and expenses incurred as a result of this visit.

7.3. The Contracting Authority may organize a visit to the site of works at the time of the preparatory meeting for the preparation of the bids mentioned in article 19 of the GRIT

B. Tender File

Article 8: Content of Tender File

8.1 The Tender File describes the works forming the subject of the contract, sets the consultation procedure by contractor and specifies the terms of the contract.  Besides the addenda published in accordance with article 9 of the General Regulations of the invitation to tender, it includes the following documents:

| Document No. 1 | The tender notice in English and French signed by the Delegated Contracting Authority |
| --- | --- |
| Document No. 2 | The General Regulations of the invitation to tender which has model clauses that are not to be modified; |
| Document No. 3 | The Special Regulations of the invitation to tender containing provisions of documents No. 2 which should be completed or specified within the context of the invitation to tender concerned |
| Document No. 4 | The Special Administrative Conditions which deal with the execution of the contract and the related payments; |
| Document No. 5 | The technical specification |
| Document No. 6 | The framework of Unit Price Schedule; |
| Document No. 7 | The framework of bill of Quantities and cost estimates |
| Document No. 8 | Framework of breakdown of unit price; |
| Document No. 9 | Draft contract; - The planning of exécution - Model form for presentation of equipment, personnel, and references ; - Model of tender letter; - Model of tender bond; - Model of final bond; - Model of startup advance; - Model of retention guarantee bond |
| Document No. 10 | Models to be used by bidders; |
| Document No. 11 | Justifications of preliminary studies to be filled by the Project Owner or Delegated Project Owner; |
| Document No. 12 | List of first-rate banking establishments and financial bodies approved by the Ministry in charge of finance authorised to issue bonds for public contracts |

8.2 The bidder must examine all the rules, forms, conditions and specifications contained in the Tender file. It is up to him to furnish all the information requested and prepare a bid in conformity with all aspects of the said file. Any deficiency may lead to a rejection of his bid.

Article 9: Clarifications on the Tender File

9.1 Any bidder who wants to obtain clarifications on the Tender File may request them from the Contracting Authority in writing or by electronic mail (telecopy or e-mail) at the Contracting Authority’s address indicated in the Special Regulations of the invitation to tender. The Delegated Contracting Authority shall reply in writing to any request for clarification received at least fourteen (14) days for national invitations to tender and twenty-one (21) days for international invitations prior to the deadline for the submission of the offers.

A copy of the Contracting Authority’s response, indicating the question posed but not mentioning the author, is addressed to all bidders who bought the Tender File.

9.2 Between the publication of the tender notice including the pre-qualification phase of candidates and the opening of bids, any bidder who feels aggrieved in the public contracts award procedure may lodge a complaint to the Contracting Authority.

9.3 The complaint must be addressed to the Contracting Authority with copies to the body in charge of the regulation of public contracts and the chairperson of the Tenders Board.

It must reach the Contracting Authority not later than fourteen (14) days before the opening of bids.

9.4 The Contracting Authority has five (5) days to react. A copy of the reaction shall be forwarded to the body in charge of the regulation of public contracts.

Article 10:  Amendment of the Tender File

10.1 The Contracting Authority may at any moment prior to the deadline for the submission of offers and for any reason, be it at his initiative or in reply to a request for clarification formulated by a bidder, amend the Tender File by publishing an addendum.

10.2 Any published addendum shall be an integral part of the Tender File, in accordance with article 8.1 of the General Regulations of the invitation to tender and must be communicated in writing or made known to all bidders who bought the Tender File. The latter must acknowledge receipt of each of the addenda in writing to the Contracting Authority.

10.3  In order to give bidders sufficient time to take account of the addendum in the preparation of their bids, the Contracting Authority may postpone as is necessary, the deadline for the submission of bids, in accordance with provisions of article 23.3 of the General Regulations of the invitation to tender.

C. Preparation of bids

Article 11: Tender fees

The candidate shall bear the costs related to the preparation and presentation of his bid and the Contracting Authority shall in no case be responsible for these costs nor pay them whatever the evolution or outcome of the invitation to tender procedure.

Article 12: Language of bid

The bid as well as any correspondence and all documents concerning the bid exchanged between the bidder and the Contracting Authority shall be drafted in English or French. Complementary documents and the forms provided by the bidder may be drafted in either language on condition that a precise translation into either English or French of the passages concerning the bid is included; in which case and for reasons of interpretation of the bid, the translation shall be considered to be authentic.

Article 13: Constituent documents of the bid

13.1 The bid presented by the bidder shall include the documents detailed in the Special Regulations of the invitation to tender, duly filled and put together in three volumes:

- Volume 1: Administrative file

It includes:

- all documents attesting that the bidder:

-  has subscribed to all declarations provided for by the laws and regulations in force;

- paid all taxes, duties, contributions, fees or deductions of whatever nature;

-  is not winding up or bankrupt;

-  is not the subject of an exclusion order or forfeiture provided for by the law in force;

ii)  The bid bond established in accordance with the provisions of article 19 of the General Regulations of the invitation to tender;

iii) the written confirmation empowering the signatory of the bid committing the bidder, in accordance with the provisions of article 6.1 the General Regulations of invitation to tender.

- Volume 2: Technical bid

b.1 Information on qualifications

The Special Regulations of the invitation to tender specify the documents to be furnished by the bidders attesting to the qualification to bid in accordance with articles 6(1), 6(2) and 18 of the General Regulations.

b.2 Technical proposals

The Special Regulations specify the constituent elements of the technical proposals of bidders notably:

    - A detailed description of the technical specifications, performance, makes, models and references of the materials proposed including technical prospectuses in accordance with article 17 of the General Regulations;

    - The calendar, schedule and execution deadline.

b.3   Proof of acceptance of conditions of the contract

The bidder shall submit duly initialled copies of administrative and technical documents relating to the contract, namely:

- The Special Administrative Conditions (SAC);

- Technical specifications.

- Volume 3: Financial bid

The Special Regulations specify the elements that will help in justifying the cost of the services, namely:

- The signed and dated original bid prepared according to the attached model, stamped at the prevailing rate;

- The duly filled Schedule of Unit Prices;

- The duly filled detailed estimate;

- The sub-details of prices and/or breakdown of all-in prices;

- The previewed payment schedule in case:

To this effect, bidders should use the model documents and forms provided for in the Tender File, subject to the provisions of article 17(2) of the General Regulations of invitation to tender concerning the other possible forms of bid bond.

13.2    If in accordance with the provisions of the Special Regulations of invitation to tender, the bidders present bids for several lots of the same invitation to tender, they could indicate rebates offered in case of award of more than one lot.

Article 14:  Amount of the bids

14.1   The general model conditions of prices shall be governed by rules prescribed in the latest edition of Incoterms published by the International Chamber of Commerce at the date of specified in the Special Regulations.

14.2   The bidder shall filled Prices as required in the model of price schedules furnished in annex.

14.3. Except as otherwise provided in the the General Regulations and Special Regulations, all rights and taxes payable by the Bidder under the future Contract, or otherwise, thirty (30) days prior to the deadline for submission of bids will be included in the price and in the total amount of its offer.

14.4. If the price revision and / or discounting clauses are provided for in the contract, the date of establishment of the initial prices, as well as the procedures for revising and / or updating said prices must be specified. It being understood that any Contract whose execution period is not more than one (1) year cannot be subject to a price revision.

14.5. All unit prices with quantities must be justified by sub-details established in accordance with the framework proposed in Exhibit THE TENDER FILE.

Article 15: Currency of bid

15.1. In the case of International Competitive Bids, the currencies of the bid must follow the provisions of either Option A or Option B below; the applicable option being that used in the Special Regulations.

15.2. Option A: The bid amount is denominated entirely in national currency. The bid price, the unit price of the price schedule and the estimated and quantitative retail prices are denominated entirely in CFA francs as follows:

a). Prices will be fully denominated in the national currency. The bidder who intends to incur expenses in other currencies for carrying out the Works, shall indicate in the Annex to the tender the percentage or percentages of the amount of the tender necessary to cover the needs in foreign currencies, not exceeding a maximum of three currencies. member countries of the market financing institution.

b). The exchange rates used by the Bidder to convert its bid into the national currency will be specified by the bidder as an appendix to the bid in accordance with the details of the RPAO. They will be applied for any payment under the Contract, so that no exchange risk is borne by the successful Bidder.

15.3. Option B: The bid amount is directly denominated in national and foreign currencies at the rates set out in the Special Regulations.

The bidder will quote the unit prices of the price schedule and the prices of the Quantitative and Estimated Detail as follows:

a). The prices of the inputs required for the Works that the Bidder intends to obtain in the country of the Contracting Authority shall be expressed in the currency of the country of the Contracting Authority specified in the Special Regulations and called "national currency".

b). The prices of the inputs required for the Works that the bidder intends to procure outside the country of the Contracting Authority shall be in the currency of the country of the bidders or that of an eligible Member State widely used in international trade.

15.4. The Contracting Authority may require bidders to express their needs in national and foreign currencies and to justify that the amounts included in the unit and total prices, and indicated in the annex to the tender, are reasonable; for this purpose, a detailed statement of its requirements in foreign currencies will be provided by the bidders.

15.5. During the execution of the works, most foreign currencies remaining to be paid on the contract price may be reviewed by agreement between the Contracting Authority and the contractor to take account of any changes in requirements. in foreign currency under the contract.

Article 16:  Validity of bids

16.1 Bids must remain valid during the period stated in the Special Regulations from the date of submission of the offers set by the Contracting Authority in application of article 23 of the General Regulations.  A bid valid for a shorter period shall be rejected by the Contracting Authority or Contracting Authority as not being in conformity.

16.2 Under exceptional circumstances, the Contracting Authority may request the consent of the bidder for the prolongation of the validity time-limit.  The request and the responses that will be given shall be in writing (or by telecopy).  The validity of the bid bond provided for in article 19 of the General Regulations shall equally be extended for a corresponding duration.  A bidder may refuse to extend the validity of his bid without losing his bid bond.

A bidder who consents to an extension shall not be asked to modify his bid nor be authorised to do so.

16.3 Where the contract does not include a price revision clause and that the period of validity of offers is extended for more than sixty (60) days, the amounts payable to the bidder retained shall be updated by application of the related formula featuring in the request for extension that the Contracting Authority shall address to bidders.

The Contracting Authority’s request must include a form of price revision. The updating period shall run from the date of overrun of the sixty (60) days to the date of notification of the contract or the Administrative Order for start of execution of services by the retained bidder, as specified in the Special Administrative Conditions. The effect of updating shall not be taken into account for purposes of evaluation.

Article 17: Bid bond

17.1   In application of article 13 of the General Regulations, the bidder shall furnish a bid bond of the amount specified in the Special Regulations and which shall become a full part of his offer.

17.2    The bid bond must conform to the model presented in the Tender File; other models may be authorised subject to the prior approval of the Contracting Authority. The bid bond will remain valid for thirty (30) days beyond the original date set for the validity of bids or any other validity time-limit requested by the Contracting Authority and accepted by the bidder, in accordance with article 20(2) of the General Regulations.

17.3   Any bid without an acceptable bid bond shall be rejected by the Contracting Authority as not being in conformity.  The bid bond of associated enterprises must be established in the name of the representative submitting the bid and should mention each member of the associated grouping.

17.4    The bid bonds of bidders who are not retained shall be returned within fifteen (15) days after publication of the award result.

17.5   The bid bond of the successful bidder shall be released as soon as the latter would have signed the contract and furnished the required final bond.

17.6    The bid bond may be seized:

a)  if the bidder:

i)  withdraws his bid during the time-limit which he specified in his bid;

ii)  does not accept the correction of errors in application of article 30(4) of the General Regulations; or

b)  if the bidder retained:

i) defaults in his obligation to sign the contract in application of article 42 of the General Regulations; or

ii) defaults in his obligation to furnish the final bond in application of article 43 of the General Regulations.

Article 18: Variant proposals from bidders

18.1. Where the work can be performed in variable turnaround times, the special Regulations will specify these times, and indicate the method used to assess the Bidder's proposed completion time within the specified time frame. Bids offering deadlines beyond those specified will be considered non-compliant.

18.2. Except in the case mentioned in Article 18.3 below, bidders wishing to offer technical variants must first encrypt the basic solution of the Contracting Authority as described in the Tender Documents, and provide in addition, all the information that the developer needs to complete the evaluation of the proposed variant, including plans, calculation notes, technical specifications, price sub-details and proposed construction methods, and all other useful details. The developer will only examine the technical variants, if any, of the bidders whose bid in accordance with the basic solution has been evaluated as the lowest bidder.

18.3. When bidders are permitted, subject to the special Regulations, to submit technical variants directly for certain parts of the work, these parts of the work must be described in the Technical Specifications. Such variants will be evaluated according to their merit in accordance with the provisions of Article 32.2 (g) of the general Regulations.

Article 19: Preparatory meeting for the preparation of bids

19.1. Unless the special Regulations provides otherwise, the Bidder may be invited to attend a preparatory meeting to be held at the place and date indicated in the special Regulations.

19.2. The purpose of the preparatory meeting will be to provide clarification and answers to any questions that may be raised at this stage.

19.3. The Bidder is requested, as far as possible, to submit any questions in writing so that it reaches the project owner at least one week before the preparatory meeting. The project owner may not be able to answer questions received too late during the meeting. In this case, questions and answers will be sent according to the terms of Article 19.4 below.

19.4. The minutes of the meeting, including the text of the questions asked and answers given, including responses prepared after the meeting, will be sent without delay to all those who have purchased the Tender Documents. Any modification of the tender documents listed in Article 8 of the General Agreement that may be necessary at the end of the preparatory meeting will be made by the Contracting Authority by issuing an addendum in accordance with the provisions of Article 10 of the General Regulations; the minutes of the preparatory meeting cannot take place.

19.5. The fact that a bidder does not attend the pre-bid meeting will not be grounds for disqualification.

Article 20:  Form and signature of the bid

20.1 The bidder shall prepare an original of the constituent documents described in article 12 of the General Regulations in a volume clearly indicated “ORIGINAL”. In addition, the bidder shall submit the number required in the General Regulations, bearing “COPY”. In case of discrepancy, the original shall be considered as authentic.

20.2 The original and copies of the bid must be typed or written in indelible ink (photocopies shall be accepted in the case of copies) and must be signed by the person(s) duly empowered to sign on behalf of the bidder, in accordance with article 6(1a) or 6(2c) of the General Regulations, as the case may be.

All the pages of the offer containing alterations or changes must be initialled by the signatory (ies) of the bid.

20.3 The bid shall bear no modification, suppression or alteration, unless such corrections are initialled by the signatory (ies) of the offer.

D.  Submission of bids

Article 21:  Sealing and marking of bids

21.1 The bidder shall place the original and each of the copies of the bid in separate and sealed envelopes bearing the inscription “ORIGINAL” and “COPY”, as the case may be. These envelopes should then be placed in another envelope which should equally be sealed and which provides no indication on the identity of the bidder.

21.2 The external and internal envelopes:

- should be addressed to the Contracting Authority at the address indicated in the Special Regulations;

- should bear the name of the project as well as the subject and number of the invitation to tender indicated in the Special Regulations and the inscription

“TO BE OPENED ONLY DURING THE BID-OPENING SESSION”.

21.3 The internal envelopes should equally carry the name and address of the bidder in a way as to enable the Contracting Authority return the sealed offer if it is not opened.

21.4 If the external envelopes are not sealed and marked as indicated in article 21(1) and 21(2) above, the Contracting Authority shall not be responsible if the bid is misplaced or opened prematurely.

Article 22: Date and time limit for submission of bids

22.1 The bids must be received by the Contracting Authority at the address specified in article 21(2) of the Special Regulations not later than the date and time stated in the Special Regulations of the invitation to tender.

22.2 The Contracting Authority may, at his discretion, postpone the deadline set for the submission of the bids by publishing an addendum in accordance with the provisions of article 9 of the General Regulations.  In this case, all the rights and obligations of the Contracting Authority and bidders previously governed by the initial date will henceforth be governed by the new date.

Article 23: Late bids

Any bid received by the Contracting Authority beyond the deadline for the submission of bids set by the Contracting Authority in application of article 22 of the General Regulations shall be declared late and consequently rejected.

Article 24:  Modification, substitution and withdrawal of bids

24.1 A bidder may modify, replace or withdraw his bid after submitting it, on condition that the written notification of the modification or withdrawal is received by the Contracting Authority prior to the end of the time-limit prescribed for the submission of bids. The said notification must be signed by an authorised representative in application of article 21(2) of the General Regulations.

The modification or the corresponding replacement offer must be attached to the written notification. As the case may be, the envelopes must bear the inscription “WITHDRAWAL”, and “REPLACEMENT BID” or “MODIFICATION”.

24.2 The notification of modification, replacement or withdrawal should be prepared, sealed, marked and forwarded in accordance with the provisions of article 22 of the General Regulations. The withdrawal may equally be notified by telephone but should, in this case, be confirmed by a duly signed written notification whose date, post mark being authentic, must not be posterior to the time-limit set for the submission of offers.

24.3 Bids being requested to be withdrawn in application of article 25(1) shall be returned unopened.

24.4 No bid may be withdrawn in the interval between the deadline set for the submission of bids and the expiry of the validity period of the bids set in the model bid. The withdrawal of a bid by a bidder during this interval may lead to the confiscation of the bid bond in accordance with the provisions of article 19(6) of the General Regulations.

E.  Opening of envelopes and evaluation of bids

Article 25: Opening of envelopes and petitions

25.1 The competent Tenders Board shall open the envelopes in single or two phases in the presence of the representatives of bidders who wish to attend and who have a perfect mastery of the file, at the date, time and address specified in the Special Regulations. Representatives of bidders present shall sign a register attesting to their presence. A single phase opening shall be appropriate where the qualification criteria are easily applicable.

25.2 Firstly, envelopes marked “withdrawal” shall be opened and the contents announced to the hearing of everyone, while the envelope containing the corresponding bid shall be returned to the bidder unopened. Withdrawal of a bid shall be allowed only if the corresponding notification contains a valid empowerment of the signatory to request this withdrawal and if this notification is read to the hearing of everyone. Then the envelopes marked “Replacement offer” are opened and announced to the hearing of everyone and the new corresponding bid substituted for the preceding one which will be sent to the bidder concerned unopened.

The replacement of a bid shall only be allowed if the corresponding notification contains a valid empowerment of the signatory requesting the replacement and read to the hearing of everyone. Lastly, the envelopes marked “modification” shall be opened and their contents read to the hearing of everyone with the corresponding bid. The modification of the bid shall only be allowed only if the corresponding notification contains a valid empowerment of the signatory requesting the modification and read to the hearing of everyone. Only bids which were opened and announced to the hearing of everyone during the opening of bids shall then be evaluated

25.3 All envelopes shall be opened successively and the name of the bidder announced aloud as well as the possible modification mentioned, the price offered, including any rebates [in case of opening of financial bids] and any variant, where necessary, the existence of a guarantee of the bid if it is required and any other details which the Contracting Authority deems useful to be mentioned. Only rebates and variants of bids announced to the hearing of everyone during the opening of bids shall be submitted for evaluation.

25.4 Bids (and modifications received in accordance with the provisions of article 24 of the General Regulations) which were not opened and read to the hearing of everyone during the bid-opening session for whatever reason, shall not be submitted for evaluation.

25.5 Bid-opening minutes are recorded on the spot mentioning the admissibility of bids, their administrative regularity, prices, rebates and time-limits as well as the composition of the Evaluation sub-committee. A copy of the said minutes to which is attached the attendance sheet is handed over to all the participants at the end of the session.

25.6 At the end of each bid-opening session, the chairperson of the Tenders Board immediately hands over to the focal point designated by ARMP an initialled copy of the bids presented by bidders and a copy to MINMAP for files requiring his prior endorsement.

25.7 In case of petition as provided for by the Public Contracts Code, it should be addressed to the Minister Delegate at the Presidency of the Republic in charge of Public Contracts  with copies to the body in charge of the regulation of public contracts, the head of structure to which is attached the Tenders Board concerned.

It must reach within a maximum deadline of three (3) working days after the opening of bids in the form of a letter to which is obligatorily attached a sheet of the petition form duly signed by the petitioner and possibly by the chairperson of the Tenders Board.

The Independent Observer must attach to his report the sheet that was handed to him, including any related commentaries or observations.

Article 26: Confidential nature of the procedure

26.1 No information relating to the examination, evaluation, comparison of bids and verification of the qualification of bidders and the contract award recommendation shall be given to bidders or to any other person concerned with the said procedure as long as the contract award has not been made public.

26.2 Any attempt by a bidder to influence the Tenders Board or the Evaluation sub-committee of the bids or the Contracting Authority in his award decision may cause the rejection of his bid.

26.3 Notwithstanding the provisions of article 26(2), between the opening of envelopes and the award of the contract, if a bidder wishes to enter into contact with the Contracting Authority for reasons having to do with his bid, he should do so in writing.

Article 27: Clarifications on the bids and contact with the Contracting Authority

27.1 To ease the examination, evaluation and comparison of bids, the Tenders Board may, if it desires, request any bidder to give clarifications on his bid. This request for clarification and the response given are formulated in writing but no change on the amount or content of the bid is sought, offered or authorised, except it is necessary to confirm the correction of calculation errors discovered by the Evaluation sub-committee during the evaluation in accordance with the provisions of article 32 of the General Regulations.

27.2 Subject to the provisions of paragraph 1 above, bidders shall not contact members of the Tenders Board and the Evaluation sub-committee for questions related to their bids, between the opening of envelopes and the award of the contract.

Article 28: Conformity of bids

28.1 The Evaluation sub-committee shall carry out a detailed examination of bids to determine if they are complete, if the required guarantees are furnished, if the documents were correctly signed and if generally the bids are in proper order.

28.2 The Evaluation sub-committee shall determine if the bid is essentially in conformity with the conditions fixed in the Tender File based on the content without recourse to external elements of proof.

28.3 A bid that conforms to the Tender File shall essentially be a bid that respects all the terms, conditions and specifications of the Tender File, without substantial divergence or reservation.  A substantial divergence or omission is that:

- which substantially limits the scope, quality or performance of the supplies and ancillary services specified in the contract;

- which substantially limits and is not in conformity with the Tender File, the rights of the Contracting Authority or the obligations of the bidder in relation to the contract; or

- whose acceptance would be prejudicial to other bidders who presented bids that essentially conformed with the Tender File.

28.4   If a bid is essentially not in compliance, it shall be rejected by the competent Tenders Board and shall not eventually be rendered in compliance.

28.5   The Contracting Authority reserves the right to accept or reject any modification, divergence or reservation. Modifications, divergences, variants and other factors which are beyond the requirements of the Tender File shall not be considered during the evaluation of bids.

Article 29: Qualification of the bidder

The Evaluation sub-committee shall ensure that the bidder retained for having submitted the bid that substantially conformed to the provisions of the Tender File, meets the qualification criteria stipulated in article 6 of the Special Regulations. It is essential to avoid arbitrariness in determining qualification.

Article 30: Correction of errors

30.1   The Evaluation sub-committee shall verify the bids considered essentially in   conformity with the Tender File to rectify the possible calculation errors. The sub-committee shall rectify the errors in the following manner:

a)  If there is a contradiction between the unit price and the total obtained by multiplying the unit price by the quantities, the unit price shall be authentic and the total price shall be corrected, unless, according to the Evaluation sub-committee, the decimal point of the unit price is manifestly badly placed. In which case the total price indicated shall prevail and the unit price corrected.

- If the total obtained by the addition or subtraction of sub totals is not exact, the sub totals shall be authentic and the total corrected;

30.2. The amount in the Submission will be corrected by the Subcommittee of Analysis in accordance with the aforementioned error correction procedure and, with the Bidder's confirmation, said amount will be deemed to be binding.

30.3. If the Bidder submitting the lowest evaluated bid fails to accept the corrections made, the bid will be rejected and the bid secured.

Article 31: Conversion into a single currency

31.1   To facilitate the evaluation and comparison of bids, the Evaluation sub-committee shall convert the prices expressed in various currencies into an amount in which the bid is payable in CFA francs.

31.2 The conversion shall be done using the current exchange rate set by BEAC in force at the deadline for submission of bids under the conditions set in the Special Regulations.

Article 32: Financial evaluation of bids

32.1 The Evaluation sub-committee shall proceed to the evaluation and comparison of bids which it had determined essentially met the provisions of the Tender File within the meaning of articles 30,  31 and 32 of the General Regulations.

32.2   For this evaluation the Evaluation sub-committee shall consider the following elements:

- the bid price, indicated according to the provisions of article 30.2 of the General Regulations;

- adjustments made on the price to correct the arithmetical errors in application of article 32(3) of the General Regulations;

- adjustments made on the price as a result of rebates offered in application of paragraph 31.2 of the General Conditions;

- By appropriately adjusting, on a technical or financial basis, any other modification, divergence or quantifiable reserve;

- Taking into consideration the different lead times proposed by the bidders, if they are authorized by the special Regulations;

- If applicable, in accordance with the provisions of Article 13.2 of the General Regulations and special Regulations, applying the discounts offered by the Bidder for the award of more than one lot, if this call for tenders is issued simultaneously for several lots.

- Where applicable, in accordance with the provisions of section 18.3 of the special Regulations and the Technical Specifications, the proposed technical variants, if permitted, will be evaluated according to their merit and regardless of whether or not the Bidder will have bid for the award. Technical solution specified by the Owner in the RPAO.

32.3. The estimated effect of the price revision formulas in the “CCAGs” and “CCAPs”, applied during the period of performance of the Contract will not be taken into account in the evaluation of the tenders.

32.4. If the lowest evaluated bid is found to be abnormally low or is significantly out of balance with the Owner's estimate of the work to be performed under the Contract, the commission may from the price sub-detail provided by the bidder for any element, or for all elements of the Quantitative and Estimated Detail, check whether these prices are compatible with the construction methods and the proposed schedule. In the event that the evidence submitted by the bidder does not seem satisfactory to him, the Employer may reject the tender after the technical opinion of the Public Contracts Regulation board.

Article 33: Margin of preference

If this provision is mentioned in the Special Regulations, national businesspersons may benefit from a national preference margin as provided for in the Public Contracts Code for reasons of evaluation of the bids.

F. Award of the contract

Article 34: Award of the contract

34.1    The  Contracting Authority shall award the contract to the bidder whose offer was judged essentially in conformity with the Tender File and who has the required technical and financial capacities to execute the contract satisfactorily and whose bid was evaluated as the lowest by including, where necessary, proposed rebates.

34.2     If the invitation to tender has several lots, the lowest bid shall be determined by evaluating this contract in relation with the other lots to be awarded concurrently, by taking into consideration the rebates offered by the bidders in case of award of more than one lot, as well as their financial situation at the time of award.

34.3 Any award of Works contracts shall be made to the Bidder fulfilling the technical and financial capacities required as a result of the evaluation criteria and presenting the bid evaluated as the lowest bidder.

Article 35:  The right by the Contracting Authority to declare an invitation to tender unsuccessful or cancel a procedure

The Contracting Authority reserves the right to cancel a procedure of invitation to tender after the authorisation of the authority  in charge of public contracts where the offers have been opened) or to declare an invitation to tender unsuccessful after the advice of the competent Tenders Board, without any claims being entertained.

Article 36: Notification of the award of the contract

Before the expiry of the validity of the bids set in the Special Regulations, the Delegated Contracting Authority shall notify the successful bidder by telecopy confirmed by registered mail that his bid was retained. This letter shall indicate the amount the Delegated Contracting Authority will pay the supplier to execute the contract and the execution time-limit.

Article 37: Publication of results of award and petitions

37.1     The Contracting Authority shall communicate to any bidder or administration concerned, upon request addressed to it within a maximum deadline of five (5) days after publication of the award results, the Independent Observer’s report as well as the minutes of the award session of the related contract to which shall be attached the evaluation report of the bids.

37.2 The Contracting Authority is bound to communicate the reasons for the rejection of bids of the bidders concerned who so request.

37.3     After publication of the award results, bids that are not withdrawn within fifteen (15) days shall be destroyed, without any claims for compensation being entertained. Only the copy destined for the body in charge of regulation shall be kept.

37.4      In case of petition, it should be addressed to the Minister Delegate in charge of Public Contracts with copies to the Public Contracts Regulatory Agency, to the head of structure to which is attached the Tenders Board concerned and the chairperson of the said Tenders Board.

It must take place within a maximum deadline of five (5) working days after the publication of the results.

Article 38: Signing of the contract

38.1      After publication of the results, the draft contract subscribed by the successful bidder shall be submitted to the Tenders Board (and the competent Specialised Contracts Control Board, where need be) for approval.

38.2     The Contracting Authority has seven (7) days to sign the contract from the date of reception of the draft contract approved by the competent Tenders Board and subscribed by the successful bidder.

38.3    The contract must be notified to the successful bidder within five (5) days of its date of signature.

Article 39:  Final Bond

39.1    Within twenty (20) days of the notification by the Contracting Authority, the contractor shall furnish the Project Owner with a final bond to guarantee the full execution of the services in the form stipulated in the Special Regulations, in accordance with the model provided in the Tender File.

39.2    The bond may be replaced by a guarantee from a banking establishment approved according to the instruments in force with the Contracting Authority as beneficiary or by a joint or several guarantee.

39.3      Small and medium-sized enterprises (SME) constituted of national capital and managed by nationals may, in lieu of the guarantee, provide a statutory lien or a bond issued by a banking establishment or a first rate financial institution approved in accordance with the instruments in force.

39.4    Failure to produce the final bond within the prescribed time-limit shall likely cause the termination of the contract.

Article 40: Right to modify quantities during the award of the contract

During the award of the contract, the Contracting Authority reserves the right to increase or decrease by not more than fifteen per cent (15%), the quantity of the supplies and services initially specified in the Quantity Schedule, without changing the unit prices or other terms and conditions.

Document No. 3:

Special Regulations of the invitation to tender

Special Regulations of the invitation to tender

The following information and data concerning the acquisition of supplies should supplement or specify in the clauses of the General Regulations of the invitation to tender.  In case of divergence, the following provisions will prevail over the articles of the General Regulations.

OPEN NATIONAL INVITATION TO TENDER

N° 06/ONIT/JAKIRI COUNCIL/JCITB/2026 OF 23/01/2026

FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

| General |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Definition of Works: As part of the maintenance work on the NATIONAL road network, the LORD MAYOR OF JAKIRI COUNCIL, Contracting authority, launches an Open National Invitation to Tender FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION |  |  |  |  |  |  |
|  | The works are distributed in a batch according to the itinerary or the itineraries hereafter: LOT Bridges; Council concerned; Previewed Budget (ATI); Duration (months). FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION; JAKIRI; 85, 000,000; 04. TOTAL; 85, 000,000. |
|  | DEFINITION OF WORKS: Work to be done consists of the CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION , Jakiri Council Area, Bui Division. The works include the following: - Site Installation - Catchments and Chambers - Distribution Network - Pipe Line Construction - Hydraulic Accessories - Impact Environmental. |
| 1.2 | PROJECT DURATION : The entire period of execution of these Works is 04 months (Four months) calendar months. This duration starts as of the date of notification of the service order to start Works. |  |  |  |  |  |  |
| 1.4 | FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION. The Works will be executed in a Single Phase. |  |  |  |  |  |  |
| 2.1 | FUNDING : The Works on This tender are funded by MINEE 2026 financial year budget. The previewed cost of the entire works of this Open National Invitation to tender is: Eighty Five Million(85,000,000) FCFA all taxes included |  |  |  |  |  |  |
| 4.2 | The Present Open National Invitation to Tender is open to any Enterprise working in the Civil Engineering Domain |  |  |  |  |  |  |
| 6.2 | In the case of a Joint Venture, each member of the consortium will present complete administrative documents, the attestation of bank account, the tender purchase receipt and bid bond will be presented by the Leader of the Joint venture. |  |  |  |  |  |  |
| 6.4 | Necessary information to produce that justifies the satisfaction to eligible criteria: Attestation from the National Social Insurance Fund |  |  |  |  |  |  |
| 7.3 | At the end of the site visit to be organised two(02) weeks after the award, the Technical Service of the JAKIRI Council can be contacted via Tel: 676627995 It is advisable that every bidder should do a site visit to inspect the site and its environs and to personally obtain under his responsibility, all necessary findings for the preparation of the bid and the execution of studies and works. The cost of the site visit will be handled by the bidder. |  |  |  |  |  |  |
| 9 | Complimentary findings can be obtained during working hours from the Jakiri Council, or by all other electronic communication means indicated by the Project Owner. Clarity can be gotten not later than one week before the deposit date of the file. Request for clarifications has to mention the name and address of the bidder and sent to the following address: |  |  |  |  |  |  |
|  | Preparation of BIDS |  |  |  |  |  |  |
| 12 | BIDS language (s): French or English |  |  |  |  |  |  |
| 13.1 | The list of documents referred to in Article 13 of the General Regulations should be completed, grouped into three volumes respectively inserted in inner envelopes and detailed as follows: Volume 1: Documents constituting the administrative file They consist of: - The declaration of intention to bid stamped, signed by the legal representative or Group head designated - The original of the provisional bond (for each lot applied for) of the amount as specified in the Tender Notice (Exhibit 1 of the CAD), and a period of validity of 90 days to count the initial date of submission of tenders; - The notarized joint venture agreement and specifying the Group Head; - The POWER OF ARTORNEY; - The original of the TAX CLEARENCE certificate; - The original of the certificate of non-bankruptcy issued by the Registry of the Court of First Instance of the domicile; - The attestation of Bank Account issued by a First class Banking institution accredited by the Ministry of Finance - The original copy of the tender purchase receipt indicating the sum of One hundred thousand (100,000) Thousand paid to the Jakiri council Treasury; - The original of the certificate of non-exclusion of public contracts issued by the Agency of Regulation of Public Contracts (ARMP). - The original of the certificate signed by the Director of the National Social Security Fund, or one of his duly authorized representatives, certifying that he has actually paid into the fund the sums of which he is indebted and specifying the purpose of the tender and the number of the Invitation to tender; - The receipt delivered by CDEC backing the Bid Bond. - A certified copy of the categorisation attestation or the acknowledgement receipt for the file deposit at MINMAP NB: I the case of a joint venture, each member of the consortium will provide complete administrative documents; the documents cited in 1.2,1.3,1.5,1.6 and 1.10 will be presented only by the Head of the Joint Venture. These administrative documents are valid for three (03) months. The deadline for the validity of the above administrative documents must be later than the date of the launch of the Invitation to Tender in accordance with Article 90.3 of the Decree 2018/366 of June 20, 2018 relating to the Code des Marches Publics. In the case of a group of companies, each member of the group will produce each of the administrative documents listed above with the exception of 1.1, 1.6 to Volume 2: Parts constituting the technical offer It comprises of: 2.1 Findings on the qualification The list of documents to be furnished by the bidder in order to justify its qualification that consist of references, equipment and personnel: - Technical Offer Submission letter - References of the Bidder - The list of realised contracts(Project Owner, Subject, Amount, Reception Date) by the Bidder in the Capacity of Job Holder (or Sub Contractor) within the last Five(05) years These references have to be accompanied by justifications namely: - Copies of first and last page of contract; - Minutes of Provisional or final reception, or Attestation of completion of Job; - Other necessary justifications where necessary; - Personnel - List of Key Personnel for the construction works NB: Attached to the personnel proposed, a copy of the certificate and justifications of experience notably: - Certified copy of the certificate not older than three(03) months - Attestation issued by the National Order of Civil Engineers where necessary; - Curriculum vitae signed and dated by Expert; NB: All the documents cited above have to be conform, signed and should be almost three months with respect to the date of deposit of the tender file. - Equipment to be Mobilized during execution of works The bidder has to present the following minimum equipment that consists of the following: - A dump Truck - Concrete Mixer - Concrete Vibrator - Manual compactor - A Pick Up 4 x 4 NB: The bidder should attach certified copies issued by the competent services for the following, ownership for equipment and valid purchase receipts where necessary, accompanied by a signed lease agreement if the equipment does not belong to the bidder. 2.2 Organisation and Methodology The bidder will produce a descriptive note or methodology presenting in details the constitutive elements of the technical offer, notably: - Organization and the order with which the bidder envisages to put in place in order to effectively execute the works to which will be annexed the site visit report and the attestation of site visit signed by the bidder; - The calendar of activities, planning and execution timeframe - The dispositions taken for the use of local labour(Direct Labour technique) - The dispositions taken for the respect of environmental norms during execution - The works to be sub contracted - Other elements to be précised 2.3 The Bidder will fill and submit the following forms: - The integrity chart - The declaration for the engagement to respect all social and environmental clauses 2.4 The Proof of the acceptance of the contract terms: The bidder will submit visad copies of each page and signed copies of the last page preceded by the statement “Read and Approved” for the following documents: - The Special administrative Clauses - The Special Technical Clauses NB: The denial of any clause of the contract is immediate elimination of the bidder 2.5 Commentaries on the SAC and STC The bidder can join an observation note after the signed Special administrative and the Special technical clauses. 2.5 Financial capacity The bidder has to present the following: - A financial capacity issued by a first class bank accredited by the Ministry of finance or an Insurance company accredited to issue bonds in the framework of Public contracts at the tune of Thirty Million (30,000,000) Francs CFA. The financial documents submitted by the bidder have to be examined thoroughly and is subject to judgement. All findings that could lead to financial difficulties during execution of works will lead to the hiring of a financial expert during the evaluation of the offer. For the new companies, this situation can be appreciated in an objective manner by referencing to the financial capacity of the bidder (appropriate declarations of the banks or accredited financial institutions or where necessary, proof of professional risk insurance) and the needs for the financing of the contract. 1.The amount of the financial capacity does not have to be less than thirty(30) percent of the annual turnover 2. The period is normally three years 3. In the case of a joint venture we can indicate that one member of the consortium has to satisfy 25 or 30% of the global cost and the head has to satisfy 50 to 60% of the global amount of the contract. 4. The amount in the turnover will not be fixed in a high value in order to avoid other competitive companies capable to execute the job from being kicked out. 2.7 Attestation of non-abandonment of site within the last three years Volume 3: Financial offer This envelope comprises of the following documents: 3.1 A stamped paper submission, as per the attached template (Exhibit 10.1), signed and dated; 3.2 The price schedule (Exhibit 6) according to the model and indicating the prices excluding VAT in figures and in letters, filled in a legible manner, signed and dated; 3.3 The Bill of quantities and Cost Estimates detail of the work (Exhibit 7) filled in a legible manner, signed and dated; 3.4 The price details (Exhibit 9.9). and the decomposition of fixed prices and construction costs. NB: All the pieces of the initialled financial offer, in addition to the last pages must be signed, sealed and dated. |  |  |  |  |  |  |
|  | Price and tender currency |  |  |  |  |  |  |
| 14.4 | Market prices are firm and non-revisable. |  |  |  |  |  |  |
| 15.2 | The amount of the bid is denominated entirely in national currency (CFA franc). |  |  |  |  |  |  |
|  | Preparation and submission of BIDS |  |  |  |  |  |  |
| 16.1 | Period of validity of tenders: - BIDDERS remain bound by their offer for a period of ninety (90) days from the closing date for the submission of tenders, during which time the Contracting Authority will notify the firms selected - .In exceptional circumstances, before the expiry of the initial period of validity of tenders, the Contracting Authority may request bidders to extend the period of validity for an additional period of time. The request and answers must be in writing. A Bidder may refuse to extend the validity of its bid without losing the bid bond. The Bidder who agrees to extend the period of validity of its bid may not modify its bid, but must extend the period of validity of the Bid Deposit accordingly, in accordance with the provisions of Article 17 of the General Agreement |  |  |  |  |  |  |
| 17.1 | Amount of the bid bond: 1) Pursuant to Article 6 of the RPAO, the Bidder will provide, a bid bond, the amount specified in the Tender Notice, which will form an integral part of its bid. The amount of the bid bond stands at: No; Amount in Figures(Fcfa); Amount in Words(Fcfa). 1; 800,000; Eight hundred Thousand. |
| 19.1 | Preparatory Meeting for the establishment of the offer will take place NO |  |  |  |  |  |  |
| 20 | Submission of Bids |  |  |  |  |  |  |
| 20.1 | Submission of Bids Each bid, prepared in English or in French in (07) seven copies, that is (01) one original and (06) six copies noted as such, shall be forwarded to the delegated contracting authority, notably to the Secretariat of Jakiri Council Tenders board, situated at the JAKIRI Council latest the : 17/02/2026 at 10:00am local time bearing OPEN NATIONAL INVITATION TO TENDER N° 06/ONIT/JAKIRI COUNCIL/JCITB/2026 OF 23/01/2026 FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION To be opened only during session |  |  |  |  |  |  |
| 22.1 | Deadline for submission of tenders: Tenders will be submitted by 11:00am (date of submission of tenders) at 18/02/2026 (time of submission of tenders) hours. |  |  |  |  |  |  |
|  | Mode of Submission The submission mode retained for this tender is offline.. |  |  |  |  |  |  |
|  | Opening of Bids and Evaluation |  |  |  |  |  |  |
|  | Place, date and time of the opening of the BIDS: The opening of tenders will take place on 18/02/2026 (put the date of submission of tenders) as early as11:00am (time of opening of tenders, one hour after the date of submission of tenders) 11 am in the, conference hall of the Jakiri Internal tender’s board. All bidders may attend this opening session or be represented by a single duly mandated person (even in case of consortium) of their choice with a perfect knowledge of the file. To avoid being rejected, the required Administrative documents will be imperatively produced in original or in certified true copies by the issuing service, in conformity with the stipulation of the rules and regulations of this tender. These Administrative documents have a validity period of three (03) months. This validity period has to begin after the date of the launching of the tender. In case of absence or non-conformity of an administrative document during the opening session, after a deadline of 48 hours given by the commission, the offer will be rejected. The following file will be declared rejected by the Internal Tenders Board: - All bids that do not conform to the specifications of this tender file - Absence of original copy of bid bond issued by a first-class financial organization authorized by the Ministry of Finance to issue Bid Bonds within the framework of public Contracts or the non-respect of the models presented in the tender file implies the simple and pure reject of the bid without any consideration. A bid bond produced but which doesn’t have any link with the current tender file is considered absent. A bid bond presented during the opening session is equally rejected. |  |  |  |  |  |  |
|  | Evaluation and comparison of offers |  |  |  |  |  |  |
|  | ELIMINATORY CRITERIA A-Administrative Documents - Absence during bid opening session of original copy of bid bond issued by a first-class financial organisation authorized by the Ministry of Finance to issue Bid Bonds within the framework of public Contracts; accompanied by a CDEC receipt - Non-conformity after a period of 48 hours following the deposit of bids, of at least one Administrative document; NB: A bid bond produced but which doesn’t have any link with the current tender file is considered absent. A bid bond presented during the opening session is equally rejected. B-Technical Documents - Absence of the declaration by the bidder attesting that the latter has not abandoned any contract within the last three (03) years, and that he does not future in in the list of non-performant companies established by MINMAP. - Absence of financial capacity drafted with respect to the COBAC model issued by first class bank approved by the Minister of Finance; No; Amount in figures Fcfa; Amount in Words Fcfa. 1; 85,000,000; Eighty five Million. - Did not validate 2/3 of the essential criteria and obligatorily the equipment criteria; - Did not have the minimum required equipment - A dump Truck - Concrete Mixer - Concrete Vibrators - Manual compactor - A Pick Up 4 x 4 - Absence of attestation of site visit dated, stamped and signed by the bidder; - Absence of references satisfying the condition and specific experience required by the tender file - Absence of categorization certificate issued by MINMAP - Proof of acceptance of clauses within the contract C-Incomplete financial bid for absence of one of the following documents: - Unit Price breakdown non-conform with that of the tender file ; - Incomplete offer with the absence of the bill of quantities and Cost Estimates; - The unit price schedule non-conform with that of the tender file; - Absence of a quantified price in the financial offer; - Absence of an element in the financial offer(the tender letter, the Unit Price Schedule, the Bill of Quantities and cost Estimates. D-General Eliminatory Criteria: - Absence of the soft copy of the bid - Non respect of the format for the files - Absence of original copy of bid bond - False declaration, falsified documents or non authentic, fraudulent practices 17-2 : Essential criteria : The technical bids will be evaluated according to the following ten (10) main criteria: - Key personnel of the enterprise on three (03) criteria ; - The site equipment to be mobilized on five (05) criteria ; - The Enterprise references on two (02) criteria. NB: A civil servant without any justification of secondment from the public service will not be evaluated; |
|  | EVALUATION GRILLE |  |  |  |  |  |  |
| I | Eliminatory Criteria |  |  |  |  |  |  |
| No |  |  | Description | Yes/No |  |  |  |
| - A -Eliminatory Criteria relative to the Administrative Documents |  |  |  |  |  |  |  |
| 1 |  |  | Absence during bid opening session of original copy of bid bond issued by a first-class financial organisation authorized by the Ministry of Finance to issue Bid Bonds within the framework of public Contracts; NB: A bid bond produced but which doesn’t have any link with the current tender file is considered absent. A bid bond presented during the opening session is equally rejected. | Yes/No |  |  |  |
| 2 |  |  | Non-production within a period of 48 hours following the deposit of bids, of at least one Administrative document declared non-conform or absent during opening of bids (This does not apply for absence of bid bond). | Yes/No |  |  |  |
| - B -Eliminatory Criteria relative to the Technical Bids |  |  |  |  |  |  |  |
| 3 |  |  | Absence of the declaration by the bidder attesting that the latter has not abandoned any contract within the last three (03) years, and that he does not future in in the list of non-performant companies established by MINMAP. |  | Yes/No |  |  |
| 4 |  |  | Absence of integrity chart dated and signed. |  | Yes/No |  |  |
| 5 |  |  | Absence of declaration on the engagement to respect environmental clauses; |  | Yes/No |  |  |
| 6 |  |  | Absence of financial capacity drafted with respect to the COBAC model issued by first class bank approved by the Minister of Finance of at least; No; Amount in figures Fcfa; Amount in Words Fcfa. 1; 85,000,000; Eighty Five Million. | Yes/No |  |  |
| 7 |  |  | Did not validate 2/3 of the essential criteria and obligatorily the equipment criteria; |  | Yes/No |  |  |
| 8 |  |  | Did not have the minimum required equipment - A dump Truck - Concrete Mixer - Concrete Vibrators - Manual compactor - A Pick Up 4 x 4 |  |  |  |  |
| 9 |  |  | Absence of attestation of site visit dated, stamped and signed by the bidder; |  | Yes/No |  |  |
| 10 |  |  | The bidder has to proof his references in the execution of engineering structures for the last five (05) years (2020-2025) with Contract Amount equal or more than Fifty Million(50,000,000) Francs CFA |  | Yes/No |  |  |
| 11 |  |  | Absence of categorization certificate OR receipt of deposit issued by MINMAP |  | Yes/No |  |  |
| 12 |  |  | Proof of acceptance of clauses within the contract |  | Yes/No |  |  |
| C-Eliminatory Criteria relative to Financial Offer |  |  |  |  |  |  |  |
| 13 |  |  | Unit Price breakdown non-conform with that of the tender file ; |  |  | Yes/No |  |
| 14 |  |  | Incomplete offer with the absence of the bill of quantities and Cost Estimates; |  |  | Yes/No |  |
| 15 |  |  | The unit price schedule non-conform with that of the tender file; |  |  | Yes/No |  |
| 16 |  |  | Absence of a quantified price in the financial offer; |  |  | Yes/No |  |
| 17 |  |  | Absence of an element in the financial offer (the tender letter, the Unit Price Schedule, the Bill of Quantities and cost Estimates. |  |  | Yes/No |  |
| D- General Eliminatory Criteria |  |  |  |  |  |  |  |
| 18 |  |  | Non respect of the format for the files |  |  | Yes/No |  |
| 20 |  |  | Absence of original copy of bid bond |  |  | Yes/No |  |
| 21 |  |  | False declaration, falsified documents or non authentic, fraudulent practices |  |  | Yes/No |  |
| II- Essential Criteria The evaluation of the essential criteria or relative to the qualification of bidder will be based on: A. Presentation of offer; (Clearness, documents respecting the SRIT, table of content, colour separators, page numbering) B. Experience - General Experience in Construction Works Experience in general construction works relative to roads, building and construction works with at least three (03) contracts executed by bidder for the last five (05) years preceding the latest date of deposit of the bid. - Specific Experience in Similar Construction Works Specific Experience in construction works with at least two (02) contracts executed by bidder for the last five (05) years preceding the latest date of deposit of the bid. Total Amount of at least Seventy Five (75,000,000) million all taxes inclusive per contract Or Specific Experience in construction works, with at least one (01) contract executed by bidder for the last five (05) years preceding the latest date of deposit of the bid. Total Amount of at least thirty million all taxes inclusive per contract. These references have to be accompanied by justifications that include: - Copies of first and last pages of contract; - Minutes of Provisional or final reception or Attestation of completion of works - Other justifications where necessary C. Personnel The bidder will establish a list of his personnel for the key experts required notably: No; POST; QUALIFICATION/EXPERIENCE; Observation. Yes; No. 1; Works Director; - Minimum BSc in Civil Engineering with at least ten(10) years’ Experience and registered in the, - Occupied position of Works Director for at least five(05) water projects with span greater than six(06) meters and Project cost of at least Fifty million Francs (50,000,000). 2; Site Foreman; - Minimum HND in Civil or Rural Engineering with at least five(05) years’ Experience - Occupied position of Site Foreman for at least two(02) water projects with span greater than six(06) meters and Project cost of at least fifty million Francs (50,000,000). NB: Provide the following for each candidate: - A dated and signed curriculum vitae - A certified copy of the required certificate endorsed by the competent administrative authority - Attestation of availability signed by the candidate NB: The proposed personnel will be considered if and only if the justifications cited above have been presented, certifications done within three(03) months as from date of deposit of documents and duly signed as instructed above. D. EQUIPMENT The Bidder must justify that he owns or he is hiring the following equipment: NO; Description and characteristics of equipment; Age/State; Minimum Number Required; Owner/Hired; Year Obtained; Justification. 1; Dump Truck(01). 2; Concrete Mixer(01). 3; Concrete Vibrator(01). 4; Manual compactor(01). 5; Pick up 4 x 4 (01). 6; Small tools carpentry, building, electricity etc. NB: Furnish certified copies from the issuing service or any other competent authority for the vehicle registration certificate and the purchase receipts for the others, where necessary accompanied by the signed lease agreement and the sales certificate within the framework of this tender file. NB: The Equipment criteria is satisfactory if the score obtained is equal to or more than 15 on 20 on the criteria previewed above for evaluation. E. Proof of Acceptance of clauses No; Experience; Acceptable(Yes/No). 1; Special Administrative Clauses(SAC). 2; Special Technical Clauses (STC). NB: The validation of this criterion is based on the fact that the bidder obtains Yes for both. In case of conflicting information found in the tender file, the elimination of a bid for non-conformity prescribed in the tender file will be based only on the criteria found in the Special Regulations of the Invitation to Tender. |
|  |  | F-AWARD OF CONTRACT |  |  |  |  |  |
| 34.1 |  | The Project Owner attributes the contract to the bidder whose offer was conform to the tender file and who demonstrated technical and financial capacities required to execute this works satisfactorily and whose offer was evaluated as the lowest bidder after the calculations where necessary. |  |  |  |  |  |
| 34.2 |  | The contract will be awarded to the biddder submitting the lowest evaluated bid, according to the case, fulfilling the required administrative, technical and financial criteria. It cannot be awarded more than ____(specify the number of lots in letters and in numbers from which a biddder may be awarded) lot (s) per BIDDER under this Invitation to Tender. |  |  |  |  |  |
|  |  | Final guarantee |  |  |  |  |  |
| 39.2 |  | The final guarantee Bond is set at two percent two (2%) of the amount inclusive of all taxes of the contract. The bidder will furnish the final bond within a period of twenty (20) days from the date of notification of the contract done by the Project Owner following the model attached to this tender file. The non-production of the final bond within the specified time and the conditions of article 28 of the Special Administrative Clauses exposes the bidder to sanctions previewed in article 37 of the Special Administrative Clauses. |  |  |  |  |  |
|  |  | Ethics Principle The Presidents and members of commission, the bidders and the other stakeholders of the procedure have to always observe strictly the rules and ethics of the profession. They have to decline from all types of corruption and fraudulent malpractices. In principle, the expressions made above are defined as follows: i) Is guilty of “corruption” anyone who offers, gives, solicits or accepts directly or indirectly any advantage in view of influencing an action of a public agent during the attribution or the execution of a contract or a jobbing order; ii) Is guilty of “corruption” anyone who furnishes, solicits or accepts many offers proposed by the same bidder using different companies and/or different registered numbers; iii) Is abetting in fraudulent malpractices anyone who deforms or misinforms with the aim of influencing the award or execution of a contract or jobbing order in a manner that is detrimental to the Project Owner and the Delegated Project Owner. The fraudulent malpractices are made up of all agreements or manipulations of bidders (before or after the submissions of the bids) with the aim of artificially maintaining the prices of the offer to the tune that will not correspond to the expected results in a concurrent manner free and open, and in turn deprive the Project Owner of the advantages of the latter. |  |  |  |  |  |

Document No. 4:

Special Administrative Conditions (SAC)

Content

Chapter I: General

Article 1     -     Subject of the contract

Article 2     -     Award procedure (GAC supplemented)

Article 3     -     Definitions and duties (article 2 of GAC supplemented)

Article 4     -     Applicable language, law and regulations

Article 5     -     Standards (article 3 of GAC supplemented)

Article 6     -     Constituent documents of the contract (article 9 of GAC)

Article 7     -     General applicable instruments (GAC supplemented)

Article 8     -     Communication (article 6 of GAC supplemented)

Article 9     -     Administrative Orders (article 8 of GAC)

Article 10   -     Supplier’s material and personnel (GAC supplemented)

Chapter II: Financial clauses

Article 11    -     Guarantees and bonds

Article 12    -     Amount of contract

Article 13    -     Place and method of payment (GAC supplemented)

Article 14    -     Price variation (article 18 of GAC)

Article 15    -     Price revision formula (article 19 of GAC)

Article 16    -     Price updating formula (article 19 of GAC)

Article 17    -     Direct labour works (travaux en regie)

Article 21    -     Payment of works

Article 22    -     Interest on overdue payments

Article 23    -     Penalties for delay

Article 23: -       Penalties of delay
Article 24      Regulation in the case of a grouping of undertakings
Article 25        final BILLS
Article 26       General and FINAL BILLS

Article 27    -    Tax and customs schedule

Article 28    -     Stamp duty and registration of contracts

Chapter III: Execution of works

Article 29    -     Time limit for works

Article 30    -     Patent rights

Article 31: - Provision for documents and site
Article 32:   insurance of works and civil responsibilities
Article 33: - consistency of work
Article 34: - DOCUMENTS to be provided by the contractor
Article 35: - organization and safety of worksite

35.1 security of worksite

35.2 maintaining the circulation
Article 36: - implantation of works
Article 37: - subcontracting
Article 38: - construction laboratory and testing
Article 39: - journal and site meetings

39.1 workshop journal

39.2 site meetings
Article 40: - use of explosives

Chapter IV:   Acceptance

Article 41    -     Provisional acceptance

Article 42    -     Documents to be furnished before the technical acceptance

Article 43    -     Guarantee deadline

Article 44    -     Final acceptance

Chapter V: Miscellaneous provisions

Article 45   -     Termination of the contract

Article 46   -     Case of force majeure

Article 47   -     Differences and disputes

Article 48   -     Drafting and dissemination of this contract (GAC supplemented)

Article 49 and last   -     Entry into force of the contract (GAC supplemented)

Chapter I

Generalities

Article 1:  Subject of Contract

The Lord Mayor JAKIRI Council; CONTRACTING AUTHORITY within the framework of the execution of the 2026 state budget initiates on the behalf of the Republic of Cameroon, an Open National Invitation to tender for

THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

| LOT | Nature of works | Council concerned | Previewed Budget (ATI) | Duration (months) |
| --- | --- | --- | --- | --- |
| 1 | FOR CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION | JAKIRI | 85, 000,000 | 04 |
|  | TOTAL |  | 85, 000,000 | 04 |

Article 2: Award procedure

This contract shall be awarded through

OPEN NATIONAL INVITATION TO TENDER

06/ONIT/JAKIRI COUNCIL/JCITB/2026 OF 23/01/2026

FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

Article 3: Definitions and duties

1 General definition:

For the applications of the general definitions of this contract, it is precised that:

-  The Project Owner shall be The Lord Mayor of Jakiri Council. He is the signatory and ensures the proper functioning. He ensures the preservation of originals of contract documents and the transmission of copies to ARMP through the focal point designated to this effect,

- The Contract Manager shall be The Secretary General Jakiri Council hereinafter referred to as the Contract Manager; He ensures the respect of the administrative, technical, financial conditions and contractual time-limits.

- The Contract Engineer shall be The Divisional Delegate of Water and Energy for Bui, hereinafter referred to as the Engineer. He is accredited by the Project Owner for the supervision of the execution of works

- The Project Manager shall be The divisional Chief of Service in charge of Water, hereinafter referred to as the PROJECT MANGER.

- The authority in charge with the external control of the execution of the contract shall be, the Divisional  Delegate of Public Contracts  BUI,

    - The Authority in charge of clearance is the Administrator Road Fund;

    - The contractor is _________________,

    - The competent tender’s board is the. Jakiri council internal tenders board

3.1: - SECURITY

The collateral is subject to the rules applicable in this matter to government procurement, including Article 150 of Decree No. 2018/366 of 20 June 2018 on the PUBLIC CONTRACT CODE.

With a view to applying the system of collateral instituted by the abovementioned decree, are defined as:

- Authorizing authority: The Lord Mayor of Jakiri council;

- Authority responsible for the liquidation of expenses for monthly accounts:  The Lord Mayor of Jakiri council;

- The paying agency is the Jakiri Council Treasury.

- Officials competent to provide the information within the framework of the execution of this contract is: The Contract Manager and Contract Engineer

3.2. SITE INSTALLATION

MEMBERS:

    - The contracting Authority or his representative

    - The Contract Manager

    - The Contract Engineer

    - DD.MINMAP OR Representative

    - DD Environment

    - THE Project Manager

    - CONTRACTOR

3.3: - RESPONSIBILITIES OF THE PROJECT ENGINEER

The Project ENGINEER is responsible for having the work EXECUTED satisfactorily in accordance with the contractual provisions and the TECHNICAL SPECIFICATIONS of the WORKS.

It may not relieve the contractor of any of its contractual obligations, nor (except as expressly stipulated below) order any work likely to delay the execution of the works or to provoke an additional payment by the Contracting Authority, nor order any significant modification to the work to be performed. The Project ENGINEER is competent to prepare and sign technical service orders.

At the request of the CONTRACTOR or the Project ENGINEER contradictory findings may be made to fix the quantities of certain works. Such contradictory findings will be made when a work may no longer be measurable.

Article 4: Language, applicable law and regulation (GAC supplemented)

- The language to be used shall be [English and/or French].

- The CONTRACTOR shall be bound to observe the law, regulations and ordinances in force in the Republic of Cameroon and this both within his own organization and in the execution of the contract.

If in Cameroon the regulations, laws and administrative and fiscal measures in force at the date of signature of this contract are amended after the signature of the contract, the possible direct resulting costs shall be taken into account without gain or loss for either party.

Article 5: Constituent documents of the contract

The constituent contractual documents of this contract are in order of priority

5.1 The CONTRACTOR’s bid and its annexes in all provisions not contrary to the Special Administrative Conditions (GAC) and the Special Technical Conditions (STC) referred to above;

5.2 the contract contents the following:

- The Special Administrative Conditions (SAC);

- The Technical Specifications (TS);

- The particular elements necessary for the determination of the contract price, such as, in order of priority:, the statement of all-in prices, detailed estimates,

5.3 the unit price schedule,/ the breakdown of all-in prices and the sub-details of unit prices,

5.4 the tender file;

5.5 the updated and approved planning of works,

5.6 The approved execution plan

5.7   The General Administrative Conditions (GAC) applicable to supplies contracts as put in force by Decree No. 043 of 13 February 2007;

Article 6: General instruments in force

This contract shall be governed by the following general instruments:

In the case that is not contrary to the provisions of this contract, the other party remains subject to the general texts hereafter:

6.1. Law No. 92/007 of 14 August 1992 on the Labour Code;

6.2. Law No. 96/07 of 8 April 1996 on the protection of the modified road assets and supplemented by the laws n ° 98/011 of July 14, 1998 and 2004/021 of July 22, 2004;

6.3. framework law N ° 096/12 of 05 August 1996 on a framework law on environmental management;

6.4. the law n ° 2000/10 of July 13th, 2000 fixing the organization and the modalities of the exercise of the profession of Engineer of the Civil Engineering;

6.5. Law No. 001 of 16 April 2001 on the Mining Code, and implemented by Decree No. 2002/048 / PM of 26 March 2002;

6.6. Law No. 2007/006 of 26 December 2007 on the Financial Regime of the State;

6.7. Law No. 2017/021 of 20 December 2017 on the Budget Law of the Republic of Cameroon for the 2018 Financial Year;

6.8. Ordinance N ° 2018/001 of 09 April 2018 amending and supplementing certain provisions of Law N ° 2017/021 of 20 December 2017 on the Finance Law of the Republic of Cameroon for the financial year 2018;

6.9. Ordinance N ° 2018/002 of 04 June 2018 amending and supplementing certain provisions of Law N ° 2017/021 of 20 December 2017 on the Finance Law of the Republic of Cameroon for the financial year 2018;

6.10. The Mining Code

6.11. Decree No. 2001/048 of 23 February 2001, on the organization and functioning of the Public Procurement Regulatory Agency (ARMP);

6.12. Decree No. 2004/651 / PM of 16 April 2004 laying down the procedures for the application of the tax and customs regime for Government Procurement;

6.13. Decree No. 2005/577 of 23 February 2005 laying down the procedures for carrying out environmental impact studies;

6.14. Decree No. 2008/376 of 12 November 2008 on the administrative organization of the Republic of Cameroon;

6.15. Decree No. 2011/408 of 9 December 2011 on the organization of the Government;

6.16. Decree N ° 2012/075 of the 08/04/2012 leading organization of the Ministry of Public Procurement;

6.17. Decree N ° 2012/076 of 08/04/2012 amending and supplementing certain provisions of Decree N ° 2001/048 of 23 February 2001 on the creation, organization and functioning of the Agency for the Regulation of Public Procurement;

6.18. Decree N ° 2013/271 of 05 August 2013 amending and supplementing certain provisions of Decree N ° 2012/074 of 08 March 2012 on the creation, organization and functioning of Procurement Commissions;

6.19. Decree No. 2013/334 of 13 September 2013 on the organization of the Ministry of Public Works;

6.20. Decree No. 2014/0611 / PM of 24 March 2014, setting the conditions for the recourse and application of labour-based approaches;

6.21. Decree No. 2018/190 of March 02, 2018 amending and supplementing certain provisions of Decree No. 2011/408 of December 9, 2011 on the organization of the Government;

6.22. Decree No. 2018/1991 of 02 March 2018 on the redevelopment of the Government;

6.23. Decree No. 2018/366 of 20 June 2018 on the Public Procurement Code;

6.24. Law N ° 2004/017 of 22 July 2004 on the orientation of Decentralization;

6.25. Law N ° 2004/018 laying down the general rules applicable to the municipalities;

6.26. Order No. 093 / CAB / PM of 5 November 2002 fixing the amounts of the bid bond and the cost of purchasing the Bidding Documents;

6.27. Order No. 070 / MINEP of April 20, 2005 setting out the different categories of operations whose realization is subject to the environmental impact study;

6.28. Order No. 043 / CAB / PM of 13 February 2007 putting into effect the General Conditions of Contract (CCAG) applicable to public contracts;

6.29. Order No. 07 / MINTP of 16 October 2012, containing terms and conditions specifying the technical conditions and procedures for the exercise of powers transferred by the State to the Communes in the field of road maintenance work;

6.30. Circular No. 004 / CAB / PM of 30 December 2005 on the application of the Public Procurement Code;

6.31. Circular No. 004 / CAB / PM of 18 April 2008 on compliance with the rules governing the award, execution and control of public contracts;

6.32. Circular No. 002 / CAB / PM of 31 January 2011 on improving the performance of the Public Procurement system;

6.33. Circular No. 003 / CAB / PM of January 31, 2011 specifying how to manage changes in the economic conditions of public markets;

6.34. Circular No. 001 / CAB / PR of 19 June 2012 on the awarding and control of the execution of public contracts;

6.35. Circular N ° 0001877/ C / MINFI of 31/12/25 ,Bearing instructions on the implementation of financial laws, monitoring and the control of the execution of the Budget of the State and other Public Entities for the 2026 Fiscal year

6.36. Circular-letter No. 0005 / LC / MINMAP / CAB of July 3, 2018 specifying the transitional measures to be observed following the signature and publication of Decree No. 2018/366 of June 20, 2018 on the Public Procurement Code;

6.37. Letter No. 00908 / MINTP / DR dated 1997 from the Ministry of Public Works issuing guidelines for the consideration of environmental impacts in road maintenance;

6.38. the technical standards in force in Cameroon;

6.39. The directives in force at the Ministry of Public Works allocating roles among the various stakeholders for the ongoing road maintenance campaign with the Owner;

6.40. the French CCTG, in particular its preamble and fascicles 1, 2, 4, 7, 23, 24, 25, 27, 29, 30, 31, 50, 56, 61, 62, 63, 65-A, 66, 68, 70 as well as French standards (in the absence of Cameroonian standards) and the technical opinions of the French technical network;

6.41. the national collective agreement for construction, public works and related activities of December 10, 2013.

Article 7: Communication

7.1 THE CONTRACTOR DOMICILLIATION

The CONTRACTOR is required to take up residence near the place of work and to make known the address of this domicile to the CONTRACT MANAGER.

Failure by him to have fulfilled this obligation within fifteen (15) days from the date of notification of the Service Order to begin the work, all notifications related to the contract will be valid when they have been made at THE CONTRACT ENGINEERS OFFICE

After the provisional acceptance of the works, the CONTRACTOR is released from the aforementioned obligation. In this case, any notification will then be validly made to the registered office mentioned in the tender and listed on the cover page of this contract.

7.2 CORRESPONDENCE

All correspondence between the CONTRACTOR, the PROJECT OWNER, the CONTRACT MANAGER, the CONTRACT Engineer, the Project Manager, are exclusively made in writing.

They shall be sent by post, telegram, telex, telefax, E-mail or deposited against discharge at the addresses indicated by the parties.

In the event that the Client is the addressee, copies will be sent within the same time, to the Head of Service, the Engineer and the Project Manager.

The CONTRACTOR will send all written notices or correspondence to the Project Manager, with a copy to the CONTRACT MANAGER and to the CONTRACT Engineer.

Article 8: Administrative Orders

The various service orders will be establish and notified as follows

  - The Administrative Order to start execution of works shall be signed by the CONTRACTING AUTHORITY and notified to the contractor by the contract Engineer with copies to the contracting authority, Contract Manager, Project Manager and paying body.

  - Administrative Orders with incidence on the objective, amount or supply deadline shall be signed by the Project owner and notified to the supplier by the contract manager with a copy to the Project Owner, contract engineer, Engineer, Project Manager and Paying Body. The prior endorsement of the Paying Body shall possibly be required for those with a financial incidence.

  - Administrative Orders of a technical nature linked to the normal progress of the supplies shall be signed directly by Contract Manager and notified to the supplier by the Engineer or Project Manager (where applicable) and a copied to the Contracting Authority and Contract Manager..

  - Administrative Orders serving as warnings shall be signed by the Project Owner and notified to the supplier by Contract Manager and copied to the Contracting Authority, Engineer and Project Manager.

  - Administrative Order for suspension or resumption of supplies for reasons of the weather shall be signed by the Contract Manager upon the proposal of the Project Owner after the opinion of the Engineer and notified to the supplier by the Engineer.

  - Administrative Orders prescribing works necessary to remedy disorders not within the remit of normal maintenance which could appear during the guarantee period and not related to normal usage shall be signed by the Contract Manager upon the proposal of the Contract Engineer and notified to the supplier by the Contract Engineer.

  - The supplier shall address all written notifications or correspondences to the Project Manager and copied to the Contract Manager and Engineer

  - The supplier has a time-limit of fifteen (15) days to issue reservations on any Administrative Order received. Having reservations shall not free the enterprise of executing the Administrative Orders received.

ARTICLE 9: - CONDITIONAL WRAPPING CONTRACT

9.1 The contract is not conditional; however, it should be stressed that task 1 on “clearing or weeding the roadside” should be subject to two or three passes (depending on the Regions),

Article 10: Supplier’s equipment and staff

10.1 MATERIALS AND PERSONNEL TO BE SET UP

The contracting party will mobilize the equipment and personnel necessary for the execution of the works.
10.2 REPRESENTATIVE OF THE COCONTRACTOR
Within five (05) days from the date of notification of the service order to begin the work, the CONTRACTOR must compulsorily designate HIS SITE ENGINEER, who will have sufficient powers of representation and decision to direct the site.

This designation will be made by mail to the Project Manager with a copy to the CONTRACT MANAGER, signed by the contractor and containing the specimen signature of the manager so designated.

Chapter II: Financial conditions

Article 11 Guarantees and securities

11.1 DEFINITIVE SECURITY
11.1.1 The final guarantee in the execution of the work will be constituted within a period of twenty (20) days from the date of notification of the order of service of start of works. It will be kept by the Paying Organization.
The provisional guarantee of submission is returned to the other party as soon as this final bond is established
11.1.2 Its amount is fixed at Two percent (2%) of the amount inclusive of all taxes of the market.
11.1.3 The final guarantee may be replaced by a personal and joint guarantee of a first-rate financial institution established in Cameroon and approved by the Minister in charge of Finance.
11.1.5 At the end of the work, the final bond will be returned, or the bank surety will be replaced, at the written request of the other party.
11.3 GUARANTEE OF STARTING ADVANCE
The start-up loan set in Article 20.1 of this SCC shall be 100% bonded by a financial institution established in Cameroon and approved by the Minister in charge of Finance.

Article 12: Amount of the contract

The amount of this contract as shown on the attached is_______ (in figures)_______(in letters) CFA francs Inclusive of All Taxes; that is:

    - Amount exclusive of VAT: _________(_______) CFA F

    - Amount of VAT: __________(______) CFA F.

The amount of the contract calculated under the conditions laid down in article 19 of the GAC, results from the application to the amount exclusive of the VAT, of the Value Added Tax (VAT).

Article 13: Place and method of payment

  - In return for the payments to be done by the Delegated Contracting Authority to the supplier under the conditions laid down in the contract, the supplier is bound by these provisions to execute the contract in accordance with the terms of the contract.

  - Payments shall be made into account No. _____ opened in the name of the supplier in  _____bank.

- For payments in CFA francs either (amount in figures and letters exclusive of VAT), by credit to account No. ______ opened in _____ bank in the name of the supplier.

- For payments in foreign currency, either (amount in figures and letters exclusive of VAT) be credit to account No.  _____ opened in _____ bank in the name of the supplier.

Article 14: Price variation

14.1: CONSISTENCY OF PRICES
14.1.1 The prices of this contract include all the constraints imposed on the EXECUTION of the work as well as the local conditions that may affect their EXECUTION and cost.
14.1.2 Lump sum mileage prices include, in particular, labor, the supply of materials and materials, leasing, depreciation, operation and maintenance of equipment, personnel transportation costs, allowances, leasing and agreement of the local residents for the depositing of the products of weeding or removal and all things necessary for the good execution of the works.
14.1.3 These prices also include bonuses, insurance costs, including civil liability and construction site insurance, and social security charges due to various personnel and all local taxes and fees related to good signage of the building site.
14.1.4 Memorandum prices or for which quantities are not priced retail even though they appear in the Price Schedule and in the price sub-items of the initial offer, are not part of the contract.
14.1.5 Under no circumstances may the other party claim the insufficiency of information provided by the Administration to revert the price quoted or to claim compensation in the course of the contract.
14.2: BREAK DOWN PRICE
14.2.1 The Bidder has provided in its bid the sub-detail of each application price, established according to the rules in use, and detailing the amount per task.
14.3: VARIATION OF PRICES
Prices in this CONTRACT are firm.

Article 15: Price revision formulae

Not applicable

Article 16: Price updating formulae

Not applicable

Article 17: direct labour works

Not applicable

ARTICLE 18: - VALORIZATION OF WORK

This contract is at unit prices. The amount due is determined by multiplying the corresponding unit prices by the quantities of work EXECUTED and ASSESS.

ARTICLE 19: - VALORIZATION OF SUPPLIES
Not applicable.

ARTICLE 20: - ADVANCES
20.1 START-UP ADVANCE
20.1.1 In accordance with the regulations in force and at the express request of the other CONTRACTOR, a start-up advance of up to TWENTY PERCENT (20%) of the amount inclusive of VAT may be granted.
However, this request will be transmitted to the Owner only after notification of the service order to start the work.
20.1.2 The start-up advance shall be reimbursed by fifty percent (50%) of the work of each statement from the time the work performed exceeds forty percent (40%) of the contract price. It must be completed at the latest when the amount of the work reaches eighty percent (80%) of the contract value. In any case, the refund must be completed one (01) month before the expiry date of the contractual period.
20.1.3 As and when the advances are reimbursed, the DELEGATED CONTRACTING AUTHORITY shall give the hand-over of the corresponding deposit if the other party so requests.

Article 21: Payment of works

21.1 START-UP ADVANCE PAYMENT

After the eventual agreement of THE CONTRACT MANAGER to the start-up loan application referred to in article 20.1.1 above, the relevant statement, corresponding to the percentage granted, shall be drawn up by the contracting party and sent to the Project Manager, along with the equivalent BID bond.

21.2 ASSESSMENT THE WORK DONE
At the reception of the work of each pass, the contractor and the Project Manager establish an contradictory ASSESSMENT which summarizes the details of the executed work, which may give the right to payment.
21.3 BILLS
21.3.1 The payment of the BILLS of each pass is conditioned by the presentation of the approved execution PROGRAMME.
21.3.2 Only the VAT Exclude statement will be paid to the other party. The calculation of the amount of VAT will be borne by the PUBLIC WORKS Budget.
21.3.3 The Concession Holder will be compensated for the quantities actually executed. It will deliver in seven (07) copies, (01 stamped original and 06 copies), after the reception of the works of the considered pass, to the Project Manager, two drafts provisional BILLS (a BILL without taxes (HT) and a BILL OF the amount of the fees), establishing the total amount of the sums he can claim as a result of the EXECUTION of the contract.
21.3.4 The amount of the VAT bill is the sum of the amount of work determined on the basis of the quantities of the contradictory ASSESSMENT, to which are applied the prices of the list from which will be deducted:
(i) the sums for the repayment of advances made to the contractor in accordance with article 20.1.2 of this SCC;
ii) late penalties, possibly.
21.3.5 The settlement of the amount of the taxes will be the subject of a written order between the MINTP Fund and the MINFI.
The VAT amount of the settlement to be paid to the CONTRACTOR, a taxpayer under the effective tax rate regime, shall be charged as follows:
- 97.8% paid directly to the counterparty’s account;
- 2.2% paid to the Public Treasury in respect of the IR (Income Tax) owed by the other party and deducted at source.

21.3.6 The Project ENGINEER will check the BILLS for validation or make corrections. He will forward them to the CONTRACT MANAGER who will forward them to the CONTRACT MANAGER for prior approval before transmission to the Paying Agency, so that they are in his possession by the 15th of the month at the latest.

Payments will be made by the BAMENDA TREASURY within the statutory deadlines from the submission of the approved statement.

However, QUANTITIES OF WORKS EXECUTED and BILL must be checked and validated during site meetings.

A copy of the MINUTES and corresponding QUANTITIES OF WORKS EXECUTED shall be sent to the CONTRACT MANAGER and the Engineer for the follow-up file at the same time.

In case of corrections, a copy of the corrected BILL is returned to the CONTRACTOR.
21.4 TRANSMISSION OF BILLS TO THE CONTRACTING AUTHORITY
21.4.1 Pursuant to the provisions of Article 47 of Decree No. 2018/366 of 20 June 2018 establishing the Public CONTRACT Code, a copy of the provisional and final BILLS will be sent to the Minister for PUBLIC Contracts. Only the final BILL will be subject to the approval of the DIVISIONAL Delegate of Public CONTRACT territorially competent, before its transmission to the Paying Agency.

Article 22: Interest on overdue payments

Any default interest is paid by statement of the sums due in accordance with the provisions of Articles 166 and 167 of Decree No. 2018/366 of 20 June 2018 on the Public CONTRACT Code.

Article 23: Penalties for delays

  - Penalties for delay of work:

23.1.1 If the other party fails to have completed all the works within the specified time, it will be applied, after prior notice, penalties of delay in accordance with the provisions of Article 168 of Decree No. 2018 / 366 of June 20, 2018 relating to the Publics CONTRACT Code :

- 1 / 2000th of the total amount of the CONTRACT per calendar day of delay from the first (1st) to the thirtieth (30th) day.

- 1 / 1000th of the total amount of the CONTRACT per calendar day of delay beyond the thirtieth (30th) day.

In the event of an extension of time by the Employer at the request of the company, except in cases of force majeure, expenses relating to the services of the Control Mission will be borne by the company.

  - Penalty for late execution of contractual documents:

- THE CONTRACTOR representative: 3,000F / day late beyond fifteen (15) days from the date of notification of the start-up service order;

- Co-contractor’s home address: 3,000F / day late beyond fifteen (15) days from the date of notification of the start-up service order;

- Staff and Equipment List: 5,000F / d over fifteen (15) days from the date of notification of the start-up service order;

- Insurances: 5000F / day late beyond fifteen (15) days from notification of the Seed Service Order.

- Final Bond: 5,000F / d over twenty (20) days from notification of the Seed Service Order;

- Execution Program: 15,000F / d over thirty (30) days from the notification of the start-up service order.

  - Penalties for failure to perform:

- No filling of the construction log found during visits: 3 000F / visit

- Unavailability of the site log during visits: 5,000 / visit.

  - Cumulative penalties may not exceed ten per cent (10%) of the TTC amount of the contract In accordance with Article 169 of Decree No. 2018/366 of 20 June 2018 on the Public CONTRACT Code.

  - A rate greater than ten percent (10%) may result in the termination of the contract In accordance with Article 182 of Decree No. 2018/366 of 20 June 2018 on the Public CONTRACT Code.

  - It is the responsibility of the Co-contractor to collect, as and when the works are carried out, the supporting documents of a possible file for the submission of penalties.

  - The execution of penalties may be pronounced by the PROJECT OWNER only after favourable opinion of the Government CONTRACT Regulatory Agency.

  - No bonus is provided in case of advance on the contractual period.

ARTICLE 24 REGULATIONS IN THE CASE OF A GROUPING

24.1 Direct payments from contractors are envisaged provided that the agent or the contracting party has agreed to the amounts to be paid in this way.

ARTICLE 25 FINAL BILLS

After completion of the work and within a maximum of 45 days after the date of provisional acceptance, the CONTRACTOR will establish on the basis of conflicting findings, the draft final BILLS of the work actually EXECUTED, which summarizes the total amount of sums he can claim from does the work as a whole.
The final draft bill is presented by the CONTRACTR to the verification of the project manager, the engineer’s visa, the Chief of Service’s visa and the approval of the contracting authority.
This final draft bill, once accepted or rectified by the CONTRACT MANAGER becomes final settlement. It is used for the establishment of the deposit for balance of the CONTRACT, established under the same conditions as those defined above for the establishment of monthly statements.
ARTICLE 26 GENERAL AND DEFINITIVE BILLS
26.1 The general and final BILLS at the end of the contract will be signed by the PROJECT OWNER.
26.2 After the acceptance of the works, the Project ENGINEER draws up the general and definitive BILLS of the contract, which is signed by the Contractor on the one hand, the Engineer, the CONTRACTMANAGER and the PROJECT OWNER.

This count includes:

- the final BILL,

- the deposit for balance,

- the summary of the DISCOUNTS.

The amount of the general count is equal to the result of this last recapitulation.
26.2 The signature of the general and definitive BILLS without reservation by the CONTRACTOR binds the parties definitively and terminates the contract, except with regard to default interest, possibly the revision or discounting of the prices, which are settled by the Member States. Dues, not included in the amount of the contract.
ARTICLE 27: - TAX AND CUSTOMS REGIME

27.1 This contract is subject, in the field of taxation, to the regulations in force in the Republic of Cameroon.
27.2 This contract is concluded inclusive of all taxes, in accordance with the decree n ° 2004/651 / PM of April 16th, 2004 fixing the modalities of application of the fiscal and customs regime of the public CONTRACTS.
ARTICLE 28: - Stamp duty and registration of contracts

28.1 Seven (7) original copies of this contract shall be stamped and registered by the care and expense of the CONTRACTOR, in accordance with the regulations in force.
28.2 After registration, it will be returned to the PROJECT Owner, five (05) original copies for ventilation
28.3 Failure to register within the prescribed deadlines will result in penalties provided for by the General Tax Code.

Chapter III

Execution of services

Article 29: Time limit of the contract

  - This deadline of this contract shall run from the date of notification of the Administrative Order to start execution and is of ________________ calendar months

Article 30: Role and responsibilities of the contractor

30.1 The CONTRACTOR acknowledges having read and verified the volume and nature of the work to be EXECUTED. It cannot claim any omission or underestimation of the CONTRACT to make claims of any nature whatsoever.

30.2 The contractor shall be held responsible for any damage to the road, residents or vehicles resulting from the use of working methods that do not comply with this contract, in particular the use of fire for weeding of any nature whatsoever is formally prohibited.

30.3 The CONTRACTOR is obliged to set up a specific signage for any obstacle created on the day carriage because of the work (temporary deposit of materials before loading). It is strictly forbidden to leave a night obstacle on pavement and paved shoulders, even if reported. Failure to comply with these safety rules will result in penalties as defined in section 14 of this SCC.

30.4 The CONTRACTOR must comply with the environmental protection regulations in force in the Republic of Cameroon, and in particular the framework law n ° 096/12 of 05 August 1996 on the management of the environment and the letter n ° 00908 / MINTP / DR dated 1997 of the Minister of Public Works publishing the Guidelines for the consideration of environmental impacts in road maintenance. In particular, he must comply with the CPT’s requirements in this respect.

30.5 The CONTRACTOR may not evade the confirmation decided by the PROJECT OWNER without breaking the market due to his wrongdoing and subjecting himself to the sanctions provided for by the regulations in force.

ARTICLE 32: - INSURANCE OF WORKS AND CIVIL RESPONSIBILITIES

32.1 The CONTRACTOR must prove that he holds a “civil liability” insurance policy, for damages of any kind caused to third parties:

(a) by his salaried staff working at work;

(b) by the equipment he uses;

c) because of the work.
32.2 In addition, the site must be covered for all the work of an “all risk building site” insurance issued by a company approved by the competent authority. The costs inherent in this insurance are borne by the CONTRACTOR.
32.3 No regulations except the start-up loan shall be made without presentation of a certificate from one company proving that the CONTRACTOR has paid in full the premiums or contributions relating to the works concerned.
32.4 The CONTRACTOR shall have a period of fifteen (15) days from the date of notification of the service order to commence work to present a certificate from an insurance company proving that it has been fully paid premiums or contributions relating to the work for this contract. After this period, the contract may be terminated.

ARTICLE 33: - CONSISTENCY OF WORK
33.1 The works are defined in the CPT, the price schedule and the estimated detail and generally include:

These works comprise the following descriptions:

Nature of Works

Works comprise especially the items listed in the table below:

Work to be done consists of the CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

. The works include the following:

- Site Installation - Catchments and Chambers - Distribution Network - Pipe Line Construction - Hydraulic Accessories - Environmental Impact

33.2 Services not provided for, due to accidents or whose complexity requires means not defined in the above documents will be performed by the company at the express request of the PROJECT OWNER by order of service. Any service EXECUTED without an order for service will not be paid by the PROJECT OWNER.
33.3 Prior to the commencement of all work, the contractor and the Project Manager shall proceed to a measure of the length of the lot and an identification of the work with marking on the roadway every hundred (100) meters. This will be the subject of a report signed by both parties.
33.4 Environmental protection
The CONTRACTOR will be required to comply with the laws governing the protection of the environment in force in the Republic of Cameroon and in particular the law n ° 096/12 of 05 August 1996 on the framework law on the management of the environment and the Letter No. 00908 / MINTP / DR dated 1997 from the Minister of Public Works publishing the Guidelines for the consideration of environmental impacts in road maintenance.

In particular, he must comply with the provisions of the CCTP (chapter V) in this respect.

ARTICLE 34: - DOCUMENTS TO BE PROVIDED BY THE COCONTRACTOR
34.1 WORK EXECUTION PROGRAMME
34.1.1 Within a period of five (05) days from the notification of the service order to start the work of each pass, the CONTRACTOR will submit to the validation of the CONTRACT Engineer, after approval of the Project Manager, and in six (06) copies a execution PROGRAMME of the works after a detailed visit of the site, accompanied by the Project Manager. The project manager has two (02) DAYS for the visa or rejection of the project, the CONTRACT Engineer also has three (04) days for validation or rejection. The rejects should focus on the corrections to the execution PROGRAMME to be unique at each level of validation.
34.1.2 This execution PROGRAMME will include:
- The Methodology of works;

- The CV of the Key Personnel and the copy of the diplomas;
- The organization of the company to carry out the work of each workshop;
- The quantitative survey and the location of all the essential tasks to be EXECUTED, so as to obtain a better level of service and good visibility after the works;
- A temporary signage plan for the site during the execution of the work.

ARTICLE 35: - ORGANIZATION AND SAFETY OF SITE
35.1 SECURITY OF WORKSITE
35.1.1 Construction Identification Signs
The identification or WORKS announcement signs will be placed at the beginning and at the end of each section, and must be put in place within a maximum of one month after the service order to start the work.
35.1.2 Signalisation of work
35.1.2.1 The work SIGNALISATION shall be in accordance with the temporary signalling plan validated in the execution PROGRAMME. It is carried out under the control of the Project Manager by the contractor, the latter having to support the supply and installation of signs and signalling devices, unless otherwise stipulated in the contract.
35.1.2.2 The contractor shall be personally liable for all direct or indirect consequences of a lack of signalling or the maintenance of temporary structures necessary for the maintenance of traffic.
35.1.2.3 All costs incurred by site-specific road signs are the responsibility of the Contractor. The latter will remain alone and fully responsible for all accidents or damage caused to third parties, during the execution of the work due to his equipment or errors and omissions concerning the signalling.
35.1.3 Night work, holidays and Sundays.
The works cannot continue neither at night, nor on Sundays, nor holidays without the prior written authorization of the CONTRACT Engineer.
35.2 MAINTAINING THE CIRCULATION
35.2.1 The CONTRACTOR shall take all necessary steps to ensure that the circulation is maintained throughout the duration of the work of each pass. He will not be able to use the subjections that would result to evade the obligations of his market, nor to raise any claim, except in case of force majeure;
35.2.2 The CONTRACTOR will refer to the project manager, who will inform the administrative authority with territorial jurisdiction for the taking of a regulatory act in case of interruption of traffic on a route. This referral must be done at least fourteen (14) days before.

ARTICLE 37: - SUBCONTRACTING
It is not allowed to use subcontracting.

Chapter IV: Acceptante

Article 41: Provisional Acceptance

ARTICLE 41: - ACCEPTANCE
The provisional acceptance of the works will be granted at the end of the execution of these works.
41.1- OPERATIONS PRIOR TO ACCEPTANCE
41.1.1 At the end of the works, the CONTRACTOR will make the request in writing to the Project ENGINEER with a copy to the CONTRACT MANAGER.
41.1.2 Within a period of seven (07) days from the date of submission of the request for acceptance, a prior visit will be organized by the Project Manager, with the participation of the CONTRACT Engineer, in the presence of the contractor.
This visit includes among other things:

- The qualitative and quantitative recognition of the work carried out;

- The possible finding of non-performance of the services provided for in the contract;

- The findings relating to the completion of the works;

- The route diagram of the executed works.

41.1.2 These operations are the subject of a report drawn up on the spot and signed by the Engineer, the Project Manager and countersigned by the contractor.
41.1.3 At the end of this pre-acceptance inspection, the Project Manager may specify the reserves to be lifted and the corresponding works to be carried out before the provisional acceptance date that the CONTRACT MANAGER will fix in agreement with the Engineer and the Contractor. Project Manager.
41.2- ACCEPTANCE COMMISSION
41.2.1 The ACCEPTANCE commission shall consist of the following members:
1. The CONTRACTING AUTHORITY or his representative: President;

2. The CONTRACT MANAGER, Member;

3. The CONTRACT Engineer, Rapporteur;

4. The DIVISIONAL DELEGATE OF MINMAP Bui or his representative, observer;

5. The Project Manager, Member;

6. The Contractor or his representative, observer.

7. The DD Environment

41.2.3 The aforementioned members and the contractor are summoned, by mail from the CONTRACT MANAGER, with a copy to the Representative of the PROJECT OWNER, to take part in the ACCEPTANCE VISIT, at least seven (07) days before the date of the ACCEPTANCE.
The absence of the CONTRACTOR is equivalent to the unreserved acceptance of the conclusions of the commission of receipt.
41.2.4 The Commission, under the direction of the President, after visiting the site, examines the report or the minutes of the operations prior to the reception and pronounces or not the provisional acceptance of the works.
This will be the subject of the minutes of provisional acceptance signed forthwith by all present members of the commission.
41.2.5 The provisional acceptance report shall fix the date of completion of the work.
41.2.6 In the event that the works cannot be received, notification is made to the contractor, by way of service order signed by the PROJECT OWNER, omissions, imperfections or defects noted that make it impossible to receive. This Service Order gives notice to the contractor to complete the incomplete works or to remedy imperfections and defects in a specified period, without prejudice to the application of the provisions of Article 77 of the GCC.
When the contractor considers that the works are completed, he must again ask the PROJECT MANAGER, provisional acceptance. After the period indicated in the service order, the CONTRACT MANAGER may have another contractor perform, in accordance with the regulations in force, the execution of the necessary works, the damages, costs, risks and perils of the CONTRACTOR. 
41.2.7 If the ACCEPTANCE Committee does not meet within fifteen (15) days of the favourable report prior to receipt, the CONTRACTOR cannot be held responsible for the consequences of this delay on the quality of the work EXECUTED.
41.2.8 At the end and after the acceptance of the works, the CONTRACT MANAGER will deliver to the CONTRACTOR, at his request, the certificate of completion.

ARTICLE 42: - DOCUMENTS TO BE PROVIDED
A SITE logbook will be kept by the Contractor and made available to the Project Manager and his representatives.
The CONTRACTOR may record incidents or observations that may give rise to a claim on its part.
The SITE logbook will be signed by both the Project Manager and the Site FOREMAN at each site visit.
For any claims of the CONTRACTOR, only events or documents mentioned in due time may be reported to the SITE logbook.

ARTICLE 43: - WARRANTY PERIOD AND MAINTENANCE DURING THE GUARANTEE PERIOD

  - Guarantee period

The period of guarantee is one year at from the date of provisional acceptance and concern only the MAINTENANCE works put in place.

  - Maintenance during guarantee period on hydraulic structures.

Article 44: Final acceptance

The procedure is the same as that of the provisional acceptance of works, after expiration of the period of guarantee. The acceptance commission will make sure the the hydraulic structure continue to function well.

Chapter V

SUNDRY PROVISIONS

Article 45: Termination of the contract

The contract may be terminated ipso jure by the Contracting Authority, as provided for in Title V, Chapter I, Section II, Sub-Section I of Decree No. 2018/366 of June 20, 2018 relating to the Public CONTRACT Code and also in the conditions set out in sections 74, 75 and 76 of the TS (Works), including any of the following:

- Death of the contractor. In this case, the PROJECT OWNER may, if necessary, authorize the acceptance of the proposals submitted by the rights holders for the continuation of the services;

- Bankruptcy of the holder of the contract. In this case, the PROJECT OWNER may accept, if applicable, proposals that may be submitted by the creditors for the continuation of the services;

- Judicial liquidation, if the co-contractor of the Administration is not authorized by the court to continue the operation of his business;

- In the case of subcontracting, subcontracting or subcommand without prior authorization from the Contracting Authority or the Contracting Authority;

- Failure of the Administration's co-contractor duly noted and notified to the latter by the Contracting Authority to the Contracting Authority;

- Non-compliance with labor legislation or regulations;

- Significant variation in prices under the conditions defined by the general administrative clauses, following the modification of the economic conditions or the initial quantities of the contract;

- Fraudulent maneuvers and corruption duly noted.

- The contract may also be terminated in the following cases:

- Delay of more than thirty (30) calendar days in the execution of a service order or unjustified termination of the work of more than seven (07) calendar days;

- - Accumulated penalties exceeding 10% of the T.T.C. amount of works;

- Refusal of resumption of poorly executed work;

- Failure of the contracting partner.

Article 46: Case of force majeure

46.1 Cases of force majeure shall be recorded in accordance with the provisions of Section 75 of the GCC.

46.2 It is the responsibility of the Delegated Contracting Authority to assess the nature of force majeure and the evidence provided by the CONTRACTOR.

Article 47: Disagreements and disputes

Any dispute or dispute arising between the contracting parties shall be the subject of an attempt at a friendly settlement.
In the absence of amicable settlement, any dispute arising from the contract will be brought before the competent Cameroonian jurisdiction, in accordance with the provisions of Article 187 of Decree No. 2018/366 of 20 June 2018 on the PUBLIC CONTRACT CODE.

Article 48: Production and dissemination of this contract

48.1 The drafting and formatting of the documents constituting the contract is done by the PROJECT OWNER.
48.2 The edition of this contract, in twenty (20) copies subscribed, is the responsibility of the PROJECT OWNER.

Article 49 and last: Entry into force of the contract

This contract shall be final only upon its signature by the Contracting Authority. It shall enter into force as soon as it is notified to the supplier by the Contracting Authority.

Document No. 5:

Technical specifications

SPECIAL TECHNICAL CLAUSES

SUMMARY

INTRODUCTION

CHAPTER 1: GENERAL INFORMATION

Article 1: Volume of work to be executed.

Article 2: General Instructions

CHAPTER II: ORIGIN AND QUALITY OF GEOMATERIALS AND CEMENT

Article 3: Quality and Quantity of Geo-materials

Article 4: Origin and quality of sand

Article 5: Origin and quality of gravel

Article 6: Origin and quality of stones

Article 7: Origin and quality of cement

CHAPTER III: CONCRETE WORKS

ARTICLE 8: PREPARATION OF CONCRETE

CHAPTER IV: METHOD OF EXECUTION

Article 9: General Information

9.1: Security at the work site

9.2: Traffic

Article 10: Stone Masonry

Article 11: Pointing and plastering

11.1 Pointing

11.2 Plastering

Article 12: Plumbing works

12.1 Pipe Specifications

12.1.1 Control tests on pipes

12.2 Fitting specifications

Article 13: Piping

13.1 Description

13.2 Care/Laying of pipes

13.3 methods of determining quality of G.I and PVC piping laid.

CHAPTER V: CONSTRUCTION METHODS

Article 14: Setting out of Works

Article 15: Excavation of Trenches

Article 16: Backfill

Article 17: Maintenance of Excavations

CHAPTER VI: WORK EVALUATION METHOD

Article 22: Calculation of the Level of Realization.

INTRODUCTION

The technical specifications presented herein below define the waterworks that shall be executed For the Rehabilitation And Extension of Potable Water to Nseh, Nkum Sub Division, Bui Division of the North West Region and the manner in which these works shall be carried out. So the Contractor is expected to read these specifications critically and identify all the articles that are applicable to his job

CHAPTER 1: GENERAL INFORMATION

ARTICLE 1: VOLUME OF WORK TO BE EXECUTED.

In each case, the volume of work to be executed is indicated by the bill of quantities, network maps and/or plans provided for each project. The various works to be executed shall conform to the relevant terms of the technical specifications given herein below.

ARTICLE 2: GENERAL INSTRUCTIONS

It should be understood that the provision of a bill of quantities for any project does not absolve the potential Contractor of the necessity to affect a well-planned site visit, at his own expense, to gain complete knowledge of the conditions prevailing on the terrain. This knowledge shall come in handy when preparing the List of Tasks and the Unit Price Schedule. Potential Contractors (or Bidders) shall provide a detailed and sequenced List of Tasks to be effected on each component of the project. Within fifteen (15) days from the date of notification to start work, the contractor shall provide the Supervising Engineer with:

-A detailed plan of the work, showing the scheduling of the various works to be executed in time

-Detailed technical drawing of the works to be realized

-A manpower deployment plan

-A schedule of the delivery of materials to the project site, showing possible delays

-Failure to forward the foregoing documents shall engender the postponement of the reception of project materials, which could result in a punishable overall delay in the execution of the project.

No material shall be used that has not been checked for conformity with the technical specifications by the Supervising Engineer.

The Supervising Engineer reserves the right to modify the plans and Work schedule provided by the Contractor, which modification shall first be submitted to the Delegated Contracting Authority for approval. Under exceptional circumstances, the Supervising Engineer may suggest modifications to the technical specifications for any component of a project to the Delegated Contracting Authority, while making sure that the overall cost of the project stays within the limits of the financial bid of the Contractor.

Any modification must be done in writing, with sufficient justification. For this purpose, a numbered page book (the project log book) shall be kept on site in which the Supervising Engineer shall write his approved instructions. Both the Contractor, or his representative, and the Supervising Engineer shall initial every page of the project logbook

It is therefore obligatory for the contractor to execute the works in conformity with:

-The Bills of Quantities and Estimates,

-The Special Administrative Clauses

-The Special Technical Clauses stated herein,

-Any other special rules and regulations that may be applicable to his job,

-The work schedule,

-The detailed technical drawings,

Subject to any approved modifications indicated in the project log book by the Supervising Engineer.

The Contractor shall take note of any omission or discrepancies that may exist in the three documents mentioned in the preceding paragraph, which omission or discrepancies could fundamentally affect the technical or aesthetic quality of the works executed to his detriment, and call the attention of the Supervisory Engineer who shall remain at his disposal of the Contractor for necessary information and inquiries through the duration of the project.

In this regard, the Contractor shall not absolve himself of the responsibility for poor quality work by citing imprecision, omissions or discrepancies in the technical specifications or modifications thereof indicated in the project log book by the Supervising Engineer.

Any works effected without regard for the foregoing instructions or provisions shall be demolished at the expense of the Contractor

CHAPTER II: ORIGIN AND QUALITY OF GEOMATERIALS AND CEMENT

ARTICLE 3: QUALITY AND QUANTITY OF GEOMATERIALS

The Contractor shall supply all the sand, stones and gravel that may be required for the execution of any component of a project. He shall also be responsible for the excavation and backfilling of the pipeline under the supervision of the Engineer. In that regard, it is obligatory for the potential Contractor (or bidder) to visit the project site, at his own expense, before preparing his bids, in order to verify whether available geo-material are of good quality and of sufficient quantity. He shall make any reservations concerning geo-materials in his bid.

ARTICLE 4: ORIGIN AND QUALITY OF SAND

The nature and origin of sand remain subject to the approval of the Supervising Engineer.  Sand shall be obtained either from rivers or through crushing of rocks. The sand shall be of high quality. It shall be crunchy, stable, clean and shall be free of dust particles, schistose, gypseous or clayey debris and organic matter. It shall contain neither sulphur compounds no substances that can react with cement or metallic reinforcements. The sand component shall be more than 80% and the very fine constituents, with a dimension not exceeding eighty (80) microns that can be eliminated by settling, should be less than four percent (4%). No grain of sand should have a dimension greater than four (4) millimeters. If deemed necessary by the Supervising Engineer, the sand shall be sieved and washed thoroughly before use.

Moreover, filter grade sand shall have a grain size ranging from 0.8mm to 1.2mm inclusive. Furthermore, it shall be fried in order to eliminate algae zygospores, bacteria and/or bacteria spores, fungi and/or fungal hyphae.

ARTICLE 5: ORIGIN AND QUALITY OF GRAVEL.

Gravel shall be obtained from deposits or quarries chosen by the contractor and approved by the Supervising Engineer. It shall be clean, without an excess of flat elongated pieces, dust or impurities. Constituents that can be eliminated through settling should be less than 2%.Its grading should be suited to its use. If deemed necessary by the Supervising Engineer, it shall be washed before use.

ARTICLE 6: ORIGIN AND QUALITY OF STONES

Stones shall be obtained from deposits or quarries chosen by the Contractor and approved by the Supervising Engineer. No stone shall have a dimension less than twenty (20) centimeters. Basalts stones, commonly called black stones, are highly recommended, or else stones of other quality, such as un-weathered  granites, rhyolites, ignimbrites, etc, duly tested and approved by the Supervising Engineer may also be used.

ARTICLE 7: ORIGIN AND QUALITY OF CEMEMT

Cement shall be of the CPA 325 class and shall be obtained from an approved factory.

CHAPTER III: CONCRETE WORKS

ARTICLE 8: PREPARATION OF CONCRETE

Concrete works shall be of three (3) kinds:

- Mass concrete for foundations works; it shall be a mixture of 250kg of cement per m3 of sand and of appropriate thickness.

- Re-enforced concrete for floor and roof slabs and slab covers for storage tanks, valve chambers and interruption chambers; it shall be a mixture of 350kg of cement per m3 of sand and shall be of appropriate thickness.

- Mass concrete for catchment’s works; it shall be a mixture of 400kg of cement per m3 of sand.

CHAPTER IV: METHOD OF EXECUTION

ARTICLE 9: GENERAL INFORMATION

9.1 SECURITY AT THE WORK SITE

The contractor shall place at the entrance to work site signboards in bold letters indicating that work is underway and prohibiting the public and unauthorized persons from entering the work site. He shall be responsible for any accident that may occur on the work site or may be suffered by a third party, his staff and employees or officials of the Administration as a result of their presence on the work site. Organization of work and security on the work site shall therefore be the sole responsibility of the Contractor. Furthermore, the Contractor shall be bound by the labour legislation in Cameroon vis-a vis his workers and the Administration. Moreover, his insurance policy shall cover any damages he could cause to any one during the execution of the job.

9.2 TRAFFIC

The Contractor shall be responsible for ensuring that traffic is not obstructed on the entire stretch of his work site throughout the period of work, right up till provisional reception. No obstruction of traffic shall be allowed for more than two hours. Maintenance of traffic flow shall be the responsibility of the Contractor. In  case of any breach of contract in this matter , the Supervising Engineer may bring in a third party to correct any shortcomings that may be impeding the traffic flow, and related expenses shall be borne by the Contractor.

Where interference of the traffic flow for a given period is inevitable, the Supervising Engineer shall be informed of the situation at least 7 days in advance, so that he can seek the opinion of local Administrative authorities and get everything arranged beforehand.

In case a deviation has to be used, the contractor shall submit to the Supervising Engineer for approval after consultation with local administrative authorities, the deviation route and his plan for maintaining the deviation throughout the duration of the works that have necessitated the deviation.

ARTICLE 10: STONE MASONRY

Stone masonry shall be aesthetical and in accordance with structure type and civil engineering rules.

Binding mortar shall be a mixture of 400kg of cement per m3 of sand, no grain of which shall have a dimension exceeding 4mm.

Mortar containing a mixture of 450kg of cement per m3 of sand shall be used for the finishing of the external joints of non-visible walls of stone masonry

Mortar consisting of a mixture of 500kg  of cement per m3 of sand, to which shall be added a quantity of SIKA Nº 1 recommended by the manufacturer and approved by the Supervising Engineer, shall be used for waterproofing the interior  surfaces of water-retaining structures (storage tanks, interruption chambers, sedimentation basin, filters, etc).

ARTICLE 11: POINTING AND PLASTERING

11.1 POINTING

The joints of all external walls of stone masonry that are visible shall be carefully pointed to give them an aesthetic look. Mortar containing 600kg of cement per m3 of sand shall be used for pointing with a cement paste (1:0) finish

11.2 PLASTERING

Plastering of surfaces in contact with water shall comprise pointing of the mortar joints followed by a 1cm thick layer of spatter dash 1:2 (m625). This shall then be followed by the application of a rendering coat of 2cm thick 1:4 (m300) mixtures and a setting coat 2cm thick 1:2 (m625).The walls shall then be finished with cement paste. Plastering of surfaces not in contact with water, such as chambers for air valves, control valves and washouts shall consist of 1 coat of plaster 1cm thick and a mixture of 1:3 (m400)

ARTICLE 12: PLUMBING WORKS

By pluming works include:

- Laying of pipes in the trenches

- Construction and installation of chambers for air valves, washouts and control valves

- Installation of branch lines right up to the last plastic before the standpipes.

12.1 PIPE SPECIFICATIONS

Pipes should meet the physical characteristics presented in table1 below:

Table 1: Physical Characteristics of pipes

| Internal Ø &external Ø (mm) | Thickness (mm) |  |  | Socket length (mm) | Nominal service pressure (bars) | Length of pipe (m) |
| --- | --- | --- | --- | --- | --- | --- |
|  | Minimum | Nominal | Maximum |  |  |  |
| 21x25 | 1.9 | 2.0 | 2.3 | 28 | 10 | 6 |
| 28x32 | 1.9 | 2.0 | 2.3 | 32 | 6 | 6 |
| 26.8x32 | 2.4 | 2.6 | 2.9 | 32 | 10 | 6 |
| 35x40 | 2.3 | 2.5 | 2.8 | 40 | 6 | 6 |
| 33.6x40 | 3.0 | 3.2 | 3.5 | 40 | 10 | 6 |
| 43.6x50 | 3.0 | 3.2 | 3.5 | 50 | 6 | 6 |
| 42x50 | 3.7 | 4.0 | 4.3 | 50 | 10 | 6 |
| 56.6x63 | 3.0 | 3.2 | 3.5 | 63 | 6 | 6 |
| 53x63 | 4.7 | 5.0 | 5.4 | 63 | 10 | 6 |
| 68.6x75 | 3.0 | 3.2 | 3.5 | 75 | 6 | 6 |
| 66.6x75 | 3.8 | 4.2 | 4.5 | 75 | 10 | 6 |
| 63.2x75 | 5.5 | 5.9 | 6.3 | 75 | 10 | 6 |
| 80.6x90 | 4.3 | 4.7 | 5.0 | 90 | 6 | 6 |

TOLERANCES

OVALIZATION: ± 1mm

Length of pipe: ± 1% =>±6cm

Socket length: ± 0.6mm

12.1.1 CONTROL TESTS FOR PIPES

i) Length

The tolerance for pipe lengths shall be ± 1% (± 6cm). For every 100 pipes, if the number of pipes not respecting this tolerance is less than 3 i.e. 3%, then the whole lot shall be considered okay, otherwise the Supervising Engineer shall request that as many pipes as possible be tested in the lot.

ii) External Diameter

The tolerance shall be ± 0.3mm for pipes of external diameters between 25mm and 50mm, and ± 0.4mm for pipes between 63mm and 75mm in external diameter. Before reception, the Supervising Engineer shall verify the external diameters of 15 pipes for every 300 pipes. If 6 or more pipes fail to meet the tolerances prescribed above, he shall reserve the right to reject the whole lot. If 5 pipes fail to meet the tolerance stipulated above, 15 other pipes shall be selected at random from the same lot and verified. If the same results are obtained for 5 pipes, the whole lot shall be rejected.

iii) Thickness

Thickness verification should adhere to the specifications presented in table II below.

Table II: Thickness Verification

| No. of pipes in the lot | No. of pipes randomly selected for verification | No of bad pipes X |  |
| --- | --- | --- | --- |
|  |  | Lot accepted if X max = | Lot rejected if Xmin= |
| 100-199 | 10 | 2 | 3 |
| 200-299 | 15 | 3 | 4 |
| 300-499 | 20 | 3 | 4 |
| 500-899 | 25 | 5 | 6 |
| 899-1300 | 30 | 6 | 7 |
| 1300-3200 | 40 | 8 | 9 |

The Supervising Engineer shall carry out thickness verification in accordance with table II above

iv)  Socket length

The socket length shall be verified according to agreed norms. The value obtained should have the theoretical value of the diameter of the tube plus 1.3mm. The tolerance shall be 0.6mm

v) Shrinkage cracks

Shrinkage cracks tests should be carried out according to agreed methods by the Supervising Engineer on a 15-30cm long sample. No shrinkage cracks should occur if the pipe is at 90º to its horizontal axis. If this occurs for 15 samples representing a lot of 100 pipes, the lot shall be rejected.

vi)  Internal Pressure

Pipe samples shall be subjected to 1.5 times the service pressure for duration of one hour. If one out of every five samples ruptures, another set of five shall be selected for retest. If the second set respects the specified relation with the service pressure, the set shall be considered satisfactory. Otherwise, either necessary adjustments shall be carried out to meet the required specifications, or the lot shall be rejected.

vii) Impact

This test shall be carried out on three samples, one from each extremity and the third, from the center, all three, one meter long. Perpendicular masses shall be dropped from a height of one meter onto the samples as shown in table III.

Table III: Impact Test Schedule

| Pipe diameter | Mass (kg) |
| --- | --- |
| 25 | 1 |
| 32 | 1 |
| 40 | 1 |
| 50 | 3.5 |
| 63 | 5 |
| 75 | 7.5 |
| 90 | 7.5 |

The pipes shall be accepted if, and only if, the percentage of broken pipes in the tested samples does not exceed 40%

viii) Labels

The Contractor shall ensure that all pipes for this project are labeled <H>.The Supervising Engineer shall reject any pipe not labeled as such

The Contractor shall furnish the Supervising Engineer with information (name, address, phone, etc) on the factory being used to procure pipes for any project.

The Contractor shall present to the Supervising Engineer a guarantee certificate from the factory of origin ascertaining that the pipes meet the required standards as described in the forgoing sections. The Contractor shall arrange for free access to the factory for the Supervising Engineer to enable him request, as required, for all factory tests described in the aforementioned sections to be carried out by the manufacturer.

The performance guarantee of works shall cover all defects in pipes, their handling and workmanship.

FITTINGS SPECIFICATIONS

The fittings required for these works, are presented in Table IV below. Contractors are required to strictly respect these specifications.

All fittings shall be approved by the Supervising Engineer before use. All fittings not conforming to those specified in Table IV shall be rejected. The performance guarantee of work shall cover all defects in fittings, their handling and workmanship.

TABLE IV: SPECIFICATIONS FOR FITTINGS

| Description of Goods |  | Description of Goods |
| --- | --- | --- |
| ADAPTOR UNION 25-¾” |  | NIPPLE 2” |
| ADAPTOR UNION 32-1” |  | NIPPLE 2½” |
| ADAPTOR UNION 40-1 ¼” |  | PVC ELBOW 63 |
| ADAPTOR UNION 50-1 -½” |  | PVC RED SOCKET 40-32 |
| ADAPTOR UNION 63-2” |  | PVC RED SOCKET 50-40 |
| ADAPTOR UNION 75-2½” |  | PVC RED SOCKET 63-50 |
| AIR VALVES |  | PVC RED SOCKET 75-50 |
| BALL VALVE 1 ½” |  | PVC RED SOCKET 75-63 |
| BALL VALVE 2” |  | PVC TEE 32 |
| DEC VALVE 0¾” |  | PVC TEE 40 |
| DEC VALVE 1 ¼” |  | PVC TEE 50 |
| DEC VALVE 1½” |  | PVC TEE 63 |
| DEC VALVE 2” |  | PVC TEE 75 |
| DEC VALVE 2½” |  | PVC VALVE 32 |
| ELBOW 0¾” |  | PVC VALVE 40 |
| ELBOW 1 ¼” |  | PVC VALVE 50 |
| ELBOW 1 ½” |  | PVC VALVE 63 |
| ELBOW 2” |  | PVC VALVE 75 |
| ELBOW 2 ½” |  | REDUCER G.I.1”-¾” |
| FLOAT VALVE 63 |  | PVC RED SOCKET 75-63 |
| G.I PIPE 0¾” |  | SADLE PIECE 32-1” |
| G.I PIPE 1” |  | SADLE PIECE 40-1 |
| G.I PIPE 1¼” |  | SADLE PIECE 50 |
| G.I PIPE 1½” |  | SADLE PIECE 50-1” |
| G.I PIPE 2” |  | SADLE PIECE 63 |
| G.I PIPE 2½” |  | SADLE PIECE 63-1” |
| G.I SOCKET 0¾” |  | SADLE PIECE 75-1” |
| G.I SOCKET 1¼” |  | TAP 0¾” |
| G.I SOCKET 1½” |  | UNION 0¾” |
| G.I SOCKET 2” |  | UNION 1” |
| G.I TEE 1” |  | UNION 1 ¼” |
| G.I TEE 1¼” |  | UNION 1 ½” |
| G.I TEE 1½” |  | UNION 2 “ |
| G.I TEE 2” |  | UNION 2½” |
| G.I TEE 2½ |  | NON RETURN VALVE 2” |
| NIPPLE 0¾” |  | GEBAJOINT |
| NIPPLE 1” |  | GLUE 1 kg |
| NIPPLE 1¼” |  | HERM (ROLL) |
| NIPPLE 1½” |  | SAND PAPER ( ml) |

ARTICLE 13: PIPING

13.1 DESCRIPTION

This item shall consist of the supply and lying of all pipes, including the installation of accessories like couplings, tees, reducers, etc. etc. to entirely complete this item as per these specifications and plans provided.

13.2 CARE/LAYING OF PIPES

The soil in the bottom of the trench shall be lightly scarified before laying the pipes or other hydraulic elements.

During transport, storage, and assembling of piping element care shall be taken to avoid soil and other contamination from entering the system.

Lying of pipes, assembling of pipes and all other works directly related to piping works, shall only be executed during dry weather conditions.

Pipe elements and connecting accessories shall be assembled in such a way that no tension can occur in the separate elements.

Only skilled plumbers shall be employed on any plumbing work.

Pipe joints, reducers, tees, etc shall be connected in conformity with the manufacturer’s prescriptions

13.3 METHOD OF DETERMINING QUANTITY OF G.I AND PVC PIPING LAID

The quantity of PVC and G.I piping laid shall be measured per linear meter of laid pipe. Measurements shall be made for each class of pipe and each diameter of pipe separately.

CHAPTER V: CONSTRUCTION METHODS

ARTICLE 14: SETTING OUT OF WORKS

The contractor shall be responsible for the setting out of all pertinent lines, works, grades, reference points and levels that may be required for the proper and accurate positioning of all the structures on the work site. The works so set out shall be received by the Supervising Engineer before construction work actually begins

ARTICLE 15: EXCAVATION OF TRENCHES

Pipe trenches shall be excavated to a depth of at 60cm and at most 100cm and width of 40cm.The bottom of each trench shall be free of any stones or other materials which could damage the pipes.

ARTICLE 16: BACKFILL

The Contractor shall be responsible for all backfill operations. However, such operations shall only be carried out after the dimensions of the trenches have been approved by the Supervising Engineer.

After the pipes have been laid in the trenches by qualified plumbers, and the successful hydraulic tests conducted, they shall be carefully covered with soil and rammed in, in soil layers of 20cm thick.

The backfilling of pipes crossing motor able roads shall be done in conformity with laid down norms. The compaction requirement for backfill shall be at least 90% of the dry modified optimum proctor density.

ARTICLE: 17.  MAINTENANCE OF EXCAVATIONS

The Contractor shall bear the risk associated with the collapse of any surface exposed as a result of excavation effected anywhere on the work site, whether or not he takes any precautions against such accidents. The nature of the precautions he may take shall be entirely at his discretion. No water shall be allowed to accumulate in any part of an excavation. For that reason, every excavation shall be protected against flooding, seepage, run-off, etc. should water accidentally enter any excavation; it shall be immediately removed by pumping or bailing at the expense of the Contractor.

CHAPTER VI: WORK EVALUATION METHOD

ARTICLE 18. CALCULATION OF THE OVERALL LEVEL OF REALISATION

Each month, the overall level of realization shall be calculated using field data and the unit prices quoted by the Contractor in the Unit Price Schedule.

ARTICLE 19. DESCRIPTION OF STORAGE TANK:

The storage tank shall have an effective water volume of 30m3. The internal diameter (Di) of the tank shall be 4.6m and the height (H) on the floor of the tank to the under-roof of the tank shall be 2.2m to have an effective and useful storage volume of 30m3.

ARTICLE 20. DESCRIPTION OF SEDIMENTATION BASIN:

The sedimentation basin shall be connected to the filters as a single unit constructed in stone masonry.

ARTICLE 21: ENVIRONMENTAL IMPACT NOTICE

Planting of carpet grass within the fenced area of the storage tank and the treatment plant.

PROPOSED WORKING DRAWINGS

Document No. 6:

Unit price schedule

UNIT PRICE SCHEDULE

GENERALITIES

The prices in this slip include all the constraints imposed on the execution of the work as well as the local conditions that may affect their performance and cost.

The prices include in particular the labor, the supply of material and materials, the rent, the depreciation, the operation and the maintenance of the material, the transport costs of the personnel, the allowances, the agreement of the local residents for the rejection of weeding or removal products and all things necessary for the proper execution of the work.

These prices also include bonuses, insurance and social security charges due to various staff and all local taxes and fees related to good signage on the site.

The Contractor is responsible for accidents of all kinds that would occur and where the presence of the site would be questioned.

Overhead costs applied to all prices are deemed to include the installation of two information panels positioned at each end of the site, as defined by the Project Manager.

Document No. 7:

Bill of quantities and cost estimates

Document No. 8:

Sub detail of breakdown of unit price

SUB-DETAIL MODEL OF BREAKDOWN PRICES

| PRICE SUB-DETAIL |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | DESIGNATION : |  |  |  |
| PRICE N ° | Daily yield | Total quantity | Unité | Activity duration |
|  | CATEGORIES | Daily salary | Billed days | Amount |
| WORKFORCE |  |  |  |  |
|  | TOTAL A |  |  |  |
| EQUIPMENT AND EQUIPMENT | TYPE | Daily rate | Billed days | Amount |
|  | TOTAL B |  |  |  |
| MATERIALS AND MISCELLANEOUS |  |  |  |  |
|  | TOTAL C |  |  |  |
| D | DIRECTS TOTAL COST A+B+C |  |  |  |
| E | Construction site overhead | % | = Dx% |  |
| F | Headquarters overhead | % | = Dx% |  |
| G | RETURN COST OF | - | = D+E+F |  |
| H | Risks and Benefits | % | GX% |  |
| P | SALE PRICE EXCLUDING TAXES |  | = G+H |  |
| V | UNITARY SALE PRICE WITHOUT TAXES |  | = P/Quantity |  |

Document No. 9:

Draft contract

Structure of a contract

Summary

Part I:	   Special Administrative Conditions (SAC)

Part II:   Description of supplies

Part III:  Schedule of Prices and Quantities

Part IV:  Execution calendar

| REPUBLIC OF CAMEROON Peace – Work – Fatherland ************ |  | REPUBLIQUE DU CAMEROUN Paix – Travail – Patrie ************ |
| --- | --- | --- |
| MINISTRY OF DECENTRALISATION AND LOCAL DEVELOPMENT ************ |  | MINISTÈRE DE LA DÉCENTRALIZATION ET DEVELOPPEMENT AND LOCAL ************ |
| NORTH WEST REGION ************ |  | REGION DU NORD OUEST ************ |
| BUI DIVISION ************ |  | DEPARTEMENT DU BUI ************ |
| JAKIRI COUNCIL ************ |  | COMMUNE DE JAKIRI ************ |
| JAKIRI COUNCIL INTERNAL TENDERS BOARD ************ |  | COMMISSION INTERNE DE PASSATION DES MARCHE DE LA COMMUNE DE JAKIRI |

JAKIRI COUNCIL INTERNAL TENDERS BOARD.

CONTRACT No 06/C/JAKIRI COUNCIL/JCITB/2026 OF 05/03/2026 FOR THE CONSTRUCTION OF A FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

# Awarded after an Open National Invitation to Tender

N° 05/ONIT/JAKIRI COUNCIL/JCITB/2026 OF 23/01/2026

FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

HOLDER (ETS Address): ……………………………………..

P.O BOX ………  TEL.…………………………Fax: ………………..

Trade register N°(N° R.C.): ……………………………………..

TAX PAYER N°: …………………………………

BANK ACCOUNT N°: ……………………………AT………………………… (Bank)

AGENCY OF: ……………………………………..

# SUBject: …………………………………………………………………………………

Execution deadline: …………………………………………………………………….

# Amount in FCFA:

| Amount tax inclusive |  |
| --- | --- |
| Amount without Taxes |  |
| VAT (19.25) |  |
| A.I.R. (2.2 or 5.5 %) |  |
| Net Payable |  |

Financing: …………………………………

Budget Head: ……………………………….

# Location: ……………………………………….

# ENTERED on: _______________________

# Signed on: ____________________________

# Notified on:  __________________________

Registered on: _______________________

# BETWEEN:

The Government of the Republic of Cameroon, represented by the Mayor of Nkor Council hereinafter referred to as the “The Contracting Authority”

# ON THE ONE PART,

# AND

# Enterprise ……………………………………..

Whose head office is at ………………………….

Hereinafter referred to as the “Contractor”

Represented by its Director, Mr./Ms …………………………………………………..

Address:	P.O. Box …………………………. Tel ………… Fax ……………

Business Registry No ……………………………….

Tax Payers’ Card No …………………………………….

# ON THE OTHER PART

# IT IS HEREBY AGREED AND ORDERED AS FOLLOWS:

# SUMMARY

Part I:	Special Administrative Clause (SAC)

Part II:	 Special technical Clauses (STC)

Part III: Schedule of Unit Prices

Part IV: Details or Estimates

Page ………… and last of CONTRACT No 06/C/JAKIRI COUNCIL/JCITB/2026 OF 06/03/2026 awarded after an Open National Invitation to Tender N° 06/ONIT/JAKIRI COUNCIL/JCITB/2026 OF 23/01/2026

With …………………………………

__________________COMPANY

P.O. Box ______ at ___ Tel ____ Fax: ______

Business Registry No. ____ A

Taxpayer’s No. _______

FOR THE CONSTRUCTION OF FAAKUI WATER SCHEME IN JAKIRI- COUNCIL, BUI DIVISION OF THE NORTH WEST REGION

Execution DEADLINE: FOUR (04) MONTHS

# Amount of CONTRACT in FCFA:

| Amount tax inclusive |  |
| --- | --- |
| Amount without Taxes |  |
| VAT (19.25) |  |
| A.I.R. (2.2 or 5.5%) |  |
| Net Payable |  |

Read and accepted by the Contractor JAKIRI ………………. (date)

Signed by the LORD MAYOR NKOR COUNCIL JAKIRI………………… (date)

Registration

DOCUMENT No. 10:

Model documents to be used by bidders

Model table

Annex 1: Declaration of intention to tender.

Annex 2: Tender Template.

Annex 3: Bid bond template.

Annex 4: Final bonding model.

Annex 5: Model of advance loan guarantee.

Annex 6: Model of guarantee retainer.

Annex 7: Model of commitment of availability

Annex 8: Model of references of the Enterprise

Annex 9: Model of equipment list

Annex 10: Model of key staff

Annex 11: Model of site visit report

ANNEX No. 1: DECLARATION FORM

THE MODEL UNDERTAKING BY THE BIDDER

Name of project:………………………..Invitation to tender No. :…………………

For ………………………………………………..

I (We) the undersigned (8) …………………………………………………………….

Acting in the capacity of (9) ……………in the name and on behalf of (10)…………………………………………………. at …………………….RC No. …………………by virtue of the power vested in me (us), domiciled at P.O.Box……………. (Town) ………………, telephone N° ………………………., after having studied all the documents of the tender file relating to the Invitation to Tender N° …………………………….., and after having assessed in my (our) point of view and under my (our) responsibility the nature and difficulties entailed with the execution of the job, I (we) do hereby tender and commit myself (ourselves) to carry out works for  ……………………………………………………… in keeping with the terms and conditions of the tender file.

I commit myself (We commit ourselves) in case my (our) tender is retained, to execute the contract within ……………… (……………………) months as from the date of notification of award of the contract.

I hereby commit myself (We hereby commit ourselves) to maintain the amount of my (our) tender for a period of ninety (90) days with effect from the deadline for submission of bids.

Done at ……………………………. , on ………………

General Manager

Signature(s)…………………….

Biddder(s)………………………………….

For companies, indicate:

The company (company or trade name, form, nationality and registered office)

« represented by the undersigned ……………………………… » (name, first name and status)

For companies without a legal status, indicate:

« We, the undersigned, ……………………………………………………………………. »

(For each person: name, first name, company name, nationality, location of the registered office)

« Constituted in a group of companies for the execution of this contract, jointly commit ourselves …….. »

(8) Name, first name, profession, residence

(9) Position in the enterprise

(10) Company name

Annex 2: Tender Template

I, the undersigned ... ............................... ............ [indicate the name and the quality of the signatory] representing the company, the company or the group ........................ .............. ... .. ... whose head office is at .......... ... .... .......................... .... registered in the commercial register of ......... ............... ........................ ... under the number .................. ..... ............................. ......

After having read all the documents appearing or mentioned in the tender documents including the addendum (s), the invitation to tender [recall the number and subject of the Call Offers]

- After having personally visited the site of the works and having greatly appreciated the situation and noted the nature and constraints of the work to be done

- Remits, bearing my signature, the list of unit prices and the estimate established in accordance with the frameworks in the tender dossier.

- Submit me and undertake to perform the work in accordance with the tender documents, for the prices I have established for each type of work, which prices show the amount of the offer for Lot No ......... ............. to

-	………........................................... [in numbers and in letters] Cfa francs Excluding VAT, and

......... .............................. CFA Francs All Taxes Included. [in figures and in letters]

- I undertake to perform the work within a period of ......... ............. months

- Also commit myself to maintain my offer within the time limit ......... ............. days [indicate the period of validity, in principle 90 days for the NSO and 120 days for the ICB ] from the deadline for submission of tenders.

- The discounts and the conditions of application of the said rebates are the following ones (in case of possibility of attribution of several lots):

The Client will release the sums due by him under this contract by giving credit to the account n ° .................. ................. opened at name of …................................…. at the bank ... ................................ ............... Agency of ... ..... ......................... ........................ ..

Before signing the contract, the present bid accepted by you will be worth engagement between us.

Made in ………....................……. the ………...............................…….

Signature of ......... ........................................... ...... ....

in quality of ………..................................……. duly authorized to sign the tenders for and in the name of ......... .................................... ....... ..........

Annex 3: Model Bid Deposit

A [indicate the Delegated Contracting Authority and its address], "the Contracting Authority"

Whereas the company ............... .......................... ......... .., hereinafter referred to as "the biddder" , submitted its offer dated ............... .......................... ......... .. to [recall the subject of the Invitation to Tender], hereinafter referred to as "the offer", and for which it must attach a provisional bond equivalent to [insert amount] CFA francs,

We ............ .................... ... ........................ .. ......... .. [name and address of the bank], represented by ............... .......................... ... ...... .. [names of signatories], hereinafter referred to as "the bank", declare to guarantee payment to the Delegated Contracting Authority of the maximum sum of [insert amount] CFA Francs, which the bank undertakes to pay in full to the Contracting Authority, binding itself, its successors and assigns.

The conditions of this obligation are as follows:

If the biddder withdraws his tender during the period of validity laid down in the Tender Documents;

or

If the biddder has been notified of the award of the contract by the Delegated Contracting Authority during the period of validity:

- to sign or refuse to sign the contract, while it is required to do so;

- fails or refuses to provide the final contract security (final bond), as provided for in the contract.

We undertake to pay to [Contracting Authority] an amount up to the maximum of the sum stipulated above, upon receipt of its first written request, without the Delegated Contracting Authority having to justify its request, provided, however, that in its request, the Delegated Contracting Authority will note that the amount claimed by the Delegated Contracting Authority is due to it because one or both of the above conditions, or both, are met, and that it will specify which (s) condition (s) has (have) played.

This deposit shall enter into force upon signature and from the date fixed by the Delegated Contracting Authority for the submission of tenders. It will remain valid until the thirtieth day inclusive after the end of the period of validity of the offers. Any request from the Delegated Contracting Authority to have it played shall reach the bank by registered letter with acknowledgment of receipt, before the end of this period of validity.

This deposit is subject for its interpretation and execution under Cameroon law. The courts of Cameroon shall have exclusive jurisdiction to rule on all matters relating to this undertaking and its consequences.

Signed and authenticated by the bank

to ............... .......................... ......... .., the ............... ...... .................... ......... ..

[bank signature]

Annex 4: Final Bond Model

Bank:

Reference of the Deposit: N ° ............... .................................. .......... .

A [indicate the Client and his address] Cameroon, hereinafter referred to as the Employer "

Whereas; ... ................................................... ........... [name and address of the undertaking], hereinafter referred to as "the contractor", undertook, in execution of the designated contract "the contract", to carry out [indicate the nature of the work ]

Whereas he; is stipulated in the contract that the contractor will give the Client a final bond, equal to [indicate the percentage between 2 and 5%] of the amount of the works of the corresponding contract, as a guarantee of the execution performance obligations in accordance with market conditions,

Whereas; we agreed to give the contractor this bond.

We,................................................ .......................... ......... .. [name and bank address], represented .......... .................................................. .... .......... ... .. [names of signatories], hereinafter referred to as "the bank", we undertake to pay to the Owner, within a maximum period of eight (08) weeks, upon request in writing stating that the Contractor has not fulfilled its contractual obligations under the Contract, without being able to defer payment or raise any dispute for any reason, any amount up to ... .............................................. .......... [in figures and in letters].

We agree that no changes or additions or other changes to the Market will release us from any obligation under this Final Bond and we hereby waive any change, addendum or change.

This final bond shall take effect upon signature and upon notification of the contract. The deposit is released within [insert time] from the date of provisional acceptance of the work.

After the aforementioned period, the deposit becomes moot and must be automatically returned to us without any form of procedure.

Any request for payment made by the Client under this guarantee must be made by registered letter with acknowledgment of receipt, received at the bank during the period of validity of this commitment.

This final guarantee is submitted for its interpretation and execution under Cameroonian law. The Cameroonian courts will have exclusive jurisdiction to rule on all matters relating to this undertaking and its consequences.

Signed and authenticated by the bank

to ............... .......................... ......... .., the ............... ...... .................... ......... ..

Annex 5: Model of a Start Advance Bond

Bank: reference, address ............... ........................................ ......................................

We the undersigned (bank, address), declare hereby guarantee, on behalf of: ............... .......................... .................................................. ........ [the holder], for the benefit of the Owner [Address of the Owner]

(" The beneficiary ")

Payment, without dispute and upon receipt of the first written request of the beneficiary, declaring that ............ ................. ...... .. [the holder] does not has not paid its obligations, relating to the repayment of the start-up loan according to market conditions ............ ................. ...... .. of ... ........................... ...... .. relating to the work [indicate the purpose of the work, the references of the Call for Tenders and the lot, if possible], of the maximum total sum corresponding to the advance of [twenty (20)%] of the amount of all taxes included in the contract No ............ ........... ................................, payable upon notification of the corresponding service order, that is: ......... ... .......................................... ...... .. CFA francs

This guarantee will come into effect and will take effect after transfer of the respective shares of this advance to the accounts of ............ ......................... ..................... ... .. [the holder] open at the bank ...... ............... .. ...... .. ............ ................. ...... .. under number ............ ........... ...... ...... .. ............ ................. ...... ..

It will remain in effect until repayment of the advance in accordance with the procedure set by the SCC. However, the amount of the deposit will be reduced proportionately to the repayment of the advance as and when repayment.

The law and jurisdiction applicable to the guarantee are those of the Republic of Cameroon.

Signed and authenticated by the bank

to ............... .......................... ......... .., the ............... ...... .................... ......... ..

[bank signature]

Appendix 6: MODEL RETENTION FUND

Bank: ............ ........................... ........................

Reference of the Deposit: N ° ............ ........................... ........................

A [indicate the Owner]

[Address of the Contracting Authority]

hereinafter referred to as "the Client"

Whereas; ............ ........... ...... ............ .................. [name and address of the company], hereinafter referred to as " the Contractor ", undertook, in execution of the contract, to carry out the work of [indicate the purpose of the work]

whereas he; is stipulated in the contract that the holdback of [% below 10% to be specified] of the TTC amount of the contract may be replaced by a joint and several guarantee,

Whereas; we have agreed to give the contractor this bond, We, ............ ........................... ............. .............. ..................... [name and bank address], represented by ................... ........ .................................... .............................. .. ............ [names of signatories], and hereinafter referred to as "the bank",

Therefore, we hereby affirm that we are the guarantors and responsible to the Owner, in the name of the contractor, for a maximum amount of ............. ......... ........................ [in figures and in words], corresponding to [less than 10% to be specified] of the amount of the contract,

And we undertake to pay the Owner, within a maximum period of eight (08) weeks, upon a simple written request from the latter stating that the contractor has not satisfied his contractual commitments or that he is found to be the Principal's debtor under the amended contract, if necessary by its amendments, without being able to defer payment or raise any dispute for any reason whatsoever, any sum (s) within the limits of the amount equal to [percentage less than 10% to be specified] of the cumulative amount of work included in the final statement, without the Owner having to prove or give the reasons or the reason for his request for the amount of the sum indicated above .

We agree that no changes or additions or other changes to the market will release us from any obligation under this warranty and we hereby waive any change, addendum or change.

This guarantee comes into force upon signature. It will be released within thirty (30) days from the date of final acceptance of the works, and on release delivered by the Owner.

Any request for payment made by the Client under this guarantee must be made by registered letter with acknowledgment of receipt, received at the bank during the period of validity of this commitment.

This deposit is subject for its interpretation and execution under Cameroon law. The Cameroonian courts will have exclusive jurisdiction to rule on all matters relating to this undertaking and its consequences.

Signed and authenticated by the bank

to ............... .......................... ......... .., the ............... ...... .................... ......... ..

[bank signature]

ANNEX No.7:  MODEL OF COMMITMENT OF AVAILABILITY

To Whom It May Concern:

Subject: COMMITMENT OF AVAILBILITY.

I the undersigned,  (specify Name, qualification -diploma or certificate) and holder of National Identity Card No _________________ issued on ________________ at ________ Tel: __________is committed and will be available to work as (specify post occupied)   with (name of enterprise) if  Open National Invitation  to Tenders No.   …………………………………………… for …………. (indicate the name of project) ………… is awarded to ETS …………………………………………..

Done at ___________ the ___________

Sign; ______________

ANNEX No. 8:   MODEL REFERENCES OF THE ENTERPRISE

The most representative services and similar to those described in the Special technical conditions above over the last five years

| N° | Year | Contract | Purpose | Funding | Amount (ATI) (CFAF) | Acceptance date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |

NB : for each contract named in the above board,  please join :

- Photocopy of first,second and last pages of the contract,

- Photocopy of provisional (or final) acceptance report.

Done on ..……………………, at ………………………….

Mr (Messrs)..……………………………………………….

Signature(s)…………………………………………………

ANNEX No. 9:   MODEL EQUIPMENT LIST.

| DESIGNATION | NUMBER | AGE-STATE | ORIGIN | STATUS |
| --- | --- | --- | --- | --- |

ANNEX No.10:

KEY STAFF

| Name | Proposed Function | Minimum Qualification | General Years of Experience | Specific Experience with respect to Similar Project | Post occupied for similar Project |
| --- | --- | --- | --- | --- | --- |

|  | NAME | QUALIFICATION | EXPERIENCE | FUNCTION |
| --- | --- | --- | --- | --- |
| SUPPORT STAFF |  |  |  |  |

ANNEX No: 11

SITE VISIT REPORT [not more than five (05) pages]

- INTRODUCTION

TENDER Nº (with project title) …………………………………………………………………

NAME OF ENTERPRISE ……………………………………………………………………..

DATE:……………………………………………TIME: …………………………………….

II) COMMENTARY:

II-1) Nature of the project site …………………………………………………….

II-2) Accessibility to the project site: ……………………………………………………

II-3) Vegetation (trees, shrubs etc) ………………………………………………………

II-4) Topography of the site ……………………..

III) AVAILABILITY OF SERVICES (water, electricity, etc)

IV) AVAILABILITY OF CONSTRUCTIONAL MATERIAL (stones, sand, gravel, wood etc)

V)DIFFICULTIES:

………………………….……………………………………………….

…………………………………………………………………………………………………………………….…………………………………………………………………………………………………………………….

V)CONCLUSION

…………………………………………………………………………

……………………………….…………………………………………………………………………………………………………………….

SIGNATURE:

`

ATTESTATION OF SITE VISIT

I the under signed Mr.…………………………………………………………..

In the capacity of ………………………representing………………………………company

Hereby make a sworn statement that on this day …………………. I have visited the project-site for the …………………………………………………………………………………..

Subject of Open National Invitation to Tender No ………………………. ………………..

Following this visit the observations listed below were made:

- Technial observations:

-------------------------------

Signature

ANNEX No: 12

To: The Project Owner

Subject: Letter of submission of Technical offer

Sir,

We, the undersigned, are pleased to propose our services as service provider for “Subject Matter of Bid/offer” in accordance with invitation to tender “Bid reference”   of the _____________ and our offer. We hereby submit our technical bids.

If negotiations take place during the period of validity of the offer that is before __________________ we pledge to negotiate on the basis of the personnel proposed here. For us our bid is binding, subject to the modifications resulting from the negotiation of the contract.

We know that you are not bound by any of the proposals received.

Yours faithfully,

Signature of empowered representative:________________________________

Name and title of signatory:__________________________________________.

Name of candidate firm:_____________________________________________.

Address__________________________________________________________.

ANNEX No: 13

To: The Project Owner

Subject: Letter of submission of Financial offer

Sir,

We, the undersigned, are pleased to propose our services as service provider for “Subject Matter of Bid/offer” in accordance with invitation to tender “Bid reference”   of the _____________ and our offer. We hereby submit our technical bids.

Find herewith our financial offer which stands as  [insert Amount in words and Figures]___________________ Francs CFA . This amount is net with of taxes, duties, dues which we have estimated at [insert Amount in words and Figures]___________________  Francs CFA for contracted duration of ____________ months.

Our financial offer has for us binding on us, up to the deadline of validity of the offer, that is, up till _________________ subject to modifications resulting from negotiation of the contract.

We are aware that you are not bound to accept any offer.

Yours faithfully,

Signature of empowered representative:________________________________

Name and title of signatory:__________________________________________.

Name of candidate firm:_____________________________________________.

Address__________________________________________________________.

Document No. 12:

List of banking establishments and financial bodies authorised to issue bonds for public contracts

###### B AN KS

- Afriland First Bank

- Banque Atlantique

- Banque Gabonaise pour le Financement International (BGFI BANK)

- Banque International du Cameroun pour l’Epargne et le Crédit

- CITI Bank

- Commercial Bank of Cameroon

- Ecobank

- National Financial Credit Bank

- Société Camerounaise de Banque au Cameroun

- Société Générale de Banque au Cameroun

- Standard Chartered Bank Cameroon

- Union Bank of Cameroon

- United Bank for Africa.

- Banque Camerounaise des Petites et Moyennes Entreprises (BC-PME), B.P. 12962 Yaoundé ;

- Bank Of Africa Cameroun (BOA Cameroun), B.P. 4593 Douala

- BANGE BANK CAMEROUN (BANGE CMR);

- Crédit Communautaire d’Afrique – Bank (CCA – Bank), BP :30 388, Yaoundé ;

- La régionale Bank, BP : 30 145 Yaoundé, Tél : (+237) 222 22 02 39

- Insurance Companies

  - Chanas assurances ;

  - Activa Assurances

  - Atlantique Assurances S.A., B.P. 2933 Douala ;

  - Zénithe Insurance S.A. ;

  - Pro-Assur S.A ;

  - Aréa Assurances S.A, B.P :1531 Douala ;

  - Bénéficial General Insurance S.A., B.P. 2328 Douala ;

  - CPA S.A., B.BP. 54Douala ;

  - NSIA Assurances S.A., B.P. 2759 Douala ;

  - SAAR S.A., B.P. 1011 Douala ;

  - Saham Assurances S.A., B.P. 11315 Douala