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TENDER NOTICE
[bookmark: _Hlk239386602]OPEN NATIONAL INVITATION TO TENDER
NO 19/ONIT / MINDDEVEL / FEICOM/ BC/BCITB/NWR/ 2026 OF THE  23 /10/2026 FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
 BY AN EMERGENCY PROCEDURE

FINANCING: FEICOM AND BAFUT COUNCIL BUDGET, 2026 FINANCIAL YEAR
1.Subject of the Invitation to Tender
[bookmark: _Hlk238036107]With the frame work of the FEICOM/ BAFUT Council budget, the Mayor of BAFUT Council, the Contracting Authority, hereby launches an Open National Invitation to Tender for the construction of a bridge measuring 20m long and 8 meters wide over the Mbee river in Bafut Council, Mezam Division of the North West Region BY AN Emergency procedure.

2. Nature of works
For each bridge the works will include the dredging of the river bed, excavation and hard core. Construction of reinforced concrete abutments, slabs, sidewalk and decks, guardrails, markers and the application of paint. The MBEE river has the span of 20m long and width of 8m. The works comprise notably :
3. Estimated deadline:
The maximum duration provided by the Project Owner for the execution of the works forming the subject of this invitation to tender is 240 Days (8 calendar months) as from the date of notification of the contractor by the control engineer to start work.
4. Allotment:
The work is a unique lot as follows: 
the construction of a bridge measuring 20m long and 8 meters wide over the Mbee river in Bafut Council, Mezam Division of the North West Region BY AN EMERGENCY PROCEDURE
5. Estimated cost: 
The estimated cost after preliminary studies stands at One Hundred and Seventy-Eight Million, Five Hundred and Forty-Six Thousand, Three Hundred and Eighty-Two (178,546,382) FCFA all taxes inclusive
6. Participation and origin:
Participation to this Invitation to Tender is open to all Cameroonian enterprice that are in compliance with the fiscal law, excluding companies under suspension following the termination of a contract, in accordance with the Public Contracts Code.
7. Financing:
Works which form the subject of this Invitation to Tender shall be financed by the budget of FEICOM and BAFUT council for 2026 financial year. 

8. Bid bond 
Each bidder must include in his administrative documents, a bid bond issued by a first-rate banking establishment approved by the Ministry in charge of Finance and whose list is found in document No. 12 of the Tender File, of an amount of THREE MILLION FIVE HUNDRED AND SEVENTY THOUSAND NINE HUNDRED AND TWENTY SEVEN FCFA (3,579,927 CFA) valid for thirty (30) days beyond the date of validity of bids. The said guarantee must be accompanied by a receipt issued by CDEC in accordance with circular letter No.000019/L/MINMAP of 5th June 2024 relating to deposit, retention, restitution and deconsignment of bonds on public contracts.

9. Consultation of Tender File:
This file may be consulted during working hours at the SIGAMP OFFICE of the BAFUT Council during working hours from 7:30 am to 3:30 pm as soon as this notice is published.
10.     Acquisition of Tender File:
			The file shall be obtained from the SIGAMP OFFICE of the BAFUT Council, as soon as this notice is published against payment of the sum of One hundred ans fifty thousand FCFA (150 000 CFA), payable at the BAFUT Council Municipal Treasury, representing the cost of purchasing the Tender File. 
11.    Submission of bids:
Each offer drafted in English or French in 07 (seven) copies including 01 (one) original and 06 (six) copies marked as such, should reach the SIGAMP OFFICE at BAFUT Council, on 06/11/2026
at 10:00 AM local time and should carry the inscription: 

<< OPEN NATIONAL INVITATION TO TENDER NO 19/ONIT / MINDDEVEL / FEICOM/ BC/BCITB/NWR/ 2026 OF THE 23/10/2026 FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
 BY AN EMERGENCY PROCEDURE>>

   “To be opened only during the bid-opening session”
12. Admissibility of bids
        Under penalty of being rejected, only originals or true copies certified by the issuing service or administrative authorities (Senior Divisional Officer, Divisional Officers) must imperatively be produced in accordance with the Special Regulations of the Invitation to Tender. 
They must obligatorily not be older than three (3) months preceding the date of submission of bids or may be established after the signature of the tender notice
 Any bid not in compliance with the prescriptions of the Tender File shall be declared inadmissible. This refers especially to the absence of or insufficient bid bond issued by a first-rate bank approved by the Minister in charge of Finance, a valid copy of a CDEC receipt and a copy of a certificate of categorisation under the competent sub sector.
13. Opening of bids:
The bids shall be opened in a single phase. The opening of the administrative documents, the Technical and Financial offers will take place on the 06/11/2026 at 11:00 am local time, in the conference hall of BAFUT Council, by the BAFUT Council Internal Tenders Board. Only bidders may attend or be represented by duly mandated persons of their choice, having a good knowledge of the file
14.  Evaluation criteria
The bids shall be evaluated according to the main criteria as follows:
A. Eliminatory criteria
1. Absence or insufficient bid bond.
2. Absence of a CDEC receipt issued by the compétent authority
3.  Non-respect of  the 48hrs given for the absence or non-conformity of any other document in the administrative file;
4. False declaration or falsified documents;
5. A bid with the external envelope carrying a sign or mark leading to the identification of the bidder;
6. Incomplete bids;
7. Absence of a quantified unit price;
8. Change of quantity or unite price in the financial file 
9. Deadline for delivery higher than the prescribed
10. Score of less than  75% of essential criteria;
11. Financial capacity below 50% of the project cost
12. Absence of a valid copy of a certificate of categorization under the competent sub sector. (Legalised by the competent authority) 
 
B. Essential criteria
NB. Pursuant to circular letter No.00005/LC/MINMAP/CAB of 226/12/2023, bidders with certified true copies of the certificate of categorisation shall not submit in their TECHNICAL FILES documents relating to ; Their turnover, References of the company, own minimum technical and Logistics means ,permanent staff and head office location.

1- General presentation of the Tender Files;
2-  Financial capacity;
3- References of the company in  similar achievements;
4- Quality of the personnel;  
5- Technical organization of the works;
6- Safety measures on the site;
7- Logistics;
8- Attestation and report of site visit;
9- Special Technical Clauses initialed in all the pages;
10- Special Administrative Clauses completed and initialed in all the pages.
15. Award
This evaluation will be done in a binary way (yes) or (no) with an acceptable minimum of (75%) of the essential criteria taken in account.
The Contract will be awarded to the bidder who would have proposed the offer with the lowest amount, in conformity with the regulations of the Tender Documents and having satisfied to 100% of the eliminatory criteria and at least (75%)of the essential criteria.
16. Validity of bids
Bidders will remain committed to their offers for Ninety (90) days from the deadline set for the submission of tenders.

17. Complementary information
Complementary technical information may be obtained during working hours at the SIGAMP SERVICE of the BAFUT Council.			

18. Fight against corruption and malpractices
To report any malpractices, incidents or acts of corruption, kindly call CONAC on the number 1517, the Authority in charge of Public Contracts (MINMAP) (SMS or call) on the numbers: (+237) …………, FEICOM on the number 8567 or the PO/DPO on the number: (237) 677 527 274

Done at BAFUT  the 23/10/2026
                                                                   The Mayor of BAFUT  Council
	 Copy
· MINMAP;
· ARMP/NORTH-WEST;
· CHAIRPERSON /TENDERS BOARD BOARD/infos;
· FILE/ARCHIVES;
NOTICE BOARD
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AVIS D’APPEL D’OFFRES
AVIS D’APPEL D’OFFRES NATIONAL OUVERT
NO19/ONIT / MINDDEVEL / FEICOM/ BC/BCITB/NWR/ 2026 DU 23/10/2026, POUR LES TRAVAUX DE CONSTRUCTION D’UN PONT DE 20 METRES DE LONG ET 8 METRES DE LARGEUR SUR LA RIVIERE DE MBEE, DANS LA COMMUNE DE BAFUT, DEPARTEMENT DE MEZAM, REGION DU NORD-OUEST.
(EN PROCEDURE D’URGENCE) 

FINANCEMENT ; BUDGET DU FEICOM ET COMMUNE DE BAFUT EXERCICE 2026.
1. Objet de l'Appel d'Offre
Le Maire de la Commune de BAFUT, l’Autorité Contractante lance un Appel d’Offres National Ouvert en procédure d’urgence pour les travaux de construction d’un pont de 20 mètres de long et 8 mètres de largeur sur la rivière de Mbee, dans la commune de Bafut, Departement de Mezam, nspec du Nord-Ouest. (En procedure d’urgence)

2. Consistance des travaux
Pour chaque pont, les travaux comprendront le dragage du lit de la rivière, l’excavation et le hérisson des pierres. Sont également prévus la construction de culées, de dalles, de trottoirs et de tabliers en béton armé, ainsi que l’installation de garde-corps, de balises et la mise en œuvre de la peinture. Le pont MBEE a une portée de 20 m et une largeur de 8m.
3. Délais d’exécution
Le délai global d’exécution des travaux est de huit (08) mois calendaires (240 jours). Ce délai comprend les périodes des pluies, toutes les intempéries et sujétions diverses et court à compter de la date de notification de l’ordre de service de commencer les travaux.
4. Allotissement
Le travail est ci-après défini :
construction d’un pont de 20 mètres de long et 8 mètres de largeur sur la rivière de Mbee, dans la commune de Bafut, Departement de Mezam 
5. Coût prévisionnel
Le coût prévisionnel de l’opération à l’issue des études préalables est de 178 546 382 FCFA (Cent soixante-dix-huit millions cinq cent quarante-six mille trois cent quatre-vingt-deux) francs CFA TTC.
6. Participation et origine
	La participation au présent Appel d’Offres est ouverte à égalité de conditions à toutes les entreprises de catégorie C installées au Cameroun à l’exclusion des :
· Entreprises se trouvant sous le coup de la suspension suite à la résiliation d’un marché, en application du Code des Marchés Publics ;
· Entreprises publiques qui ne sont pas juridiquement et financièrement autonomes. 
7. Financement
Les travaux, objet du présent Appel d’Offres sont financés par le budget du FEICOM et la commune de BAFUT exercices 2026. 
8. Cautionnement provisoire
Chaque soumissionnaire doit joindre à ses pièces administratives, une caution de soumission établie par une banque de premier ordre agréée par le Ministère chargé des finances et dont la liste figure dans la pièce12 du DAO, d’un montant de Trois million, cinq cent soixante dix neuf mille, neuf cent vingt sept (3,579,927 CFA FCFA) et valable pendant trente (30) jours au-delà de la date originale de validité des offres.
9. Consultation du Dossier d'Appel d'Offres
Le Dossier d’Appel d’Offres peut être consulté et obtenu aux heures ouvrables au bureau de SIGAMP  à la Commune de BAFUT.
10. Acquisition du Dossier d'Appel d'Offres
Le dossier peut être obtenu aux heures ouvrables au bureau de SIGAMP à la Commune de BAFUT. Dès publication du présent avis, contre présentation d’une quittance de versement au Trésor Public de la somme non remboursable de cent cinquante  mille Francs CFA (150 000) F CFA
11. Remise des offres
Chaque offre rédigée en français ou en anglais en sept (07) exemplaires dont un (01) original et six (06) copies marquées comme telles, devra parvenir contre récépissé à la Commune de BAFUT, au plus tard le 06/11/2026 à10h, heure locale et devra  porter la mention suivante :
« AVIS D’APPEL D’OFFRES NATIONAL OUVERT NO 019/ONIT / MINDDEVEL / FEICOM/ BC/BCITB/NWR/ 2026  DU DU 23/10/2026, POUR LES TRAVAUX DE CONSTRUCTION D’UN PONT DE 20 METRES DE LONG ET 8 METRES DE LARGEUR SUR LA RIVIERE DE MBEE, DANS LA COMMUNE DE BAFUT, DEPARTEMENT DE MEZAM, REGION DU NORD-OUEST EN PROCEDURE D’URGENCE»
«A N’OUVRIR QU’EN SEANCE DE DEPOUILLEMENT»
12. Recevabilité des offres
Sous peine de rejet, les pièces du dossier administratif requises doivent être produites e noriginaux ou en copies certifiées conformes parle service émetteur ou une autorité administrative (Préfet, Sous-préfet,…), conformément aux stipulations du Règlement Particulier de l’Appel d’Offres.
Elles doivent dater de moins de trois (03) mois précédant la date originale de dépôt des offres ou avoir été établies postérieurement à la date de signature de l’Avis d’Appel d’Offres.
Toute offre incomplète conformément aux prescriptions du Dossier d'Appel d'Offres sera déclarée irrecevable. Notamment l'absence de la caution de soumission délivrée par une banque de premier ordre agréée par le Ministère chargé des Finances.
13. Ouverture des plis
L’ouverture des plis se fera en un temps. L’ouverture des pièces administratives et des offres techniques et financières  aura lieu le  06/11/2026 à 11h, heure locale, dans la salle de conférence de la Commune de BAFUT, par la Commission Interne de Passation de Marchés de la Commune de BAFUT siégeant en présence des soumissionnaires ou de leurs représentants dûment mandatés et ayant une parfaite connaissance du dossier.
14. Critères d’évaluation
Les offres seront évaluées selon les principaux critères suivants :
A - Critères éliminatoires
Il s'agit notamment:
1- Absence ou insuffisance d’une Caution de soumission 
2- Absence de récépissé CDEC delivré par l’autorité compétente
3-  Non respect de 48h pour l’absence ou non-conformité des autres documents dans les dossiers administratifs ; 
4- Fausses déclarations ou pièces falsifiées;
5- Offres dont l’enveloppe extérieure  porte des mentions  permettant de reconnaître le Soumissionnaire;
6- Offres incomplète,
7- Absence d’un prix unitaire quantifié ; 
8- Obtention d’un score de moins 75% ;
9- Situation financière inferieure a 50% du cout du projet 
10- Changement du quantification  ou d’unite dans le dossier financier
11- Delai de livraison superieur au delai prescript
12- Absence d’une copie valide d’un certificate de catégorisation relevant de la sous – section compétente en matière de construction. (Légalisé par l’autorité competente en charge des marchés publics)
B - Critères essentiels
N/B : La présence de la copie certifiée conforme d’attestation catégorisation délivré par le Ministre charge des marches Publics ou par son représentant dument mandaté, disperse les soumissionnaires catégorisées de la production dans leurs dossiers techniques, des pièces justificatives relatives au chiffre d’affaires, aux références, aux moyens techniques et logistiques propres minima, au personnel permanent et à la localisation du siège. 
Les critères relatifs à la qualification des entreprise porteront à titre indicatif sur :
1- Présentation générale de l’offre ;
2- Capacité financière
3- Références de l’entreprise dans les domaines de construction des bâtiments ;
4- Qualité du personnel ;
5- Organisation technique des travaux ;
6- Sécurité au chantier ;
7- Moyens logistiques ;
8- Attestation et rapport de visite du site signé par l’entrepreneur ;
9- Cahier des Clauses Techniques Particulières paraphé à chaque page  et une signature à la dernière page;
10- Cahier des Clauses Administratives Particulières complété et paraphé à chaque page et une signature à la dernière page.
Les critères essentiels sont soumis à des minima dont le détail est donné dans le Règlement Particulier de l’Appel d’Offres (RPAO).
Les critères essentiels sont soumis à des minima dont le détail est donné dans le Règlement Particulier de l’Appel d’Offres (RPAO).
15. Attribution
Cette évaluation se fera de manière purement positive (oui) ou négative (non) avec un minimum acceptable d’au moins (75%)de l’ensemble des critères essentiels pris en compte.
Le marché sera attribué au soumissionnaire qui aura proposé l’offre la moins disante, conforme pour l’essentiel aux prescriptions du Dossier d’Appel d’Offres, ayant satisfait à 100% des critères éliminatoires et au moins (75%) des critères essentiels. 
16. Durée de validité des offres
Les soumissionnaires restent engagés par leur offre pendant 90 jours à partir de la date limite fixée pour la remise des offres.
17. Renseignements complémentaires
Les renseignements complémentaires d’ordre technique peuvent être obtenus auprès de la Commune de BAFUT bureaux de SIGAMP.		
18. Lutte contre la corruption et les mauvaises pratiques
Pour toute dénonciation pour des pratiques, faits ou actes de corruption, bien vouloir appeler la CONAC au numéro 1517, l’Autorité chargée des Marchés Publics (MINMAP) (SMS ou appel) aux numéros : (+237) …….., FEICOM au numéro 8567 ou le MO/MOD au numéro : (237) 677 527 274
								BAFUT, le 23/10/2026
								LE MAIRE, COMMUNE DE BAFUT
								(Autorité Contractant) 
Copies :
· DD MINMAP Mezam
· ARMP;
· Président CIPM;
· Affichage.
· Chrono
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GENERAL RULES OF THE INVITATION TO TENDER


A. General

Article 1: Scope of the tender
1.1 The Contracting Authority as defined in the Special Regulations of the Invitation to Tender hereby launches an Invitation to tender for the works described in the Tender File and briefly described in the Special Regulations.

1.2 The bidder retained or the preferred bidder must complete the works within the time- limit indicated in the Special Regulations and which time-limit runs from the date of notification of the Administrative Order.

1.2 In this Tender File, the term “day” means a calendar day.

Article 2: Financing
The source of financing of the works forming the subject of this Invitation to Tender shall be specified in the Special Regulations.

Article 3: Fraud and corruption
3.1 The Contracting Authority requires of bidders and Contractors the strict respect of rules of professional ethics during the award and execution of Public Contracts. By virtue of this principle:

a)  The following definitions shall be admitted:

i) Shall be guilty of “corruption” whoever offers, gives, requests or accepts any advantage in view of influencing the action of a public official during the award or execution of a Contract;

ii)   Is involved in “fraudulent manoeuvres” whoever deforms or distorts facts in order to influence the award or execution of a Contract;

iii)   “Collusive practices” shall mean any form of agreement between two or among several bidders (whether the Contracting Authority is aware or not) aimed at artificially maintaining the prices of bids at levels not corresponding to those resulting from competition;

iv)   “Coercive practices” shall mean any form of harm against persons or their property or threats against them in order to influence their action during the award or execution of a Contract.

b) Any proposed award shall be rejected if it is proved that the proposed preferred bidder is directly or through an intermediary, guilty of corruption or is involved in fraudulent manoeuvres, collusive or coercive practices for the award of this Contract. 
3.2     The Minister Delegate at the Presidency in charge of Public Contracts may, as a precaution, take a decision of exclusion from bidding for a period not exceeding two (2) years against any bidder found guilty of influence peddling, of conflicts of interest, insider trading, fraud, corruption or production of non-genuine documents in the bid, without prejudice to criminal proceedings that may be brought against him

Article 4: Candidates allowed to compete
    4.1 If the Invitation to Tender is restricted, consultation is addressed to all candidates retained after a pre-qualification procedure.

    4.2 Generally, the Invitation to Tender is addressed to all entrepreneurs, subject to the following provisions:

(a)  a bidder (including all members of a group of enterprises and all sub-Contractors to the bidder) must be from an eligible country, in accordance with the funding agreement.

(b) a bidder (including all members of a group of enterprises and all sub-Contractors to the bidder) must not be in a situation of conflict of interest, subject to disqualification. A bidder shall be judged to be in a situation of conflict of interest if he:

i) is or was associated in the past with an enterprise (or a subsidiary of this enterprise) which provided consultancy services for the conception, preparation of specifications and other documents used within the scope of Contracts awarded for this Invitation to Tender; or 

ii) Presents more than one bid within the context of Invitation to Tender, except authorised variants according to article 17, where need be; meanwhile, this does not prevent the participation of sub-Contractors in more than one bid.

iii) The Contracting Authority or Project Owner has financial interests in the capital in a way as to compromise the transparency of the procedures of award of Public Contracts.

         (c)   The bidder must not have been excluded from bidding for Public Contracts.

(c) A Cameroonian public enterprise may participate in the consultation if it can demonstrate that it is (i) legally and financially autonomous, (ii) managed according to commercial laws and (iii) not under the direct supervisory authority of the Contracting Authority or Project Owner. 

Article 5: Building materials, materials, supplies, equipment and authorised services
5.1 Building materials, the Contractor’s materials, supplies, equipment and services forming the subject of this Contract must originate from countries meeting the criteria of origin defined in the Special Regulations of the Invitation to tender and all expenditure done within the context of the Contract shall be limited to the said building materials, materials, supplies, equipment and services.

5.2 Within the meaning of this 5.1 above, the term “originate” shall designate the place where the goods are extracted, cultivated, produced, manufactured and from where the services originate.

Article 6: Qualification of bidder
    6.1   As an integral part of their bid, bidders must:

(a) submit a power of attorney making the signatory of the bid bound by the bid; and

        (b)  provide all information (complete or update information included in their request for pre-qualification which may have changed in the case where the candidates took part in pre-qualification) requested of bidders in the Special Regulations of the Invitation to Tender, in order to establish their qualification to execute the Contract.

Where necessary, bidders should provide information relating to the following points:
            (i)  The production of certified balance sheets and recent turnovers;
         (ii)  Access to a line of credit or availability of other financial resources;
         (iii)  Orders acquired and Contracts awarded;
         (iv)  Pending litigations; 
         (v)  Availability of indispensable equipment.

     6.2   Bids presented by two or more associated undertakings (joint-Contracting) must satisfy the following conditions:

(a) The bid must include all the information listed in article 6(1) above. The Special Regulations must indicate the information to be furnished by the group and that to be furnished by each member of the group;

(b) The bid and the Contract must be signed in a way that is binding on all members of the group;
(c) The nature of the group (joint or several) must be specified  in the Special Regulations and justified with the production of a joint venture agreement in due form;
(d) The member of the group designated as the representative will represent all the undertakings vis à vis the Project Owner and Contracting Authority with regard to the execution of the Contract;
(e)  In case of joint co-Contracting, the co-Contractors shall share the sums which are paid by the Project Owner into a single account. On the other hand, each undertaking is paid into its own account by the Project Owner where it is joint co-Contracting.

     6.3 Bidders must equally present sufficiently detailed proposals to demonstrate that they comply with the technical specifications and execution time-limits set in the Special Regulations of the Invitation to Tender.

     6.4 Bidders requesting to benefit from the margin of preference must furnish all the necessary information to prove that they satisfy the eligibility criteria set in article 33 of the General Regulations of the Invitation to Tender.

Article 7: Visit of works site
7.1 The bidder is advised to visit and inspect the site and its environs and obtain by himself and under his own responsibility, all the information which may be necessary for the preparation of the bid and the execution of the works. The related cost of the visit of the site shall be borne by the bidder.

    7.2 The Project Owner shall authorise the bidder and his employees or agents to enter the premises and the land for the said visit but only on the express condition that the bidder, his employees and agents free the Project Owner, his employees and agents of any responsibility that may ensue and indemnify them if necessary and that they shall remain responsible for any deadly or corporal accident, loss or material damages, costs and fees incurred from this visit.

     7.3 The Project Owner may organise a visit of the site of the works during the preparatory meeting to establishing the bids mentioned in article 19 of the General Regulations of the Invitation to Tender.

B. Tender File

Article 8: Content of Tender File
   8.1 The Tender File describes the works forming the subject of the Contract, sets the consultation procedure of Contractors and specifies the terms of the Contract.  Besides the addendum (addenda) published in accordance with article 10 of the General Regulations of the Invitation to Tender, it includes the following documents:

	Document No. 1. The tender notice;
	Document No. 2. The General Regulations of the Invitation to Tender;
	Document No. 3. The Special Regulations of the Invitation to Tender;
	Document No. 4. The Special Administrative Conditions;
	Document No. 5. The Special Technical Conditions;
	Document No. 6. The schedule of unit prices;
	Document No. 7. The bill of quantities and estimates;
	Document No. 8. The sub details of unit prices;
	Document No. 9. Model documents of the Contract:
a. The execution schedule;
b. Model of forms presenting the equipment, personnel and references;
c. Model bidding letter;
d. Model bid bond;
e. Model final bond;
f. Model of bond of start-off advance;
g. Model of guarantee in replacement of the retention fund;
h. Model Contract;

Document No. 10. Models to be used by bidders; 
a. Model Contract;
         Document No. 11. Justifications of preliminary studies; to be filled by the Project Owner or Delegated Project Owner;
         Document No. 12. List of first grade banking establishments or financial institutions approved by the Minister in charge of Finance authorised to issue bonds for Public Contracts to be inserted by the Contracting Authority.

8.2 The bidder must examine all the regulations, forms, conditions and specifications contained in the Tender File. It is up to him to furnish all the information requested and prepare a bid in compliance with all aspects of the said file. 

Article 9: Clarifications on the Tender File and complaints
9.1 Any bidder who wants to obtain clarifications on the Tender File may request them from the Contracting Authority in writing or by electronic mail (fax or e-mail) at the Contracting Authority’s address indicated in the Special Regulations of the Invitation to Tender and send a copy to the Project Owner. The Contracting Authority replies in writing to any request for clarification received at least fourteen (14) days prior to the deadline for the submission of bids.

 A copy of the Contracting Authority’s response, indicating the question posed but not mentioning the author, is addressed to all bidders who bought the Tender File.

9.2 Between the publication of the tender notice including the pre-qualification phase of candidates and the opening of bids, any bidder who feels aggrieved in the Public Contracts award procedure may lodge a complaint to the Minister in charge of Public Contracts.

9.3 A copy of the complaint should be addressed to the Contracting Authority and to the body in charge of the regulation of Public Contracts and the chairperson of the Tenders Board.

9.4 The Contracting Authority has five (5) days to react. A copy of the reaction shall be forwarded to MINMAP and the body in charge of the regulation of Public Contracts.

Article 10:  Amendment of the Tender File
10.1The Contracting Authority may at any moment, prior to the deadline for the submission of bids and for any reason, be it at his initiative or in reply to a request for clarification formulated by a bidder, amend the Tender File by publishing an addendum.

10.2 Any published addendum shall be an integral part of the Tender File, in accordance with article 8.1 of the General Regulations of the Invitation to Tender and must be communicated in writing or made known by a traceable means to all bidders who bought the Tender File.

10.3 In order to give bidders sufficient time to take account of the addendum in the preparation of their bids, the Contracting Authority may postpone as is necessary, the deadline for the submission of bids, in accordance with provisions of article 22 of the General Regulations of the Invitation to Tender.


10.4 

C   Preparation of bids
Article 11: Tender costs
The candidate shall bear the costs related to the preparation and presentation of his bid and the Contracting Authority and the Project Owner shall in no case be responsible for these costs nor pay for them whatever the evolution or outcome of the Invitation to Tender procedure. 

Article 12: Language of bid
The bid as well as any correspondence and any document exchanged between the bidder and the Contracting Authority shall be written in English or French. Complementary documents and the forms provided by the bidder may be written in another language on condition that a precise translation into either English or French of the passages concerning the bid is included; in which case for reasons of interpretation, the translation shall be considered to be authentic.

Article 13: Constituent documents of the bid
 13.1 The bid presented by the bidder shall include the documents detailed in the Special Regulations of the Invitation to Tender, duly filled and put together in three volumes:

a. Volume 1:  Administrative file
It includes:

i) all documents attesting that the bidder:
· has subscribed to all declarations provided for by the laws and regulations in force;
· paid all taxes, duties, contributions, fees or deductions of whatever nature;
· is not winding up or bankrupt;
· is not the subject of an exclusion order or forfeiture provided for by the law in force; 

           ii)   The bid bond established in accordance with the provisions of article 17 of the General Regulations of the Invitation to Tender;

           iii)  the written confirmation empowering the signatory of the bid  to commit the bidder, in accordance with the provisions of article 6(1) the General Regulations of Invitation to Tender.

b. Volume 2: Technical bid
	
	b.1 Information on qualifications
	
	The Special Regulations list the documents to be furnished by bidders to justify the qualification criteria mentioned in article 6(1) of the Special Regulations of the Invitation to Tender.

	B.2 Methodology 
	The Special Conditions of the Invitation to Tender specifies the constituent elements of the technical bid of the bidders especially: a methodological statement on an analysis of the works and specifying the organisation and programme which the bidder intends to put in place or use to execute the works (installations, schedule, Quality Assurance Plan (QAP), sub-Contracting, attestation of visit of the site, where necessary, etc.).
	
	B.3 Proof of acceptance of conditions of the Contract
The bidder shall submit duly initialled copies of the administrative and technical documents relating to the Contract, namely:

1. The Special Administrative Conditions (SAC);
2. The Special Technical Conditions (STC).
	B.4 Commentaries (optional) 
	A commentary on the technical choices of the project and possible proposals.

c. Volume 3: Financial bid
The Special Regulations specify the elements that will help in justifying the cost of the works, namely:
1. The signed and dated original bid prepared according to the attached model, stamped at the prevailing rate;
2. The  duly filled Unit Price Schedule;
3. The duly filled detailed estimates;
4. The sub-details of prices and/or breakdown of all-in prices;
5. The projected schedule of payments, where need be.

In this regard, the bidders will use the documents and models provided in the Tender File, subject to the provisions of article 17(2) of the General Regulations of the Invitation to tender concerning the other possible forms of guarantees.

      13.2    If in accordance with the provisions of the Special Regulations of the Invitation to Tender, the bidders present bids for several lots of the same Invitation to Tender, they could indicate rebates offered in case of award of more than one lot.

Article 14:  Bid price 
     14.1    Except otherwise stated in the Tender File, the amount of the Contract shall cover all the works described in article 1.1 of the General Regulations of the Invitation to Tender, on the basis of the price schedule and the detailed bill of quantities and estimates presented by the bidder .

     14.2   The bidder shall fill the unit prices and totals of all items on the schedule and bill of quantities and estimates.

 14.3   Subject to contrary provisions provided for in the Special Regulations and in the Special Administrative Conditions, all dues, taxes and fees payable by the bidder on grounds of the Contract or on any other ground, thirty (30) days prior to the submission of the bids, shall be included in the prices and in the total amount of the bid presented by the bidder.

14.4 If a price revision/updating clause is provided for in the Contract, the date of establishment of the initial price, as well as the price revision/updating conditions for the said price must be specified. This is with the understanding that any Contract of duration less than one (1) year shall not be subject to price revision.

      14.5 All unit prices must be justified by sub-details established in accordance with the structure proposed in document 8 of the Tender File.

Article 15: Currency of bid and payment
       15.1 In case of international invitations to tender, the currencies of the bid shall follow the provisions of either Option A or Option B below, the applicable option being that retained in the Special Regulations of the Invitation to Tender.

	15.2 Option A: The amount of the bid shall be entirely made in the national currency.
	The amount of the bid, unit prices of the price schedule and the prices of the bill of quantities and estimates are completely made in CFA francs in the following manner:
a) Prices shall be entirely drawn in the national currency. The bidder who intends to commit expenditures in other currencies for the execution of the works shall indicate in the annex to the bid the percentage(s) of the amount of the bid necessary to cover the needs in foreign currencies, without exceeding the maximum of the three currencies of member countries of the funding institution of the Contract.
b) The exchange rates used by the bidder to convert his bid into the national currency shall be specified by the bidder in an annex to the bid in compliance with the specifications of the Special Regulations. These rates shall be applied for any payment within the framework of the Contract so that the retained bidder does not bear any change in the exchange rate.

	15.3 Option B: The amount of the bid shall be directly made in the national and foreign currency at the rates fixed in the Special Regulations.
	
	The bidder shall draw the unit prices of the price schedule and the prices of the bill of quantities and estimates in the following manner:
	
(a) The prices of inputs necessary for the works which the bidder intends to procure in the Contracting Authority’s country shall be in currency of the Contracting Authority’s country specified in the Special Regulations and called “national currency”;
(a) The prices of inputs necessary for works which bidder intends to procure out of the Contracting Authority’s country shall be in the currency of the country of origin of the bidder or of the currency of an eligible member country widely used in international trade.

15.4 The Contracting Authority may request the bidders to explain the needs in national and foreign currencies and to justify that the amounts included in the unit and total prices and indicated in annex to the bids are reasonable; to this end, a detailed statement of their needs in foreign currencies shall be furnished by the bidder.

15.5 During the execution of the works, most of the foreign currency to be paid as part of Contract may be revised by mutual agreement between the Contracting Authority and the entrepreneur in a way as take account of any modification in the foreign currency needs within the context of the Contract.

Article 16: Validity of bids
16.1 Bids must remain valid during the period stated in the Special Regulations from the date of submission of the bids fixed by the Contracting Authority, in application of article 22 of the Special Regulations. A bid valid for a shorter period shall be rejected by the Contracting Authority or Delegated Contracting Authority as not being in compliance.

16.2 Under exceptional circumstances, the Contracting Authority may seek the approval of bidders to extend the validity time-limit.  The request and the responses that will be given shall be in writing (or by fax). The validity of the bid bond provided for in article 17 of the General Regulations shall equally be extended for a corresponding duration. A bidder may refuse to extend the validity of his bid without losing his bid bond. A bidder who consents to an extension shall not be asked to modify his bid nor shall he be authorised to do so.

16.3 Where the Contract does not include a price revision clause and that the period of validity of bids is extended by more than sixty (60) days, the amounts payable to the bidder retained shall be updated by application of the related formula featuring in the request for extension that the Contracting Authority addressed to bidders.
The updating period shall run from the date of overrun of sixty (60) days to the date of notification of the Contract or the Administrative Order for start of execution of works by the retained bidder, as specified in the Special Administrative Conditions. The effect of updating shall not be taken into account for purposes of evaluation of bids.

Article 17: Bid bond
17.1   In application of article 13 of the General Regulations, the bidder shall furnish a bid bond of the amount specified in the Special Regulations and which bid bond shall be a full part of his bid.

17.2 The bid bond must conform to the model presented in the Tender File; other models may be authorised subject to the prior approval of the Contracting Authority. The bid bond will remain valid for thirty (30) days beyond the original date set for the validity of bids or any other validity  time-limit  requested by the Contracting Authority and accepted by the bidder, in accordance with the provisions of article 16 (2) of the General Regulations.

17.3   Any bid without an acceptable bid bond shall be rejected by the Tenders Board as not in conformity.  The bid bond of associated enterprises must be established in the name of the group submitting the bid and mention each member of the associated grouping.

17.4    The bid bonds of bidders who are not retained shall be returned within fifteen (15) days after publication of the award result.

17.5   The bid bond of the successful bidder shall be released as soon as the latter would have signed the Contract and furnished the required final bond.

17.6    The bid bond may be seized:

(a) if the bidder withdraws his bid during the period of validity; 
(b)  If the retained bidder:
                                 i)  fails in his obligation to register the Contract in application of  article 38 of the General Regulations;

ii) fails in his obligation to furnish the required final bond in application of article 38 of the General Regulations;

iii) Refuses to receive notification of the Administrative Order to commence execution.

Article 18: Varying proposals of bidders
18.1 Where the works can be executed within variable deadlines, the Special Regulations shall specify these deadlines and shall indicate the method retained for the evaluation of the completion deadline proposed by the bidder within the specified deadlines. Bids that propose deadlines beyond those specified shall be considered as not being in conformity.

18.2 Except in the case mentioned in article 18(3) below, bidders wishing to offer technical variants must first assess the basic solution of the Contracting Authority as described in the Tender File and furnish in addition all the information which the Contracting Authority needs for a complete evaluation of the proposed variant, including the plans, calculations, technical specifications, sub-details of prices and proposed construction methods and all other useful information. If necessary, the Contracting Authority will examine only the technical variants of the bidder whose bid is in compliance with the basic solution has been evaluated as the lowest bid.

18.3 When according to the Special Regulations the bidders are authorised to directly submit the technical variants for certain parts of the works, these parts of the works must be described in the technical specifications. Such variants shall be evaluated on their own merit in accordance with the provisions of article 31(2) (g) of the General Regulations.

Article 19: Preparatory meeting to the establishment of bids
19.1   Except otherwise stipulated in the Special Regulations, a bidder may be invited to take part in a preparatory meeting which will hold at the date and place indicated in the Special Regulations.

19.2 The subject of the preparatory meeting shall be to furnish clarifications and answer any questions which may be raised at this stage.

19.3    As much as possible, the bidder is requested to submit any question in a way as to reach the Contracting Authority at least one week before the meeting The Contracting Authority may not reply to questions received too late. In this case, the questions and answers shall be transmitted according to the methods set in article 19(4) below.  

19.4    The minutes of the meeting, including the text of the questions asked and the replies given, including questions prepared after the meeting, shall be forwarded immediately to everyone who bought the Tender File. Any modification of documents of the Tender File listed in article 8 of the General Regulations which may prove to be necessary at the end of the preparatory meeting shall be done by the Contracting Authority by publishing an addendum in accordance with the provisions of article 10 of the General Regulations and not through the minutes of the preparatory meeting.

19.5 The fact that a bidder does not attend a preparatory meeting for the establishment of bids shall not be a reason for disqualification.

Article 20: Form and signature of bid
20.1 The bidder shall prepare an original of the constituent documents described in article 13 of the General Regulations in a volume clearly indicated “ORIGINAL”. In addition, the bidder shall submit the number required in the General Regulations, bearing “COPY”. In case of discrepancy, the original shall be considered as authentic.

20.2  The original and copies of the bid must be typed or written in indelible ink (photocopies shall be accepted in the case of copies) and shall be signed by the person(s) duly empowered to sign on behalf of the bidder, in accordance with article 6(1a) or 6(2c) of the General Regulations, as the case may be. All the pages of the bid containing alterations or changes must be initialled by the signatory (ies) of the bid.

20.3 The bid shall be bear no modification, suppression or alteration unless such corrections are initialled by the signatory (ies) of the bid.

D.  SUBMISSION OF BIDS

Article 21:  Sealing and marking of bids
21.1 The bidder shall seal the original and each copy of the bid in separate envelopes (internal envelopes) by marking on these envelopes “ORIGINAL” and “COPY”, as the case may be. The envelopes shall then be placed in another envelope which will equally be sealed but which will not give any indication regarding the identity of the bidder.
	
21.2 The external and internal envelopes:
         a) Should be addressed to the Contracting Authority at the address indicated in the Special Regulations;
b) should bear the name and identification number of the project as indicated in the Special Regulations  and  bear the inscription “TO BE OPENED ONLY DURING THE BID-OPENING SESSION” as specified in the Special Regulations.
21.3 The internal envelopes should equally carry the name and address of the bidder in a way as to enable the Contracting Authority return the sealed bid if it is late in accordance with article 23 and 24 of the General Regulations.    

21.4 If the external envelope is not sealed and marked as indicated in paragraphs 21(1) and 21(2) above, the Contracting Authority shall not be responsible if the bid is misplaced or opened prematurely. 
Article 22: Date and time-limit for submission of bids 
22.1 The bids must be received by the Contracting Authority at the address specified in article 21(2) of the Special Regulations not later than the date and time stated in the Special Regulations.

22.2 The Contracting Authority may, at his discretion, postpone the deadline set for the submission of the bids by publishing an addendum in accordance with the provisions of article 10 of the General Regulations.  In this case, all the rights and obligations of the Contracting Authority and bidders previously governed by the initial date will henceforth be governed by the new date.

Article 23: Late bids
Any bid received by the Contracting Authority beyond the deadline for the submission of bids in accordance with article 22 of the General Regulations shall be declared late and consequently rejected.

Article 24: Modification, substitution and withdrawal of bids
24.1 A bidder may modify or withdraw his bid after submitting it, on condition that the written notification of the modification or withdrawal is received by the Contracting Authority prior to the end of the time-limit prescribed for the submission of the bids. The said notification must be signed by an authorised representative in application of article 20(2) of the General Regulations. The modification or the corresponding replacement bid must be attached to the written notification. As the case may be, the envelopes must bear the inscription “WITHDRAWAL”, and “REPLACEMENT BID” or “MODIFICATION”.

24.2 Notification of modification, replacement or withdrawal of the bid by the bidder should be prepared, sealed, marked and forwarded in accordance with the provisions of article 21 of the General Regulations. Withdrawal may equally be notified by telex but should in this case be confirmed by a duly signed written notification whose date, post mark being authentic, shall not be posterior to the time-limit set for the submission of bids.

24.3 In application of article 24(1), bids being requested to be withdrawn by bidders shall be returned to them unopened.

24.4 No bid may be withdrawn during the interval between the submission of bids and the expiry of the validity of bids specified by the model tender. The withdrawal of a bid by a bidder during this interval may lead to the confiscation of the bid bond in accordance with the provisions of article 17(6) of the General Regulations.

E.  Opening of envelopes and evaluation of bids

Article 25: Opening of envelopes and petitions
25.1 The BAFUT Council Tenders Board shall open the envelopes in single or double phases and in the presence of the representatives of bidders who wish to attend at the date, time and address specified in the Special Regulations. Representatives of bidders shall sign a register attesting to their presence.

25.2 Firstly, envelopes marked “withdrawal” shall be opened and the contents announced to the hearing of everyone, while the envelope containing the corresponding bid shall be returned to the bidder unopened. Withdrawal shall be allowed only if the corresponding notification contains a valid empowerment of the signatory to request this withdrawal and if this notification is read to the hearing of everyone. Then the envelopes marked “Replacement bid” are opened and announced to the hearing of everyone and the new corresponding bid substituted for the preceding one which will be sent to the bidder concerned unopened. The replacement of the bid shall only be allowed if the corresponding notification contains a valid empowerment of the signatory requesting the replacement and read to the hearing of everyone. Lastly, the envelopes marked “modification” shall be opened and their contents read to the hearing of everyone with the corresponding bid. The modification of the bid shall only be allowed if the corresponding notification contains a valid empowerment of the signatory requesting the modification and read to the hearing of everyone. Only bids which were opened and announced to the hearing of everyone during the opening of bids shall then be evaluated.

25.3 All envelopes shall be opened successively and the name of the bidder announced aloud as well as the possible modification mentioned, the price offered, including any rebates [in case of opening of financial bids] and any variant, where necessary, the existence of a guarantee of the bid if it is required and any other details which the Contracting Authority deems useful to be mentioned. Only rebates and variants of bids announced to the hearing of everyone during the opening of bids shall be submitted for evaluation.

 25.4 Bids (and modifications received in accordance with the provisions of article 24 of the General Regulations) which were not opened and read to the hearing of everyone during the bid-opening session for whatever reason, shall not be submitted for evaluation.

25.5 Bid-opening minutes are recorded on the spot mentioning the admissibility of bids, their administrative regularity, prices, rebates and time-limits as well as the composition of the Evaluation sub-committee. A copy of the said minutes to which is attached the attendance sheet is handed over to all the participants at the end of the session.

25.6 At the end of each bid-opening session, the chairperson of the Tenders Board immediately hands over to the focal point designated by the body in charge of regulation of Public Contract an initialled copy of the bids presented by bidders.

25.7 In case of petition as provided for by the Public Contracts Code, it should be addressed to the Minister Delegate in charge of Public Contracts with a copies to the body in charge of the regulation of Public Contracts, the head of structure to which is attached the Tenders Board concerned. 
	
	It must reach within a maximum deadline of three (3) working days after the opening of bids in the form of a letter to which is obligatorily attached a sheet of the petition form duly signed by the petitioner and possibly by the chairperson of the Tenders Board.
	
	The Independent Observer attaches to his report the sheet that was handed to him, including any related commentaries or observations.

Article 26: Confidential nature of the procedure
26.1 No information relating to the examination, clarification, evaluation and comparison of bids and verification of the qualification of the bidders and the recommendation for the award shall be given to bidders or to any person not concerned with the said procedure as long as the preferred bidder has not been made public, subject to the disqualification of the bid of the bidder and suspension of the authors from all activities in the domain of Public Contracts. 

26.2 Any attempt by a bidder to influence the Tenders Board or the Evaluation sub-committee of bids or the Contracting Authority in its award decision may lead to the rejection of his bid.

26.3 Notwithstanding the provisions of paragraph 26.2 above, between the opening of bids and the award of the Contract, if a bidder wishes to enter into contact with the Contracting Authority for reasons having to with his bid may do so in writing. 

Article 27: Clarifications on the bids and contact with the Contracting Authority
27.1 To ease the examination, evaluation and comparison of bids, the Tenders Board may, if it so desires, request any bidder to give clarifications on his bid. This request for clarification and the response thereto are formulated in writing but no change on the amount or content of the bid is sought, offered or authorised, except it is necessary to confirm the correction of calculation errors discovered by the Evaluation Sub-committee during the evaluation in accordance with the provisions of article 30 of the General Regulations.

27.2 Subject to the provisions of paragraph 1 above, bidders shall not contact members of the Tenders Board and the Evaluation Sub-committee for questions related to their bids, between the opening of envelopes and the award of the Contract.

Article 28: Determination of compliance of bids
28.1 The Evaluation sub-committee shall carry out a detailed examination of bids to determine if they are complete, if the required guarantees are furnished, if the documents were correctly signed and if generally the bids are in proper order.

28.2 The Evaluation sub-committee shall determine if the bid is essentially in compliance with the conditions fixed in the Tender File based on the content without recourse to external elements of proof.  

28.3 A bid that complies with the Tender File shall essentially be a bid that respects all the terms, conditions and specifications of the Tender File, without substantial divergence or reservation.  A substantial divergence or reservation is that:

i) which substantially limits the scope, quality or realisation of the works;

ii) which substantially limits, contrary to the Tender File, the rights of the Contracting Authority or his obligations in relation to the Contract; 

iii) Whose correction would unjustly affect the competitiveness of the other bidders who presented bids that essentially complied with the Tender File?

28.4   If a bid is essentially not in compliance, it shall be rejected by the competent Tenders Board and shall not subsequently be rendered in compliance.

28.5   The Contracting Authority reserves the right to accept or reject any modification, divergence or reservation. Modifications, divergences, variants and other factors which are beyond the requirements of the Tender File shall not be considered during the evaluation of bids.

Article 29: Qualification of the bidder
	  The Evaluation sub-committee shall ensure that the successful bidder retained for having submitted a bid substantially in compliance with the provisions of the Tender File, fulfils the qualification criteria stipulated in article 6 of the Special Regulations. It is essential to avoid any arbitrariness in determining qualification.

Article 30: Correction of errors
30.1 The Evaluation sub-committee shall verify bids considered essentially in compliance with the Tender File to correct the possible calculation errors. The Evaluation sub-committee shall correct the errors in the following manner:

(a) where there is an incoherence between the unit price and the total obtained by multiplying the unit price by the quantity, the unit price being authentic, the total price shall be corrected, unless the Evaluation sub-committee judges that it is a gross error of decimal point in the unit price in which case the total price as presented shall be authentic and the unit price corrected.
(b) If the total obtained by addition or subtraction of the totals is not exact, the sub totals shall be considered authentic and the total corrected.
(c) Where there is a difference between the price indicated in letters and in figures, the amount in letters shall be considered authentic, unless the amount is linked to an arithmetical error confirmed by the sub-detail of the said price, in which case the amount in figures shall prevail subject to paragraphs (a) and (b) above.

30.2 The amount featuring in the bid shall be corrected by the Evaluation sub-committee, in accordance with the error correction procedure above and with confirmation by the bidder, the said amount shall be deemed to commit him.

30.3 If the bidder who presented the bid evaluated as the lowest refuses the correction thus carried out, his bid shall be rejected and the bid bond may be seized. 

Article 31: Conversion into a single currency
31.1 To facilitate the evaluation and comparison of bids, the Evaluation sub-committee shall convert the prices of bids expressed in various currencies into those in which the bid is payable in CFA francs. 

31.2 The conversion shall be done using the selling rate fixed by the Bank of Central African States (BEAC) under the conditions defined by the Special Regulations.

Article 32: Evaluation and comparison of financial bids 

32.1   Only bids considered as being in compliance, as per the provisions of article 28 of the General Regulations, shall be evaluated and compared by the Evaluation sub-committee.

32.2 By evaluating the bids, the Evaluation Sub-committee shall determine for each bid the evaluated amount of the bid by rectifying the amount as follows:

a)  By correcting any possible error in accordance with the provisions of article 30.2 of the General Regulations;
b) By excluding projected sums and where necessary provisions for unforeseen occurrences featuring in the bill of quantities and estimates but by adding the amount of works done under State supervision where they are coasted in a competitive manner as specified in the Special Regulations.
c)  By converting into a single currency the amount resulting from the rectifications (a) and (b) above, in accordance with the provisions of article 31(2) of the General Regulations;
d) By appropriately adjusting any other modification, divergence or quantifiable reservation on technical or financial basis.
e) By taking into consideration the various execution time-limits proposed by the bidders, if they are authorised by the Special Regulations;
f) If need be, in accordance with the provisions of article 13(2) of the General Regulations and the Special Regulations by applying the rebates offered by the bidder for the award of more than one lot, if this Invitation to Tender is launched simultaneously for several lots.
g)  If need be, in accordance with the provisions of article 18(3) of the Special Regulations and the Technical Specifications, the proposed technical variants, if they are permitted, shall be evaluated on their own merit and independently of the fact that the bidder offered or not a price for the technical solution specified by the Contracting Authority in the Special Regulations.

32.3 The estimated effect of price revision formulae featuring in the GAC and SAC applied during the period of execution of the Contract shall not be considered during the evaluation of bids.

32.4 If the bid judged the lowest bid is considered abnormally low or strongly unbalanced in relation to the estimates of the Project Owner for the works to be executed in this Contract, the Tenders Board may, from the sub-details of prices furnished by the bidder for any element or all the elements of the bill of quantities and estimates, verify if these prices are compatible with the construction methods and proposed calendar. In the case where the justifications presented by the bidder are not satisfactory, the Contracting Authority may reject the bid after the technical opinion of the Public Contracts Regulatory Agency.	

Article 33: Preference granted national bidders
National Contractors shall benefit from a margin of national preference during the evaluation of bids as provided for in the Public Contracts Code.

Article 34: Award 
34.1     The Contracting Authority shall award the Contract to the bidder whose bid was judged essentially in compliance with the Tender File and who has the required technical and financial capacities to execute the Contract satisfactorily and whose bid was evaluated as the lowest by including, where necessary, proposed rebates

34.2     If, according to article 13(2) of the General Regulations, the Invitation to tender comprises several lots, the lowest bid shall be determined by evaluating this Contract with other lots to be awarded concurrently, by taking into account the rebates offered by the bidders in the case of more than one lot. 

34.3       Any award of Contract shall be made to the bidder fulfilling the technical and financial capacities required resulting from the evaluation criteria and presenting the bid evaluated as the lowest. 

Article 35:  The right by the Contracting Authority to declare an Invitation to Tender unsuccessful or cancel a procedure 
The Contracting Authority reserves the right to cancel a procedure of Invitation to tender after the authorisation of the Minister Delegate at the Presidency in charge of Public Contracts where the bids have been opened or to declare an Invitation to tender unsuccessful after the advice of the competent Tenders Board, without any claims being entertained.

Article 36: Notification of award of the Contract
               Before the expiry of the validity of the bids set in the Special Regulations, the Contracting Authority shall notify the preferred bidder by telecopy confirmed by registered mail or by any other means that his bid was retained. This letter will indicate the amount the Project Owner will pay the Contractor to execute the works and the execution time-limit.

Article 37: Publication of results of award and petitions
37.1 The Contracting Authority shall communicate to any bidder or administration concerned, upon request addressed to it within a maximum deadline of five (5) days after publication of the award results, the Independent Observer’s report as well as the minutes of the award session of the related Contract to which shall be attached the evaluation report of the bids.

37.2 The Contracting Authority is bound to communicate the reasons for the rejection of bids of the bidders concerned who so request.

37.3 After publication of the award results, bids that are not withdrawn within fifteen (15) days shall be destroyed, without any claims for compensation being entertained. Only the copy destined for the body in charge of regulation shall be kept.

37.4 In case of petition, it should be addressed to the Public Contracts Authority, with copies to the body in charge of the regulation of Public Contracts, the Contracting Authority and the chairperson of the Tenders Board concerned.

It must take place within a maximum deadline of five (5) working days after the publication of the results.

Article 38: Signing of the Contract
38.1    After publication of the results, the draft Contract subscribed by the successful bidder is submitted to the Tenders Board for examination and where applicable, to the Minister in charge of Public Contracts for prior endorsement. 

38.2     The Contracting Authority has a deadline of seven (7) days to sign the Contract from the date of acceptance of the draft Contract examined by the competent Tenders Board and subscribed by the successful bidder and where applicable, the endorsement of the Minister in charge of Public Contracts.

38.3    The Contract must be notified to the successful bidder within five (5) days of its date of signature.

Article 39:  Final Bond 
 39.1    Within twenty (20) days of the notification by the Contracting Authority, the Contractor shall furnish the Project Owner with a final bond, to guarantee the complete execution of the works. 
39.2    The bond whose rate varies between 2 and 5 percent of the amount of the Contract inclusive of all taxes, may be replaced by a guarantee from a banking establishment approved according to the instruments in force with the Project Owner as beneficiary or by a joint or several guarantee.

39.3   Small and medium-sized enterprises (SME) constituted of national capital and managed by nationals may, in lieu of the guarantee, provide a statutory lien or a bond issued by a banking establishment or first rate financial institution approved in accordance with the instruments in force.

39.4     Failure to produce the final bond within the prescribed time limit shall likely cause the termination of the Contract under the terms laid down in the General Administrative Conditions.     
.     
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    THE SPECIAL REGULATIONS OF THE INVITATION TO TENDER 






  	    























	References of the General regulations
	General

	1.1
	Definition of works:
THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION BY AN EMERGENCY PROCEDURE

Name and address of the Contracting Authority: , The Mayor BAFUT Council, Contracting Authority

Reference of Invitation to Tender: No 19/ONIT/MINDDEVEL/BC/BCITB/2026 OF 23/10/26 BY EMERGENCY PROCEDURE

	2.1
	Execution deadline: 8 months (240) days


	3.1
	Source of financing
Works which form the subject of this Invitation to Tender shall be financed by  the FEICOM/BAFUT Councill investment budget 

	4.1
	List of pre-qualified candidates, not applicable


	5.1
	Origin of building materials, equipment, materials, supplies and equipment: The materials will generally be from natural sources in Cameroon.





6.1 Evaluation criteria
The bids shall be evaluated according to the main criteria as follows:

Eliminatory criteria
1. Absence or insufficient bid bond.
2. Absence of a CDEC receipt issued by the compétent authority
3.  Non-respect of  the 48hrs given for the absence or non-conformity of any other document in the administrative file;
4. False declaration or falsified documents;
5. A bid with the external envelope carrying a sign or mark leading to the identification of the bidder;
6. Incomplete bids;
7. Absence of a quantified unit price;
8. Change of quantity or unite price in the financial file 
9. Deadline for delivery higher than the prescribed
10. Score of less than  75% of essential criteria;
11. Financial capacity below 50% of the project cost
12. Absence of a valid copy of a certificate of categorization under the competent sub sector. (Legalised by the competent authority) 
C. Essential criteria
NB. Pursuant to circular letter No.00005/LC/MINMAP/CAB of 26/12/2023, bidders with certified true copies of the certificate of categorisation shall not submit in their TECHNICAL FILE documents relating to ; Their turnover, References of the company, own minimum technical and Logistics means ,permanent staff and head office location.

· General presentation of the Tender Files;
·  Financial capacity;
· References of the company in  similar achievements;
· Quality of the personnel;  
· Technical organization of the works;
· Safety measures on the site;
· Logistics;
· Attestation and report of site visit;
· Special Technical Clauses initialed in all the pages;
· Special Administrative Clauses completed and initialed in all the pages.
The criteria relating to the qualification of candidates could be indicative on the following:
The essential criteria are subjected to minima whose detail is given in the Special Tender Regulation (RPAO).
This evaluation will be done in a purely positive way (yes) or negative (no) with an acceptable minimum from at least (75%) of the essential criteria taken in account.
The Contract will be awarded to the bidder who would have proposed the offer with the lowest amount, in conformity with the regulations of the Tender Documents and having satisfied to 100% of the eliminatory criteria and at least (75%) of the essential criteria.

ARTICLE 6 :Language of the bids:
            The offer like any correspondence and all documents concerning the tender, exchanged between the tenderer and the Project Owner will be written in French or English. The complementary documents and the printed papers form provided by the Bidder can be written in another language in condition of being accompanied by a precise translation in French or English; in which case and for purposes of interpretation of the offer, the translation will be taken. 

7.PRESENTATION OF THE TENDER.
The bids prepared in English or French and in seven (07) copies with one (01) original and six (06) copies marked thus, shall be presented in three (03) volumes as follows: 

A)	Administrative Documents
B)	Technical Documents
C) Financial Documents

7.1	External envelope. 
	Each bidder shall seal these three (03) envelopes (A, B and C) in one common envelope on which shall be written. 

<< OPEN NATIONAL INVITATION TO TENDER
NO 19/ONIT / MINDDEVEL / FEICOM/ BC/BCITB/NWR/ 2026 OF THE   23/10/2026 FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
BY AN EMERGENCY PROCEDURE.>>

	“TO BE OPENED ONLY DURING THE BID-OPENING SESSION”

N.B:	The external envelope should not carry any mark or sign that can lead to the identification of the bidder. 

NB. Pursuant to circular letter No.00005/LC/MINMAP/CAB of 26/12/2023, bidders with certified true copies of the certificate of categorisation shall not submit in their TECHNICAL FILE documents relating to ; Their turnover, References of the company, own minimum technical and Logistics means ,permanent staff and head office location.

7.2	Internal envelopes
	Three (03) internal envelopes must be sealed in an external envelope. 
The   first internal envelope shall be labeled; 
<<ENVELOPE A: ADMINISTRATIVE DOCUMENTS>> and shall contain the administrative documents of the enterprise.  These documents shall be original or copies certified by competent authorities   not more than three months.

ADMINISTRATIVE DOCUMENTS.
	DOC N°
	DESCRIPTION

	A.1
	Certified Copy of the Business Registration, not more than three months old.

	A.2
	Declaration of intention to tender stamped with the tariff en force (see model).

	A.3
	Certificate of non-bankruptcy established by the Court of 1st instance or the Chamber Commerce, Industry and Trade of the place of residence of the bidder, not more than three (03) months.

	A.4
	Attestation of bank account of the bidder, issued by a first rate-bank approved by the Ministry in charge of Finance or by a foreign bank the first order not more than three months. 

	A.5
	Purchase receipt of Tender File issued by BAFUT council treasury of One hundred and fifty thousand FCFA (150.000 FCFA)

	A.6
	A bid bond of THREE MILLION FIVE HUNDRED AND SEVENTY THOUSAND NINE HUNDRED AND TWENTY SEVEN FCFA (3,579,927 CFA) issued by a first rate-bank approved by the Ministry in charge of Finance in conformity with COBAC conditions.
The said guarantee must be accompanied by a consignment receipt issued by the “Caisse Depôt et Cosignation (CDEC) in accordance with Circular letter No 0000019/L/MINMAP of 5th June 2024 relating to the constitution of deposits, retention, restitution and deconsignment of bonds on public contracts

	A.7
	An attestation of non-exclusion from Public Contracts issued by the Public Contract Regulatory Board (ARMP)

	A.8
	An Attestation of the National Social Insurance Fund stating that the bidder has met all his obligations vis a vis the Fund; the attestation should be valid within the specified time

	A.9
	A valid Certificate of Fiscal conformity stamped with the tariff en force 

	A.10
	Copy of valid taxpayers card stamped with the tariff en force 

	A 11
	location plan of the enterprise stamped with the tariff en force

	A 12
	Power of attorney if necessary

	A 13
	Group agreement if need be





The absence of or insufficient bid bond, a valid copy of a CDEC receipt, a valid certificate of categorization and the non-respect of the   48hrs given for the absence or non-conformity of any other document in the administrative file will result to the elimination of the offer.


The second Internal Envelope shall be labeled <<ENVELOPE B:  TECHNICAL DOCUMENT>> and shall contain the following: 

	Eliminatory Criteria (See evaluation of administrative files) 

	Designation
	BIDDERS

	
	A
	B
	C

	 
	a. General presentation of bids
	EVALUATION (Yes or No)

	a1
	˗ Document spirally bound 
	 
	 
	 

	a2
	˗ Table of content page
	 
	 
	 

	a3
	˗ Colour sheets separation apart from white
	
	
	

	
	-page numbering
	
	
	

	a4
	- neatness and clarity of documents
	 
	 
	 

	a5
	˗  Presentation of documents in the order given in this tender 
	 
	 
	 

	
	
	
	
	

	 
	TOTAL a
	/5
	/5
	/5

	 
	b. The company references
	EVALUATION (Yes or No)

	
	References of the company in civil construction or similar works for the past Five years 
	 
	 
	 

	b1
	At least 01 Certified copy of similar contracts equal or above 180 million (1st and last page) and PV of provisional reception for projects executed within the last five years (pluri annual projects accepted)
	 
	 
	 

	b2
	Atleast 01 Certified copy of similar contracts below 100 million and more than 50 million (1st and last page) and PV of provisional reception.
	 
	 
	 

	 
	TOTAL  b
	/2
	/2
	/2

	 
	c. Equipment
	EVALUATION (Yes or No)

	c1
	Proof of ownership or hire of a liason vehicle (Pick up 4 x 4 or van) (Hired or owned)
	 
	 
	 

	c2
	Proof of ownership or hire of a truck of at least 20 tonnes capacity
	 
	 
	 

	c3
	Proof of ownership or hire of a front head loader or similar equipment
	 
	 
	 

	c4
	Proof of ownership or hire of a bulldozer of good condition
	 
	 
	 

	c5
	Proof of ownership or hire of a theodolite
	 
	 
	 

	c6
	Proof of ownership or hire of an optical level equipment
	 
	 
	 

	c7
	 Proof of ownership or hire of a compactor in good condition
	 
	 
	 

	c8
	Prof of ownership of a survey kit
	 
	 
	 

	c9
	Prof of ownership of a carpentry kit
	 
	 
	 

	c10
	Prof of ownership of a masonry kit
	 
	 
	 

	 
	TOTA 2 
	/10
	/10
	/10

	 
	d. Personnel of the Enterprise
	EVALUATION (Yes or No)

	 
	Works Engineer: Civil Engineer or Bachelor in Civil Engineering with at least 5yrs of experience and member of the National order
	 
	 
	 

	d1
	Certified copy of valid national identity card
	 
	 
	 

	d2
	 Diploma of work Engineer certified 
	 
	 
	 

	d3
	CV signed and dated by works Engineer
	 
	 
	 

	d4
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	 
	Site foreman: Senior Civil Engineering technician or HND with atleast 5yrs experience
	 
	 
	 

	d5
	Certified copy of valid national identity card
	 
	 
	 

	d6
	 Certified copy of certificate of Foreman 
	 
	 
	 

	d7
	CV signed and dated by site foreman
	 
	 
	 

	d8
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	 
	Chief mason: CAP, at least 5yrs of experience
	 
	 
	 

	d9
	Certified copy of valid national identity card
	 
	 
	 

	d10
	Certified copy of diploma
	 
	 
	 

	d11
	Cv signed and dated
	 
	 
	 

	d12
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	 
	Chief surveyor; Atleast Probatoir in survey with atleast five years’ experience
	 
	 
	 

	d13
	Certified copy of valid national identity card
	 
	 
	 

	d14
	Certified copy of diploma
	 
	 
	 

	d15
	Cv signed and dated
	 
	 
	 

	d16
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	 
	Chief carpenter: Atleast CAP in wood work/joinery atleast three years
	 
	 
	 

	d17
	Certified copy of valid national identity card
	 
	 
	 

	d18
	Certified copy of diploma
	 
	 
	 

	d19
	Cv signed and dated
	 
	 
	 

	d20
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	
	Hygiene, safety and environment manager.
(Environmentalist A/L+3 or more
	
	
	

	d21
	Certified copy of valid national identity card
	
	
	

	d22
	Certified copy of diploma
	
	
	

	d23
	Cv signed and dated
	
	
	

	d24
	Attestation of availability dully signed by bearer and dated
	
	
	

	
	
	 
	 
	 

	 
	TOTAL d
	/25
	/25
	/25

	 
	e) Technical Proposals
	EVALUATION (Yes or No)

	e1
	Attestation of site visit
	 
	 
	 

	e2
	Site visit report with pictures duely signed by presenter 
	 
	 
	 

	e3
	Detailed technical note and proposals
	 
	 
	 

	 
	TOTAL e
	/3
	/3
	/3

	 
	f) The methodology of intervention and execution of work
	EVALUATION (Yes or No)

	f1
	Site organisation in teams or options
	 
	 
	 

	f2
	Description of the socio - environment measures for site protection
	 
	 
	 

	f3
	Dispositions prevued for the securisation of personnel and and other ussers
	 
	 
	 

	f4
	Use of local manpower
	 
	 
	 

	f5
	CCTP dully initialled and dated on each page and signed on the last page
	 
	 
	 

	 
	TOTAL f
	/5
	/5
	/5

	 
	g. Planning of execution of works
	EVALUATION (Yes or No)

	g1
	Coherent planning with respect to tasks
	 
	 
	 

	g2
	Manpower deployment plan
	 
	 
	 

	g3
	Material deployment plan
	 
	 
	 

	g4
	Organisational chart of the enterprise
	 
	 
	 

	 
	TOTAL g
	/4
	/4
	/4

	
	
	
	
	

	 
	I.  Pre-financing
	EVALUATION (Yes or No)

	h1
	Attestation of credibility shall be at least 55% of the bid price
	 
	 
	 

	 
	TOTAL 
	/1
	/1
	/1

	 
	GRAND TOTAL
	/54
	/54
	/54


ENVELOPE C- FINANCIAL FILE

	No.
	DESIGNATION.

	C1
	A submission letter, signed, dated and stamped.(see ANNEX 3)

	C2
	Completed and signed frame work of unit prices. 

	C3
	Signed Bills of quantities and cost estimates indicating the total amount without taxes (HT) and with taxes (TTC) 

	C4
	Signed Sub details of unit prices



THE BIDDER SHALL MEET AT LEAST 70% OF THE ESSENTIAL CRITERIA (54 sub-criteria), which is 38“Yes” sub-criteria out of 54 TO BE ELIGIBLE FOR FINANCIAL EVALUATION

· The bidders will use for this purpose the documents and models envisaged in the Tender Documents, subject to the provisions of Article 19.2 of the RGAO concerning the other possible forms of bid bond. 
· The various parts of the same file must be separated with colour guides from the original as well as in the copies, so as to facilitate its examination
	
	II. Envelope B - : Technical file

The Technical Bid shall contain the documents below:

A. Methodology

· A descriptive note, stating the execution methods proposed by the bidder and enabling to appreciate the compliance of the bid with the specifications of the tender file. The bidder shall draw up a detailed report of his nspection of the site, then shall state especially the measures which he is committed to in terms of site installations (place, surfaces, brick-and-mortar constructions or mobile installations, equipment, etc.), construction site laboratory (surfaces, equipment…), execution studies, supplies of construction site equipment and materials, etc. He shall detail the proposed organisational chart and the relations between the construction site and the company’s head office)
· A works schedule stating the overall time frame and partial deadline of the main phases of the execution of works. It should enable to appreciate the compatibility between the work rates stated in this programme and those mentioned in the price sub-details. This works schedule shall take into account the maximum deadline for the services which shall be 8 (eight) months.

B. Supervisory staff
The bidder shall enclose the list of the following personnel in his bid, which he signs and dates.
	[bookmark: _Hlk238129156]S/N
	Position
	Overall experience (years)
	Experience in similar work in the position
(number of projects)

	1
	Works Engineer: Civil Engineer or Bachelor in Civil Engineering with at least 5yrs of experience and member of the National order
	 Five (05) years or more
	5 (five) years or more

	2
	Site foreman: Senior Civil Engineering technician or HND with atleast 5yrs experience)
	Eight (08) years or more
	5 (five) or more

	3
	Chief mason: CAP, at least 5yrs of experience Bacc F4/Equivalent Technical A/L or more)
	Three (03) years or more
	3 (three) or more

	4
	Chief surveyor; Atleast Probatoir in survey with atleast five years’ experience (Electrical Engineer A/L+5)
	Three (03) years or more
	5 (five) or more

	05
	Chief carpenter: Atleast CAP in wood work/joinery atleast three years
	Three (03) years or more
	3 (three) or more

	06
	Hygiene, safety and environment manager.
(Environmentalist A/L+3 or more)
	Three (03) years or more
	3 (three) or more




All these supervisory members of staff must know how to read, write and perfectly speak at least one of the two official languages of Cameroon.

C. Technical resources and equipment
The bidder shall enclose in his bid the attestation of the availability of the equipment below, which he has signed.
	S/N
	Type and characteristics of the equipment 
	YES/NO

	1
	At least 1 10-wheel dump truck of 20 tonnes minimum
	YES/NO

	2
	2 (two) Deux(02) concrete mixers of 500 litres minimum
	YES/NO

	3
	Topographical equipment (total station, spirit level etc.)
	YES/NO

	4
	1 (one) 4x4 Pick-up type or station wagon type liaison vehicule
	YES/NO

	5
	A generator
	YES/NO

	6
	Equipment for geotechnical tests (Abrams cone, complete set of sieves, sand equivalent, concrete sample test tube, weighing scale to be determined, Total station) or subcontract with an approved firm.
	YES/NO

	8
	2 concrete vibrators (engine and stabilising cables).
	YES/NO

	6
	Light site equipment : 
· 10 wheelbarrows ;
· 20 trowels ; 
· 20 spirit levels ;
· 20 shovels, pickaxe ; 
· 20 shears ;
· 20 pliers ;
· 20 clamps.
	YES/NO

	7
	Site IT equipment (computer, printer and photocopier).
	YES/NO

	8
	Proof of ownership or higher of dump truck
	YES/NO

	9
	Proof of ownership or higher of concrete mixer
	YES/NO




D. Certificate of site inspection signed by the bidder on his honour

E. Code of Conduct (ESHS)
The bidder shall submit the Code of Conduct applicable to his staff and subcontractors, in order to ensure compliancy good practices (ESHS) specified in the contract.
In addition, the bidder shall detail the manner in which the Code shall be implemented. This shall include the manner in which it shall be presented in the terms of employment and work contract, the training which shall be provided, the monitoring and manner in which the bidder intends to deal with possible breaches.
The bidder shall apply the Code of Conduct.

F.  Management strategies and plans for implementing the management of ESHS risks
The bidders shall submit management strategies and plans for the implementation of the management of major risks in these areas: environmental, social, hygiene and safety (ESHS).
The said strategies and plans shall describe in detail the actions, materials, equipment, management processes, etc. which will be implemented by the bidder and his subcontractors.
During the preparation of these strategies and plans, the bidder shall include ESHS provisions in the contract, including those which could be described in detail in the following documents:
1.  [the described Works Specifications];
2.  [environmental and social management plan (ESMP)] ;
Furthermore, the bidder shall give a broad perspective of the manner in which the Code shall be implemented. This shall include the manner in which it shall be presented in the terms of employment and work contract, the training which shall be provided, monitoring and manner in which the bidder intends to deal with possible breaches.




	
25.1.
	TENDERING METHOD
The tendering method selected for this tender shall be offline.






	
	
	
	

	S/N
	DOCUMENTS
	OPERATION TO BE CARRIED OUT
	AUTHENTICATION

	B5
	Technical proposals
	· Methodological note on the understanding, organisation and execution of works;
· Works site inspection report;
· Orks execution schedule;
· Measures taken for the protection of site’s environment, hygiene and safety;
· Project’s organisational chart;
· Code of Conduct (ESHS);
· Management strategies and ESHS risks management  implementation plans

	Date, signature and stamp of the bidder at the end of this document.

	B6
	Certificate of site inspection
	A certificate of site inspection signed by the Project Owner or his representative or a statement made on honour signed and stamped by the bidder.
	Date, signature and stamp of the Project Owner or his representative or of the the bidder

	B7
	Staff
	Qualifications and experience of the staff posted to the project as stated above
	

	B8
	Company’s references
	General experience in Public Works and specific experience in similar projects

	

	B9
	Equipment
	The candidate shall establish that he owns or has rented the equipment as described above.

	

	B10
	Proof of acceptance of the contract’s conditions
	· Special Technical Clauses as mentioned in Document No. 5 of the Tender File.
· Special Administrative Clauses as mentioned in Document No. 2 of the Tender File.
· Environmental, Social, Hygiene and Safety Clauses in Document No. 6 of the Tender File
	Initialled on each page and signed at the end of the document, with the date, signature and stamp of the bidder.




Supply price
ARTICLE 8: Currency of payment
This National Invitation to Tender is awarded on total and Contractual price, inclusive of all taxes, firm and non-revisable for the whole of the works and the equipment defined in the present Invitation to Tender. 
	The corresponding amount will be calculated inclusive of all taxes and the prices will be obligatorily expressed in francs CFA. 
	The unit Schedule price expressed out in figures and letters and in seven (07) copies will be joined to the offer. In the event of error between the prices in figures and letters, the latter will precede and be used as a basis of calculation of the amount of the offer. 
	The establishment of the prices will be done on the basis of economic condition into force in Republic of Cameroon at the handover date of the offers.

ARTICLE 9:Transport and delivery
The materials for work must be protected during transportation through packaging whether by air, railway or road according as the case may be. The conditions of storage must be of tropical type.  
ARTICLE 10:Guarantee and retention guarantee
10.1 Provisional guarantee
The amount of the provisional guarantee or guarantee of tender is fixed at seventeen million eight hundred and fifty four thousand, six hundred and thirty eight  FCFA (17,854 638 CFA). 
 The time of validity of this guarantee is ninety (90) days as from the date of depositing of the offers.

10.2 Final Bond
The final Bond is fixed at two percent (2%) of the initial amount of the services envisaged in the country. 
It could be replaced by a guarantee personal and interdependent of a banking house approved by the Ministry of Finances following COBAC conditions.  
It will have to be made up in the twenty (20) days following the notification of the signature of the Contract in a bank approved by the Minister in charge of Finances.
 10.3   Guarantee Retention 
	Guarantee Retention of ten percent (10%) will be operated on amount including all taxes of the Contract. The corresponding sum will be paid or the released guarantee, with the final reception of work.
ARTICLE 11: Period of validity of the offers
The bidder will remain committed to his offer for ninety (90) days as from the handover date of the offers. 
If at the end of this period, the Contract were not notified to him, the bidder will be able, either to cancel his offer, or to ask for a new negotiation of the unit prices.	
ARTICLE 12: A number of copies of the offer which must be filled and sent
	The tender, as all the parts accompanying it will have to be given in six (0 7) copies, including one (01) original and five (06) copies. The bidder will present his/her bids inside a sealed outer jacket being marked:
<< OPEN NATIONAL INVITATION TO TENDER
NO 19/ONIT / MINDDEVEL / FEICOM/ BC/BCITB/NWR/ 2026 OF THE   23/10/2026 FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
BY AN EMERGENCY PROCEDURE.>>
TO BE OPENED ONLY DURING THE OPENING SESSION»
ARTICLE 13: Date and latest time of deposit of offers
	The offers will have to arrive under closed fold and sealed envelopes latest the 06/11/26 at 10:00 am, deposited against receipt from the Bafut council to the following address:
THE MAYOR, BAFUT COUNCIL
CONTRACTING AUTHORITY
	             Beyond this time no offer will be received nor accepted.
ARTICLE 14: Opening of the bids
	The opening of the folds will be carried out in the conference room of the Conference Hall of BAFUT Council on the 06/11/26 as from 11 am, by the BAFUT Council Internal Tenders Board sitting in the presence of the duly elected bidders or their representatives and having a good knowledge of the file.

AWARD OF THE CONTRACT
ARTICLE 15: Award of the Contract
	 The Tenders Board will propose to the Contracting Authority to award the Contract to the bidder who will have presented the offer with the lowest offer, essentially conforming to the regulations the Tender File, having satisfied to 100% of all the eliminatory criteria and at least (75%) of the essential criteria taken into account. 
	The decision carrying attribution of the Contract will be published by way of press release or any other means of publication of use in the Administration. 
If the Contract passed on the basis of technical alternative suggested by the bidder, the Contracting authority reserves the right to introduce all the provisions there allowing him to guarantee itself against the real overrun costs of the alternative compared to his estimate of origin. In the absence of these last precise details, any additional charge due to an alternative will be inadmissible. 
	To this end, it is specified that a bidder cannot claim to be compensated, if it is not taken action on his offer. 
	The Contracting authority reserves the right not to take action on an Invitation to Tender, if it   did not obtain a proposal which appears acceptable to him.

ARTICLE 16: COMMENCEMENT OF WORK:
Before the commencement of work the Contractor must be installed on the site by the following:
· The Project Owner or his representative.                                                	
· The General Manager of FEICOM or his representative                                                  
· The C/SSCI  of FEICOM NORTH-WEST Agency                   
· The Contract Manager (CDO BAFUT Council)                                                                                                                  
· The DD MINMAP/Mezam or representative                         
· The Contract Engineer DD MINTP                                         
· The Council Project Manager (SG Bafut Council)	             		
· The Contractor or his representative				
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SPECIAL ADMINISTRATIVE CONDITIONS (SAC)




































Table of contents
Chapter I: General
Article 1     - Subject of the contract
Article 2     - Award procedure
Article 3     - Definitions and duties (article 2 of GAC supplemented)
Article 4     - Language, applicable law and regulations
Article5     - Constituent documents of the contract (article 4 of GAC)
Article 6     - General applicable instruments
Article7     - Communication (GAC articles 6 and 10 supplemented)
Article8     - Administrative Orders (article 8 of GAC supplemented)
Article9     - Contracts with conditional phases (article 15 of GAC)
Article 10   - Contractor’s personnel (article 15 of GAC supplemented) 
Chapter II: Financial conditions
Article 11   - Guarantees and bonds (articles 29 and 41 of GAC supplemented)
Article 12   - Amount of contract (articles 18 and 19 supplemented)
Article 13   - Place and method of payment 
Article 14   - Price variation (article 20 of GAC)
Article 15   - Price revision formulas
Article 16   - Price updating formulas (article 21 of GAC)
Article 17   - Work under State supervision (article 22 of GAC supplemented)
Article 18   - Evaluation of works (article 23 supplemented)
Article 19   - Evaluation of supplies (article 24 of GAC) supplemented) 
Article 20   - Advances (article 28 of GAC) 
Article 21   - Payments for the works (articles 26, 27 and 30 of GAC supplemented)
Article 22   - Interests on overdue payments (article 31 of GAC supplemented)
Article 23   - Penalties for delay (article 32 of GAC supplemented)
Article 24   - Payment in case of a group of enterprises (article 33 of GAC)
Article 25   - Final detailed account (article 35 of GAC)
Article 26   - General detailed account (article 35 of GAC)
Article 27   - Tax and customs schedule (article 36 of GAC)
Article 28   - Stamp duty and registration (article 37 of GAC)
Chapter III: Execution of the works
Article29   - Nature of works
Article 30   - Obligations of the Project Owner (GAC supplemented)
Article 31   - Execution deadline of contract (article 38 of GAC)
Article32- Roles and responsibilities of the contractor (article 40 of GAC)
Article33- Making available documents and site (article 42 of GAC)
Article34   - Insurance of structures and Civil or Rural responsibility (article 45 of GAC)
Article 35   - Documents to be furnished by the contractor (article 49 supplemented)
Article 36   - Organisation and security of sites (article 50 of GAC)
Article 37   - Implantation of structures (article 52 of GAC)
Article 38   - Sub-contracting (article 54 of GAC)
Article39   - Site laboratory and trials (article 55 of GAC)
Article 40   - Site logbook (article 56 of GAC supplemented)
Article 41   - Use of explosives (article 60 of GAC)
Chapter IV: Acceptance
Article 42   - Provisional acceptance (article 67 of GAC)
Article 43   - Documents to be furnished after execution (article 68 of GAC)
Article 44   - Guarantee time-limit (article 70 of GAC)
Article 45   - Final acceptance (article 72 of GAC)
Chapter V: Miscellaneous provisions
Article 45- Termination of the contract (article 74 of GAC)
Article 46   - Major Impediment (article 75 of GAC)
Article 47   - Differences and disputes (article 79 of GAC)
Article 48   - Drafting and dissemination of this contract
Article 49 and last: Entry into force of the contract




THE SPECIAL ADMINISTRATIVE CONDITIONS (SAC)

Chapter I: General

Article 1:  Subject of contract
The subject of this contract shall be for the construction of a bridge measuring 20m long and 8 meters wide over the Mbee river in Bafut Council, Mezam Division of the North West Region.

Article 2: Contract award procedure.
[bookmark: _Hlk526367306]This contract shall be awarded by,  OPEN NATIONAL INVITATION TO TENDER NO 19/ONIT / MINDDEVEL / FEICOM/ BC/BCITB/NWR/ 2026 OF THE  23/ 10/2026 FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
 (BY AN EMERGENCY PROCEDURE>>

Article 3: Definitions and duties (article 2 of GAC supplemented)

3.1 General definitions (cf. Code)

[bookmark: _Hlk127333690]
· The Contracting Authority shall be the Mayor of BAFUT Council. He awards the contract, ensures the preservation of originals of said Jobbing Order documents and the transmission of copies to Ministry in charge of Public Contracts and to the body in charge of regulation through the focal point designated to this effect.
· The Project Owner shall be the Mayor of BAFUT Council. He represents the beneficiary administration of the services.
· The Authority in charge of the effective provision of the services is the Ministry in charge of Public Contracts. 
· The Contract Manager shall be the Sectary General BAFUT Council. He ensures respect of the administrative, technical and financial conditions and contractual deadlines.
· The Contract Engineer shall be The Divisional Delegate MINTP for MEZAM Division. He shall be responsible for the technical monitoring of the contract
· The Project Manager for this contract is the Divisional Delegate MINTP for MEZAM Division
· The service provider [specify].

3.2 Security
This contract may be used a security subject to any form of transfer of the debt.
In this case:
· The authority in charge of ordering payment shall be the Mayor of BAFUT    Council
· The authority in charge of the clearance of expenditures shall be the General Manager of FEICOM 
· The body or official in charge of payment shall be the Accountant of FEICOM
· The official competent to furnish information within the context of execution of this Jobbing Order shall be the Mayor of BAFUT Council
· The Attributions of the Project Manager is to the control mission in charge of control and supervision of the works, who examines, verifies, testifies and approves the quality and quantity of all works executed. In consequence, he is qualified to prescribe all the dispositions that he judges necessary and confirms all the works well done. He works in collaboration with the Contract Manager.

Article 4: Language, applicable law and regulation

1.2 The language to be used shall be English or French.

1.3 The contractor shall be bound to observe the law, regulations and ordinances in force in Cameroon both within his own organization and in the execution of the contract.

If the laws and regulations in force at the date of signature of this contract are amended after the signature of the contract, the possible direct resulting costs shall be taken into account without gain or loss for either party.

Article 5: Constituent documents of the contract (Article 4 of GAC)

The constituent contractual documents of this contract are in order of priority: (to be adapted to the nature of the works).
1)  The tender or commitment letter;
2)  The bidder’s tender and its annexes in all provisions not contrary to the Special Administrative Conditions (GAC) and the Special Technical Conditions (STC) here under;
3)  The Special Administrative Conditions (SAC);
4)  The Special Technical Conditions (STC);
5)  The particular elements necessary for the determination of the contract price, such as, in order of priority: the unit price schedule, the statement of all-in prices, detailed estimates, the breakdown of all-in prices and the sub-details of unit prices;
6)  Plans, calculation notes, trial documents, geotechnical documents
7)  The General Administrative Conditions applicable on MINEE contracts that went into effect by Order No. 033/CAB/PM of 13 February 2007;
8)  The General Technical Condition(s) applicable on the services forming the subject of the contract 

Article6: General instruments in force

This contract shall be governed by the following general instruments Framework 
1. Law No. 96/12 of 5 August 1996 on the management of the environment;
2. The Mining Code;
3. Instruments governing the various professional bodies;
4. Decree No. 2001/048 of 23 February 2001 relating to the setting up, organization and functioning of the Public Contracts Regulatory Agency (and its various implementing texts) amended and supplemented by Decree No. 2012/076 of 8 March 2012; 
5. Decree No. 2003/651/PM of 16 April 2003 to lay down the procedure for implementing the tax and customs system applicable to public contracts;
6. Decree No. 2020/366 of 20 June 2020 on the Public Contracts Code and its various implementing texts;
7. Decree No. 2012/075 of 8 March 2012 to organize the Ministry in charge of Public Contracts;
8. Order No. 0203/A/MINMAP of 3 July 2020 establishing the Regional Public Contracts Commissions;
9. Letter N°004466/L/MINMAP/CAB of 03 July 2020 to municipal magistrates relating to transitional measures following the publication of a new Public Contracts Code;;
10. Letter N°004465/L/MINMAP/CAB of 03 July 2020 to the Departmental Delegates of the Ministry of Public Contracts relating to transitional measures following the publication of a new Public Contracts Code;
11. Letter N°004464/L/MINMAP/CAB of 03 July 2020 to the Regional Delegates of the Ministry of Public Contracts relating to transitional measures following the publication of a new Public Contracts Code;
12. Letter N°004479/L/MINMAP/SG/DAJ/CRL/CEA2 of 03 July 2020 on the establishment of Internal Contracts Commissions;
13. Circular letter No. 0005/LC/MINMAP/CAB of 3 July 2020 specifying the transitional measures to be observed following the signature and publication of Decree No. 2020/366 of 20 June 2020 on the Public Contracts Code;
14. Order No. 0204/A/MINMAP/of 3 July 2020 establishing internal Contracts commissions for Urban Communities, Municipalities and District Municipalities;
15. Circular No. 001/CAB/PR of 19 June 2012 on the award and control of the execution of Public Contracts
16. Letter N 00908/MINTP/DR dated 1997 from the Ministry of Public Works publishing guidelines for taking into account environmental impacts in road maintenance;
17. Circular No. 0001677/C/MINFI of 31 December 2025 on Instructions on the Execution of Finance Laws, the monitoring and  control of the execution of the Budget of the State, Public Enterprises and Institutions, Decentralized Territorial Communities and Other Subsidized Organizations, for the 2026 Fiscal Year;
18. Unified Technical Documents (DTU) for building works;
19. Applicable standards;
20. The Financing Agreement between FEICOM and the Municipality, signed and registered marking the guarantee of financing of the project to be carried out;
21. Other texts specific to the domain concerned by the contract.


Other instruments specific to the domain concerned with the contract
Article 7: Communication (Articles 6and 10 supplemented)

7.1.  All communications within the framework of this contract shall be written and notifications sent to the following address: 

a) In the case where the contractor is the addressee: Sir/Madam..........
Beyond the time-limit of 15 days fixed in article 6(1) of the GAC to make his domicile known to the Project Owner and Contract Manager, correspondences shall be validly addressed to the [to the specified] council, chief town of the province in which the work was done;
b) In the case where the Project Owner is the addressee:
Sir/Madam_______ [to be specified] with a copy addressed to the Contracting Authority, Contract Manager, Contract Engineer, Project Manager and where need be, within the same deadline.
c) In the case where the Contracting Authority is:
Sir/Madam [to be specified] with a copy addressed within the same deadline to the Project Owner, Contract Manager, Contract Engineer and Project Manager, where applicable

7.2. The contractor shall address all written notifications or correspondences to the Project Manager with a copy to the Contract Manager.

Article 8: Administrative Orders (Article 8 of GAC)

The various Administrative Orders shall be established and notified as follows:  

8.1 The Administrative Order to start execution of works shall be signed by the Contracting Authority and notified to the contractor by the Project Owner with a copy to the Contracting Authority, the Contract Manager, Contract Engineer, the Paying Body and the Project Manager, where applicable.

8.2 Upon proposal by the Project Owner, Administrative Orders with an incidence on the objective, the amount and execution deadline shall be signed by Contracting Authority and notified by the Project Owner to the Contractor with a copy to the Contracting Authority, the Contract Manager, the Contract Engineer, the Project Manager and the Paying Body. The prior endorsement of the Paying Body shall possibly be required before the signature of those that have an incidence on the amount. 

8.3 Administrative Orders of a technical nature linked to the normal progress of the work and without financial incidence shall be signed directly by Contract Manager and notified to the contractor by the Contract Engineer or Project Manager (where applicable) with a copy to the Contracting Authority and Contract Manager.

8.4 Administrative Orders serving as warnings shall be signed by the Project Owner and notified to the contractor by the Contract Manager with a copy to the Contracting Authority, the Contract Engineer and Project Manager.

8.5 Administrative Orders for suspension or resumption of work as a result of the weather or any other case of Major Impediment shall be signed by the Contracting Authority and notified by his services to the contractor with a copy to the Project Owner, Contract Manager, Contract Engineer and Project Manager. 

8.6 Administrative Orders prescribing works necessary to remedy defects which could appear on structures during the guarantee period and not related to normal usage shall be signed by the Project Owner upon the proposal of the Contract Engineer and notified to the contractor by the Contract Engineer, with copies to the Contracting Authority. 

8.7 The contractor has a time-limit of fifteen (15) days to issue reservations on any Administrative Order received. Having reservations shall not free the enterprise of executing the Administrative Orders received.

8.8 Concerning Administrative Order signed by the Contracting Authority and notified by the Project Owner, the notification must be done within a maximum of 30 days from the date of transmission by the Contracting Authority to the Project Manager. Beyond this deadline, the Contracting Authority shall establish the default of the Project Owner, take over from him and carry out the said notification.

Article 9: Contracts with conditional phases (Article 9 of GAC)

9.1 The contracthas  several phases
At the end of a phase, the Project Owner shall carry out the acceptance of the works and issue an attestation of proper execution to the contractor. This attestation shall condition the start of the following conditional phase.

9.2   The time-limit granted for notification of the Administrative Order to start execution of a conditional phase shall be [to be specified].

Article 10: Contractor’s equipment and personnel (Article 15 of GAC supplemented)

10.1 Any modification, even partial, made to the technical bid shall only occur after the written approval of the Contract Manager. In case of modification, the contractor shall have himself replaced by a member of staff of equal competence (qualifications and experiences).

10.2 In any case, the lists of supervisory staff to be used shall be subject to the approval of the Project Owner in the days following notification of the Administrative Order to start execution. The Project Manager has Seven (7) days to notify his opinion in writing with a copy sent to the Contract Manager. Beyond this time-limit, the staff list shall be considered as approved.

10.3 Any unilateral modification on the supervisory staff made in the technical bid prior to and during the works shall be a reason for termination of the contract as mentioned in article 45 below or the application of penalties [to be specified where need be].




Chapter II: Financial conditions

Article 11 Guarantees and bonds (Articles 29 and 41 of GAC)

11.1 Final bond
The final bond shall be set at 2 % of the amount of the contract, inclusive of all taxes.

It is constituted and transmitted to the Contract Manager within a maximum deadline of twenty four (24) days of the notification of the contract.

The bond shall be returned or the guarantee released within one month following the date of provisional acceptance of the works, following a release issued by the Contracting Authority upon request by the contractor.
	
11.2  Performance bond

The retention fund shall be set at 10 % of the amount of the contract, inclusive of all taxes.

The return or release of the retention fund or security shall be done within one month after final acceptance by release issued by the Project Owner upon request by the contractor.

11.3 Guarantee of start-off advance

11.3.1 Request for the start-off advance
At the express request of the contractor, a start-off advance not exceeding 20% of the contract ATI may be granted. This advance shall be 100% guaranteed by a first-rank banking institution based in Cameroon and approved by the Ministry in charge of Finance. The bond shall be drafted according to the model enclosed in Appendix.  
11.3.2 Refund of the start-off advance 
The start-off advance shall be refunded by deducting 30% of the amount of each payment on account right from the first account of the contract. It must be entirely refunded by the time the amount of work reaches 80% of the value of the contract. Whatever the case, refund must be over one month to the end of the duration of the contract. 
11.3.3 Release of bond
As the start-off advance is refunded, the delegated Contracting Authority shall release the corresponding bid bond if the contractor requests it. 
Article 12: Amount of the contract (Articles 18 and 19 of GAC supplemented) 

The amount of this contract as indicated by the attached [detail or estimates] is_______(in figures)_______(in letters) CFA francs Inclusive of All Taxes; that is: 

· Amount exclusive of VAT: _________(_______) CFA F
· Amount of VAT: __________(______) CFA F.
· Amount of TSR and/or _____________CFA F
· Net to be paid= EVAT-TSR and/or AIR

Article 13: Place and method of payment

The Project Owner shall release the sums due in the following manner:

a. For payments in CFA francs (amount in figures and letters exclusive of taxes) by credit to account No._________ opened in the name of the contractor in the ___________bank.

b. For payments in foreign currencies (amount in figures and letters exclusive of taxes) by credit to account No._________ opened in the name of the contractor in ________bank.

Article 14: Price variation (Article 20 of GAC)
			
14.1 Prices shall be firm and non revisable.

a. Payments on account made to the contractor as advances shall not be revisable.
b. Revision shall be “frozen” upon expiry of the contractual time-limit, except in the case of price reductions.

14.2 Price updating modalities (where applicable)


Article 15: Price revision formulae (article 21 of GAC)

The prices of this contract shall be firm and non-reviewable

[Comply with Circular No. 003/CAB/PM of 31 January 2011]

Article 16: Price updating formulae (article 21 of the GAC)

The prices of this contract shall be firm and non-reviewable 

Article 17: Works under State supervision (Article 22 of GAC supplemented)

17.1 The percentage of works under State supervision shall be 2 % of the amount of the contract and its additional clauses, where applicable.

17.2  In the case where the contractor was invited to execute works under State supervision, the submitted and duly justified expenditures shall be reimbursed to him under the following conditions:

· The quantities considered shall be the hours used or the quantities of building materials and materials used that was the subject of joint job cost sheets;

· The remunerations and salaries effectively paid to local labour shall be increased by forty percent (40 %) to take account of social benefits;

· The hours put in by the heavy equipment shall be counted at the rate featuring in the sub-detail of prices;

· Building materials and materials shall be reimbursed at cost price duly justified at the place of use, marked up by 10% for loss, stocking and handling;

· The amount for services thus calculated, including the hours put by heavy equipment shall be marked up by 25 % to take into account the overheads, profits and the contractor’s unforeseen.

Article 18: Evaluation of works (article 23 of the GAC)

This contract is at unit price and lump sum




Article 19: Evaluation of supplies (article 24 of the GAC supplemented)
19.1 NOT APPLICABLE 

19.2 No security shall be requested for payments on account on supplies.

Article 20: Advances (article 28 of the GAC)

20.1 The Contracting Authority shall grant a start-off advance of 20 % of the amount of the contract. 

20.2 This advance whose value cannot exceed twenty four (24) percent of the initial amount inclusive of all taxes shall be guaranteed at one hundred (100) percent by a banking establishment governed by Cameroon law or a first-rate financial institution in accordance with the instruments in force and reimbursed by deduction of the payments on accounts to be paid to the contractor during the execution of the contract according to the modalities laid down in the Special Administrative Conditions. 

20.3 The total amount of the advance must be reimbursed not later than when the value in basic price of the works reaches eighty (80) percent of the amount of the contract.

20.4  As the reimbursement advances, the Project Owner shall issue the release of the corresponding part of the guarantee upon the express request by the contractor. 

20.5  The possibility of granting start-off advance or advance for supplies must be expressly stipulated in the Tender File. 

Article 21: Payment for works (articles 26, 27 and 30 of the GAC supplemented)

21.1 Establishment of works executed
Before the 30th of each month, the contractor and the Project Manager shall jointly establish a job cost sheet which summarises and fixes the quantities executed and established for each item on the schedule during the month and capable of giving entitlement to payment.

21.2 Monthly detailed account
No later than the fifth (5th) of the month following the month of the services, the contractor shall hand over to the Project Manager two draft provisional monthly detailed accounts in seven copies (one detailed account exclusive of VAT and the other inclusive of taxes), according to the agreed model and establishing the total amount of the sums to which he may lay claim as a result of the execution of the contract since the start of the contract.

Only the detailed account exclusive of VAT shall be paid to the contractor. The detailed account of the amount of the taxes shall be the subject of an entry into the budgets of the Ministry in charge of Finance

Only the amount exclusive of VAT shall be paid to the contractor as follows:

· [100-2.2 %)] paid directly into the account of the contractor;
· 2.2 % paid to the public treasury as AIR due by the contractor.

The Project Manager has a time-limit of seven (7) days to forward to the Contract Manager the detailed accounts he has approved.

The Contract Engineer has a maximum time-limit of twenty-one (21) days to forward the detailed accounts he approved such that they are in his possession not later than the twelfth of the month.  
The Contract Manager has a deadline of fourteen (14) days maximum to sign the detailed accounts.

The contractor shall be paid on accounts drawn up by applying the prices of the unit price list to works actually carried out. 
· Record of works carried out:
At the end of every month, the contractor and the Project Manager shall draw a joint statement
 summarizing and setting the quantities achieved and recorded for each heading of the Price list during the month and which may give right to payment.
· Monthlyaccount
Not later than thefifth (5̉th) of the month following the month when the work was carried out, the contractor shall furnish to the Project Manager seven (07) copies of the provisional monthly accounts.
· End of work account
After completion of works and within fifteen (15) days following the date of acceptance, the contractor shall, from the joint records, draw the draft final account of works actually carried out which shall sum up the amounts that he can claim as payment for the works executed. 
The draft final account shall be submitted by the contractor for verification and approval by the Project Manager.
Once approved by the Project Manager, the draft final account shall become the final account. It shall serve for making out the final payment to settle the contract drawn up under the same conditions as those defined below relating to drawing of monthly accounts.
· General and final account
At the end of the period of guarantee relating to the structures which gives rise to final acceptance of works, the Project Manager shall draw up the general and final account which shall be countersigned by the contractor and the Contracting Authority. This account whose model shall be provided by the Contracting Authority at his convenience shall comprise: 
-    the final account;
· the final payment;
· the summary of monthly accounts. 
Signing of the general and final account without reserve by the contractor shall definitely bind the parties and put an end to the contract, except for issues concerning default interests.
· [bookmark: _Hlk65588917]Payment of works :
Payment shall be done by the General Manager of FEICOM after receiving accounts drawn up by the Contract Engineer and signed by the Mayor bearing the visa of the Service of Follow up of Projects and investments of FEICOM upon presentation of an account drawn up by the contracting partners in two (02) copies including the stamped original copy. 

Each request for payment shall include the following documents: 

A. Common documents 
1. The Mayor’s payment request addressed to the General Manager of FEICOM,
2. The Funding agreement between the General Manager of FEICOM and the Municipality within the framework of the project for which payment is requested;
3. FEICOM’s Notice of Approval to the Company’s contract;
4.  The original contract (s), the jobbing order or the purchase recorded for the start off advance or the first bill and the photocopy of the contract for the following ones,
5.  The original copy of the registered receipt for the start off advance or the first bill and photocopies for the others;
6. The Tax Notice,
7.  The report of work executed, for partial provisional acceptance, general provisional acceptance or final acceptance of works signed by at least two-thirds (2/3) of the members of they commission including the President,
8.  The bill (start off advance or partial or final or holdback) stamped and signed by all the stakeholders (the contractor, the project manager, the contract Engineer and Manager, and liquidated on the back by the Project Owner),
9. The validated attestation of non-indebtedness,
10. [bookmark: _Hlk65055992]The valid original copy of the attestation of Bank Account (not more than three months),
11. The original copy of the certificate of non-exclusion from Public Contracts (only fur purchase);
12. A photocopy of the company’s civil liability insurance including the photocopy of all site risk insurance (only for works of contractors) - Except holdback,
13.   A photocopy of the final bond - Except holdback,
14.  The delivery note signed by the contractor and the vote holder, or delivery note or the attestation of service signed by the Manger or the vote holder, or the attachments signed by the appointed members in accordance with the contractual provisions,
15.  A photocopy of the warranty certificate of at least six months for the equipment requiring maintenance,
B. Documents specific to request for the start-off advance payment;
1 The original copy of the start-off advance deposit or Guarantee of start-off advance
2 Notice of approval of the plan of works Execution,
3 The plan of Works Execution.
C. Documents specific to request for payment of bill No 1;
1 The Service order to start works,
2 The project Managers Activity report.
D. Documents specific to request for partial payments;
1 The detailed works Execution or services rendered stamped and signed by the contractor, the Project Manager or the contract Engineer;
2 The Minutes of works executed.
E. Documents specific to request for final bill payment requests;
1 The final detailed works Execution or services rendered stamped and signed by the contractor, the Project Manager or the contract Engineer;
2 The As-Built plans of the infrastructures (for works contractors) and the final inspection report (the Project Managers),
3 The original copy of the general provisional acceptance or technical acceptance of works report.
F. Documents specific to the payment requests of holdback;
1 The original copy of the final acceptance of works report.
2 The original copy of the certificate of release of retention signed by the Project Owner,
· Default interests
Default interests shall be paid by statement of the amounts owed.
· Currency
The currency of the tender and payment shall be the CFA Franc.

21.3  Detailed account of start-off account (if applicable).
Documents specific to request for the start-off advance payment;
a. The original copy of the start-off advance deposit,
b. Notice of approval of the plan of works Execution,
c. The plan of Works Execution.
Article 22: Interest on overdue payments (Article 31 of the GAC)

Possible interests on overdue payments are paid by statement of sums due in accordance with article 88 of Decree No. 2004/275 of 24 September 2004 to institute the Public Contracts Code.

Article 23: Penalties (Article 32 of the GAC supplemented)
A. Penalties for delay
23.1 The amount set for penalties for delays shall be set as follows:
d. One two thousandth (1/2000th)  of the initial contractamount all taxes inclusive per calendarday of delayfrom the first to the 30thdaybeyond the contractual time-limit;
e. One thousandth (1/1000th) of the initial amount of the contract inclusive of all taxes per calendardaybeyond the 30th day.
23.2 The cumulatedamounts of penalties for delayshallbelimited to ten percent (10 %) of the initial contract inclusive of all taxes.
B. Specific penalties [amount to beindicated]
23.3 Independently of penalties for overrun of contractual time-limit, the contractorshallbe liable for the followingspecial penalties for the non observation of the provisions of the contract, especially:
· Late submission of final bond;
· Late submission of insurances;
· Late submission of the draft execution schedule if the the lateness is caused by the contractor.
Article 24: Payment in case of a group of enterprises (article 33 of the GAC)
1. In the case of a group of enterprises, indicate the method of payment of co- and sub-contractors, where need be.
2. Indicate the method of payment of sub-contractors, where need be.

Article 25: Final detailed account (article 34 of the GAC)

25.1 After completion of the works and within a maximum time-limit of 30 days after the date of provisional acceptance, the contractor shall establish, based on joint reports, the draft final detailed account of works executed and which detailed account summarises the total sums to which the contractor may be entitled as a result of the execution of the whole contract. The draft shall be forwarded to the Project Manager, after the date of provisional acceptance for examination.

25.2 The Project Manager has a deadline of two weeks to notify the corrected and approved draft to the Project Manager.

25.3 The contractor has a maximum of one month to return the signed final detailed account. 



Article 26: General and final detailed account (article 35 of the GAC)

26.1 At the end of the guarantee period which results in the final acceptance of the works, the Contract Manager draws up the general and final detailed accounts of the contract after a period of one month which he has had signed jointly by the contractor and the Contracting Authority. This detailed account includes:
· the final detailed account, 
· the balance
· the summary of monthly payments on account.

The signing of the general and final detailed account without reservation by the contractor definitely binds the two parties, puts an end to the contract, except with regard to interest on overdue payments.

26.2  The contractor has a maximum of one month to return the the signed final detailed account 

Article 27: Tax and customs regulations (article 36 of the GAC)

Decree No. 2003/651/PM of 16 April 2003 lays down the terms and conditions for implementing the tax regulations and customs procedures applicable to public contracts. The taxes applicable to this contract include notably :

· Taxes and dues relating to industrial and commercial profits, including the IAR which is a deduction on company taxes;

· Registration dues in accordance with the Tax Code;

· Dues and taxes attached to the execution of services provided for in the contract;
i) Duties and taxes of entry into Cameroonian territory (customs duties, VAT, computer tax);
ii) Council dues and taxes ;
iii) Dues and taxes relating to the extraction of building materials and water.

These elements must be included in the costs which the undertaking imputes on its running costs and constitute one of the elements of the sub-details of prices exclusive of taxes.

All taxes inclusive prices mean VAT included.

Article 28: Stamp duty and registration of contracts (article 37 of GAC) 

Seven (7) original copies of the contract shall be stamped by and at the cost of the contractor, in accordance with the applicable regulations.


Chapter III: Execution of works

Article 29: Nature of the works (article 46 of GAC)
[bookmark: _Hlk231374659][bookmark: _Hlk238126498][bookmark: _Hlk238044847]The project shall consist in the construction of a bridge measuring 20m long and 8 meters high over the Mbee river in Bafut Council, Mezam Division of the North West Region.
.
Article 30: Role and responsibilities of the Project Owner (GAC supplemented)

30.1 The Project Owner shall be bound to furnish the contractor with information necessary for the execution of his mission and to guarantee, at the cost of the contractor, access to sites of projects.

30.2 The Project Owner shall ensure the contractor of protection against threats, insults, violence, assault and battery, slander or defamation of which he could be victim by reason of or during the exercise of his mission.

Article 31: Execution time-limit of the contract (article 38 of the GAC)

31.1 The time-limit for the execution of the works forming the subject of this contract shall be: eight (08) months.

31.2   This time-limit shall run from the date of notification of the Administrative Order to commence execution of the works [or that fixed in this Administrative Order- to be specified].

Article 32: Role and responsibilities of the contractor (article 40 of the CAG)

The detailed and general plan of progress of the works shall be communicated to the Project Manager in four (04) copies at the beginning of each week.

Article 33: Provision of documents and site (article 42 of the GAC)

A reproducible copy of the plans featuring in the Tender File shall be submitted by the Project Manager.

The Project Owner shall make available the site and access ways to the contractor at the appropriate time as the works progress.

Article 34: Insurance of structures and Civil or Rural liabilities (article 45 of GAC)

The following insurance policies are required within the scope of this contract in the minimum amounts indicated hereafter within fifteen (15) days of the notification of the contract (to be adapted): 
· Liability insurance, business manager;
· Comprehensive insurance of the site;
· Insurance covering its ten-year obligation, where applicable.
Article 35: Documents to be furnished by the contractor (Article 49 of the GAC supplemented)
35.1 Programme of works, Quality Assurance Plan and others (to be specified).
a) Within a minimum deadline of thirty (30) days from the date of notification of the Administrative Order to commence execution, the contractor shall submit insix (6) copies for the approval of Contract Manager after the endorsement of the Project Manager and the Contract Engineer the execution programme of the works, his supply calendar, his draft Quality Assurance Plan and the Environment Management Plan, where applicable.

This programme shall be exclusively presented according to the furnished models.

Two (2) copies of these documents will be returned to him within a deadline of fifteen (15) days from the date of reception with:
· Either the indication “GOOD FOR EXECUTION”;
· Or the indication of their rejection including the reasons for the said rejection.

The contractor has eight (8) days to present a new draft. The Contract Manager or the Project Manager and Contract Engineer then has a deadline of five (5) days to give his approval or possibly make comments.   Delay in approving the draft execution schedule shall stay the execution deadline.

The approval given by the Contract Manager or Project Manager does not in any way release the contractor of his responsibilities. Meanwhile, works executed before the approval of the programme shall neither be ascertained nor paid for. The updated and approved schedule will become the contractual schedule.

The contractor shall constantly update on site, a schedule that will take account of real progress of the site. Significant modifications may only be made on the contractual programme upon receiving the approval of the Project Manager. After approval of the execution schedule by the Contract Manager, the latter shall transmit it within five (5) days to the Contracting Authority without staying its execution. However, if important modifications alter the objective of the contract or the nature of the works, the Contracting Authority shall return the execution schedule accompanied by reservations to be lifted within fifteen (15) days of the date of reception.  

Prior to the start of the work, the execution of works programme shall have received the notice of Approval of the contract Engineer solicited by the company, care of the Contracting Authority. The Notice of Approval or rejection of execution programme, shall be carried out within time limits not exceeding twenty four (24) calendar days with effect from the date of submission to the Contract Engineer of the Execution programme approved by the Contract Engineer.

b) The Environment Management Plan should bring out notably the choice technical conditions of the site and basic life, conditions of the backfill of the extraction sites and conditions for reinstating the works and installation sites.

c) The contractor shall indicate in this schedule the equipment and methods which he intends to use as well as the personnel he intends to employ.

d) The approval granted by the Contract Manager or Project Manager shall in no way diminish the responsibility of the contractor with regard to the harmful consequences which their implementation may cause both towards third parties and the respect of clauses of the contract.

35.2 Execution draft

a)  The execution plan documents (calculations and drawings) necessary for the realisation of all the parts of the structure must be submitted for the endorsement of the [Contract Manager or Project Manager] at most 30 days prior to the date provided for the commencement of execution of the corresponding part of the structure.

b) The [Contract Manager or Project Manager] has a deadline of [fifteen (15) days] to examine and make known his observations. The contractor then has a deadline of [eight days] to present a new file including the said observations.

35.3   In case of the non observance of the approval deadlines of the above documents by the Administration, these documents shall be deemed to have been approved. 

Article 36: Organisation and safety of sites (article 50 of the GAC)

36.1 Signboards at the beginning and end of each section must be placed within a maximum deadline of one month after the notification of the Administrative Order to commence work.

36.2 The services to inform in case of interruption of traffic or along the deviated itinerary: [To be specified in accordance with article 50(2) of the GAC].

36.3 Indicate the special measures demanded of the contractor, other than those provided for in the GAC, for rules of hygiene and safety and for circulation around or in the site.

Article 37: Implantation of structures

The Project Manager shall notify within 15 days following the date of notification of the Administrative Order to commence work, the basic points and levels of the project.

Article 38: Sub-contracting (article 54 of the GAC)

The part of the works to be sub-contracted shall be 30 % of the initial amount of the contract and its additional clauses.

Article 39: Site laboratory and trials (article 55 of GAC)

39.1 Indicate if necessary, the modalities for carrying out the trials and geotechnical studies provided for in the Special Technical Conditions.

39.2 The Contract Manager has a deadline of 07 days to approve the contractor’s personnel and laboratory as soon as the request is made.

Article 40: Site logbook (article 56 of the GAC supplemented)

40.1 The Site logbook must be systematically jointly signed by the Project Manager or Engineer, where need be and the contractor’s representative each day.

40.2  It is a joint document in a single copy. Its pages must be numbered and initialled. No page should be removed. The erased or cancelled parts must be mentioned on the margin for validation.

Article 41: Use of explosives (article 60 of the GAC) 

The use of explosives shall only be accepted with authorisation from the Ministry concerned.

Chapter IV: Acceptance

Article 42: Provisional acceptance (article 67 of the GAC)

Prior to the provisional acceptance, the contractor shall request in writing from the Project Manager, the organization of a technical visit required before acceptance.
This visit shall include, among others, the following operations:
· Controlling the quality and quantity of the structures constructed;
· Carrying out trials provided for by the Special technical conditions;
· Recording the possible non-execution of works provided for under the contract;
· Recording the folding up of the installations and cleaning of the project site; 
· Recording the completion of works; 
· Recording the quantities of works actually executed.
These operations shall give rise to a report drawn up on the spot, signed by the Project Manager and countersigned by the contractor.
Following this pre-acceptance visit, the Project Manager may indicate the reserves to be lifted and the corresponding works to be carried out before the date of provisional acceptance which he shall fix in agreement with the contractor..
42.1 Tests included in the operations prior to acceptance shall include the geotechnical studies of the soil for the foundation of the building 

42.2 Possible ascertainment of the folding up of the site installations and the restitution of the site as was [insert and modify if applicable];

42.3 The Acceptance Commission shall comprise the following members indicatively:
· The Project Owner or his representative.                                                Chairman	
· The General Manager of FEICOM or his representative                            Member;                        
· The C/SSCI  of FEICOM NORTH-WEST Agency                   member;                                                                         
· The Contract Manager (CDO BAFUT Council)                      Member                                                                                             
· The DD MINMAP/Mezam or representative                         OBSERVER
· The Contract Engineer DD MINTP                                         Rapporteur
· The Council Project Manager (SG Bafut Council)	             	Member	
· The Contractor or his representative				member

The contractor shall be convened to the acceptance by mail at least 10 days prior to the acceptance. He is bound to attend (or be represented).

He takes part in the acceptance as an observer. His absence is equivalent to acceptance without reservation of the conclusion of the Acceptance Commission.

After the visit of the site, the Commission shall examine the minutes of the preliminary operations to the acceptance and shall proceed to provisional acceptance of the works if there is need.

The visit for provisional acceptance shall be the subject of minutes of provisional acceptance signed on the spot by all the members of the Commission.

The minutes of the provisional acceptance report shall specify or set the date of completion of the works.

42.4 There is no provision for partial acceptance.

42.5 The guarantee period commences from the date of provisional acceptance of the said project.

Article 43: Documents to be furnished after execution (article 68 of the GAC)

43.1 At the completion of the works and within 30 days after the provisional reception, the contractor shall provide all working documents including proof of origin of material used and the network plan with all associated geographical coordinates.

43.2 A penalty of 30% of the guarantee retention shall be retained in the event where the contractor fails to comply with 43.1 above.

Article 44: Guarantee period (article 70 of the GAC)

The guarantee period shall be one (1) year to run from the date of the provisional acceptance of the works.

Article 45: Final acceptance (article 72 of the GAC)

45.1 Final acceptance shall take place within a maximum deadline of fifteen (15) days from the date of expiry of the guarantee.

45.2 The Project Manager shall be member of the commission.

45.3 The procedure for final acceptance shall be the same as for provisional acceptance.

Chapter V: Sundry provisions

Article 46: Termination of the contract (article 182 of the GAC)
The contract may be terminated as provided for in Decree No. 2018/366 of 20/06/2018, instituting the Public Contracts Code.
· Delay of more than fifteen (15) calendar days in the execution of an Administrative Order or unjustified stoppage of more than seven (7) calendar days;
· Delay in work resulting in penalties of more than 10 % of the amount of the works;
· Refusal to repeat poorly executed works;
· Default by the contractor;
· Persistent non payment for services.

Article 47: Case of Major Impediment (article 75 of the GAC)
If the contractor were to raise the issue of force majeure, the thresholds below which claims shall not be admitted are:

· Rainfall: 200 millimetres in 24 hours;
· Wind: 40 metres per second;
· War in the area of execution of the job;
· Flood: decennial flood frequency.

Article 48: Disagreements and disputes (article 79 of the GAC)
Disagreements and disputes resulting from the execution of this contract may be settled amicably.
Where no amicable solution can be found for a disagreement, it is brought before the competent Cameroonian jurisdiction, subject to the following provisions: [to be filled, where need be].

Article 49: Production and dissemination of this contract

[Seven (07)] copies of this contract shall be produced at the cost of the contractor and furnished to the Contract Manager.

Article 50 and last: Entry into force of the contract

This contract shall be final only upon its signature by the Contracting Authority. It shall enter into force as soon as it is notified to the contractor by the Contracting Authority.
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 TECHNICAL SPECIFICATIONS

1. GENERALITIES
2.  PREPARATORY WORKS
3. ORIGIN, QUALITY, AND PREPARATION OF MATERIALS
4.  MODE OF EXECUTION OF THE VARIOUS TASKS
	· 001
	Site Installation

	· 002
	Mobilisation and demobilisation of equipment

	· 002
	Geotechnical 

	 
	Series 100- Site Preparation

	· 101
	Site Clearance

	· 102
	Felling of trees

	· 103
	Traffic flow (Diversion of watercourse/road)

	· 105
	Setting out of the bridge

	 
	Series 200 –General Earth Works

	· 201
	Excavation of trenches

	· 202
	Backfill of excavation

	· 203
	Opening complete of the right of way 10m wide of the access road on both sides of the bridge and molding of the road to 7m wide

	 
	Series 300-Foundations- Abutment-deck-wing walls

	· 301
	Hardcore

	· 302
	Stonemasonry works for a foundation, abutment, and wing walls

	· 303
	Mass concrete dosed at 400kg/m3 as for base of the footings

	· 304
	Lean concrete floor dosed at 150kg/m3

	· 305
	Reinforced concrete dosed at 400kg/m3 for the footings and other parts of the bridge

	· 306
	Reinforced concrete 20cm thick  dosed at 350kg/m3 for a raft 

	· 307
	IPE 300 for rib beams

	· 308
	IPE 500 for beams including all subjections

	· 309
	Archor of rods HA25 to a rock

	· 310
	Drainage material behind the abutment

	 
	Series 400-Equipment

	· 401
	Mixt guard rails (RC+iron tubes 60)

	· 402
	Weep holes

	· 403
	Drainage pipes

	· 404
	Signposts






1 – GENERALITIES: This present special technical specification concerns the construction of a bridge measuring 20m long and 8 meters high over the Mbee river in Bafut Council, Mezam Division of the North West Region. The contractor must realize the structure as per the execution plans that shall be approved by the competent authority and sample models of equi and furniture provided by the project owner. Through the Project Engineer, the contractor shall furnish the owner of the project and other project team members within the shortest possible time with an execution plan showing clearly how he intends to run the work worksite. A fence in local materials shall enclose the whole work site to avoid trespassing.

SIGN-POSTS: The contractor shall put in place at his expense sign-posts indicating work in conformity with the plans put at his disposal by the authority that signed the contract.

Hygiene and safety:  The contractor shall ensure total hygiene and security of the site by constructing a temporal pit latrine and putting up a temporal fence around the project site if that be the case.

The contractor shall be responsible for the protection of the structures before final reception. He shall be equally responsible for all tools and materials present at the worksite. He shall seek an insurance policy to cover theft and fire incidence.

The contractor shall take all preventive measures against accidents. The owner of the project reserves the right to intervene in case of any emergency without necessarily interfering with the responsibilities of the contractor.

The contractor shall verify all dimensions of the plans. For execution, no dimension shall be measured with a scale rule from the plans. The contractor shall check in-situ the possibility of translating the dimensions on plans to the structure before work begins. He shall refer to the Project Engineer in case of any doubt. He shall not on his own modify anything on the structure and shall inform the Project Engineer of any changes that he considers necessary.

All modifications accepted by the contractor shall be accomplished in a specified duration and at his cost without modification of the contract amount. The owner of the project shall have the right to the final choice in case of any modification.

2 - PREPARATORY WORKS – SETTING OUT: These works concern the clearing of the site and evacuation of the rubbles to the public discharge, the clearing, and leveling of the site where necessary. The setting out will be in respect to the technical plans. 
The setting out profile boards will be at least 1, 20 m from the outside axes, to facilitate trenching and other earthworks and good circulation. The commencement of excavation will be accepted by the Project Engineer without checking the conformity of the setting. 
The minimal depth of the excavation trenches shall be of as will be specified by the geotechnical studies to be carried out by the contractor before the commencement of works to precise the soil bearing capacity. 

Where there is black cotton soil or soil with low bearing capacity at the bottom of the trench, the contractor shall continue excavation up to a depth as will be approved by the Project Engineer. The excavations will be done manually or mechanically and no concrete or mortar shall be laid on the bottom of the trench without the acceptance of the trench bottom of excavation by the Project Engineer.

The descriptive notice completes or confirms the indications on the execution plans. In the case of contradictions between the plans and the descriptive notice, the project team shall be contacted for examination, elaboration, and conclusion.
These technical specifications have as objective the definition of the consistence of works to be executed by the plans and according to technical norms for the construction of classroom buildings.
ORIGIN, QUALITY, AND PREPARATION OF MATERIALS: The fine and coarse aggregates may either be from the river or quarry crushed and must be approved by the Project Engineer before any use on the site. The sand (0/5) shall have very fine elements settlement of less than 4%. The gravels (5/15 and 15/25) shall be clean and well graded with very fine elements settlement of less than 2%. The cement shall be CPA 325 class from CEMENCAM or an approved factory.

The reinforcement steel for reinforced concrete shall be of type HA FeE400 for the main reinforcement steel rods and round-smooth RL E235 for the stirrup rings. Any fill material for the foundation and the surrounding structures shall have no particle dimension above 50mm and with a plasticity index of less than 35. Fill materials shall also be free from organic elements and shall have a good granularity grading. No black vegetable soil shall be accepted for backfilling.

Stones for masonry works shall be of basalt, gneiss or granite type, be esthetical and should be gotten from the quarry or deposits approved by the Project Engineer with dimension sizes of not less than 20cm.

1. CONCRETE:
-Ordinary concrete: specifically lean concrete shall be 5cm thick and laid all around the excavated foundation trenches before the stone/blockwork is carried out and dosed at 150kg/m3.
- Concrete for the Raft: shall be 15cm thick laid on the entire floor of the bridge between the 02 abutments and dosed at 350kg/m3 over the entire surface.
NB: The inlet to the bridge shall be excavated at a depth of 60cm below the natural soil and concreted along the width of the bridge between the wings at 01m to the 02 abutments so as to resist the scouring by water upfront. The raft will receive a longitudinal slope of 2%, slopping towards the outlet of the bridge (flow of water). 
-Reinforced concrete: shall be specifically for the footings, beams seating’s and the slab of the bridge, curbs, and pillars of the mixt guard rails, and their mixture shall be in a proportion of 350kg/m3.
NB: All concrete works should be properly cured (i.e. water three times a day for seven days)

NOTE: Reinforcement Schedule.
	NO
	STRUCTURE
	SIZES
	Transversal RODS
	Longitudinal RODS
	STIRRUP
	CONCRETE DOSAGE

	TYPE

	
	
	Nos
	
	Tors
	Spacings
	
	

	1
	Footing
	
	10mm
	8mm
	20cm
	350kg/m3
	Fe-E-400

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	3
	Beam seating
	
	12mm
	10mm
	20cm
	400kg/m3
	Fe-E-400

	4
	Bridge slab
	4
	12mm
	10mm
	15cm
	400kg/m3
	Fe-E-400

	5
	Bridge raft
	4
	8mm
	8mm
	20cm
	350kg/m3
	Fe-E-400

	
	Kerb
	
	8mm
	8mm
	20cm
	350kg/m3
	Fe-E-400

	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	

	
	Pillars guard rails
	
	8mm
	8mm
	20cm
	350kg/m3
	Fe-E-400



NB: All rods should preferably be imported 

Aggregate
0. Sand: Will be free from oxide, organic material of animals or plant origin. Sieving shall vary from 0.16 – 5mm. It shall be a mix of river and crushed sand mixed to the proportion as designed. 

1. Gravel: shall consist of natural and homogeneous materials or crushed stones. A tiny layer of the grave (dust) shall be removed by sieving, blowing, or washing. It shall a mix of 5/15 and 15/25
Water: 
1. To be used for the mixture of mortar, concrete, and washing of aggregates. Shall be clean and free from impurities; meaning potable water.

Cement: 
To be used mostly for cement mortar, all concrete mixtures shall satisfy the general conditions laid down by regulation in force. It will be typed CPJ 325 Portland cement and shall not show any trace of the uneven mixture. Storage on the building site shall be done on a dry and ventilated floor. Any stock presenting an unsatisfactory pulverulent condition will be discarded and cleared away within four (04) days.
Rods: 
shall be mild steel reinforcement, Tor, or Steel by the R/C &3 rules. The steel shall be perfectly clean without any trace of rust, non-adhesive to paint or grease.
Shuttering:
 hardwood, to bear without any noticeable distortion, the load, and pressure of concrete, the effect of vibration, and the weight of workers involved in setting it up.
MASONRY:
Stones- shall be as specified above
Wood – Material: 
The wood must be pure and should not have nodes, foreign bodies, or fractures due to sawing. This shall be locally sawn eucalyptus.

MODE OF EXECUTION OF THE VARIOUS TASKS
	1) TR001.1 - Site installation
Description of works  
These works consist of the mobilization of materials and personnel, the realization of geotechnical and technical studies for the project as well as the performance program and final report, the construction of a hut for site meeting, Etc… 


	2) TR001.2- Project information signpost
Description of works  
This consists of fabricating information boards in wood, the supply to the sites at the extremes of the various roads, and eventually at the post of works (bridge) to furnish the populations with all information concerning the project.
The boards will carry the following information:
	North-West Region
           *******
	Republic of Cameroon
Peace-Work-Fatherland
                                                                           ********

	Project name
	THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION


	Owner of the project
	Mayor  BAFUT COUNCIL

	Funding body
	FEICOM/ BAFUT COUNCIL


	Chief of Techical service 
	BAFUT Council

	Project Engineer
	Div. Del. P. Works- MEZAM

	Duration of the contract
	Eight  (08) months

	Contractor
	



3) TM002 - Mobilization and folding up of equipment


Description of works  
This task consists of the mobilization of equipment to the site through a loader and at the end of the works the folding up of the equipment by same means and the realization of all the works necessary to re-establish the lieu to their initial state.

4) 101 - BUSH CLEARING
Description of works  
These works consist of removing vegetation and cleaning the edges of the road as well as on its immediate surroundings, felling trees and/ or trimming tree branches obstructing visibility, etc.   

Mode of execution of works
This consists of clearing all vegetation at a width of two meters form the outer edge of the gutter and scraping and discarding vegetative soil from the road surface. These are labor-intensive works carried out by groups of workers recruited from the community and equipped with the necessary tools to carry out the job.

5) 103 - Setting out of the structure
Description of works  
This consists of carrying out activities geared at positioning the bridge at the coordinates such that its axis will be l align with that of the access road from both sides. Also, the characteristics of the structure as designed should be respected. 

Mode of execution of works
This consists of using pegs and lines and with the help of a level position the bridge such it should be at a right angle relative to the road with the wing walls at 45 degrees relative to the road or front walls of the bridge. Equally, the position of the areas to be excavated for the abutment including the working space should be materialized. As such the length and span of the bridge as well as the wing walls, the front wall and the abutment as a whole will be positioned. After the excavation, these parameters will be verified first before the bridge works proper starts
So done, the following data will be verified before the excavation

	S/N
	Item to verify
	Expected result
	Person responsible
	Person to approve

	1
	Setting out
	Respect of specifications
	









Works Manager enterprise
	









Project Manager – DDMINTP-Menchum

FEICOM

	2
	Alignment of axis
	aligned
	
	

	3
	Distance in to in between the 2 footings 
	
8.6m
	
	

	4
	Distance in to in between the 2 front walls of the abutments
	
09 m
	
	

	5
	Footings (front wall and wing walls) 
	

	
	

	5.1
	Width
	2.00m
	
	

	5.2
	Thickness
	50cm
	
	

	6
	Length of the wing walls
	
	
	

	6.1
	Upstream
	5,0m
	
	

	6.2
	Downstream
	3.0m
	
	

	7
	Stonemasonry (front wall and wing walls)
	
	
	

	S/N
	Item to verify
	Expected result
	Person responsible
	Person to approve

	7.1
	Big base of stone masonry part of the abutment and wings ( down i.e.in contact with footing)
	
1.8m
	
















Works Manager enterprise
	
















Project Manager – DDMINTP-Menchum

FEICOM

	7.2
	The small base of stone masonry part of the abutment and wings (top i.e. beam seating support)
	

1.1m
	
	

	7.3
	Height  of the stone masonry abutment + wings (same height) No difference in the heights of the front wall and wing walls will be tolerated
	4.00 m
	
	

	8
	Deck of the bridge
	
	
	

	
8.1
	Beam seating in L form (RC) – horizontal part
	
	
	

	8.1.1
	The thickness of the base of the beam seating 
	
40cm
	
	

	8.1.2
	Thickness shock absorbers on-base beam seating
	
05cm
	
	

	8.1.3
	Height of the vertical part of the beam seating
	
5+50+25=80cm
	
	

	8.1.4
	Thickness slab
	25cm
	
	

	8.2
	Beams
	
	
	

	8.2.1
	Height I beam
	50cm
	
	

	8.2.2
	Height rib beam
	
	
	

	9
	Fittings
	
	
	

	9.1
	Kerb base=20cm height=10cm
	20x10cm
	
	

	9.2
	Guard rails
	
	
	

	9.2.1
	RC pillars spaced at 1m
	10cmx10cm
	
	

	9.2.2
	Iron tubes 
	Diam. 60mm
	
	

	10
	Expected height of the bridge from the footing
	4.00+0.4+0.05+0.50+0.25
=5.20m
	
	

	11
	The expected span of the bridge
	10m
	
	

	12
	Expected length of the bridge (span+thickness vertical parts of the beam seatings
	

10+1.0x2=11.00m
	
	

	13
	The expected carriageway of the bridge (width slab-widths of kerbs)
	

06m
	
	

	14
	Width of slab of the bridge
	6.4m
	
	


NB: These works, and this, at every stage must be received by the Contract Engineer before the next phase can continue

6) 203.1 - Excavation in ordinary terrain for the abutments and the deviation of the existing river bed
Description of works  
This consists of digging to free the space set for the construction of the bridge. The various parameters set out will be respected in the excavation. Also, the depth of the foundation as per the results of geotechnical studies should be respected i.e. 1.6m from the bed of the river

Mode of execution of works
This consists of excavating in ordinary terrain for the abutments and the deviation of the existing river bed and also for the creation of a bed off stream to deviate the existing stream to join the main bed Length=50m, width=1m depth=1m.
NB: The excavation must be received by the Project Manager before the next phase can continue

7) 205 – 207 Backfilling of the bridge and filling and resurfacing of the accesses to the bridge

Description of works  

This involves realization of the technical bloc and the linking to the existing carriage way (road) 
These works shall be executed mechanically and manually with material extracted from a borrow pit approved by the project manager. The soil used for the fill shall present the following characteristics:
· CBR at 95% of OPM after four days of immersion		       	               40
· Maximum dry density at 95% OPM  (T/M3)					 1,8
· Plasticity index(IP)								 25
· Percentage of fine grains<0.08mm			F		5F30
· Module of plasticity						F.IP		<500
· Linear inflation						%		<1
· Maximum diameter of grains					mm		40
· % passing through a sieve of 10mm				<10		35 – 90
· % passing through a sieve of 5mm				<5		20 – 60
· Residue at a sieve of 2mm					>2		10 – 40
The selected material from the borrow pit shall be laid on a trench and platform previously shaped and compacted at a dry density of at least 90% OPM. The material shall be laid in horizontal layers of 20cm thick and have water content equal to that of OPM before compaction (±2%).
The fill is compacted methodically up to 95% of the dry density of OPM. The rate of compaction shall be verified in -situ with a membrane densitometer at every 1000m2. A sample compaction test shall be carried out to determine of passes necessary to obtain the required compaction rate.

8) 305 – Stone masonry
Description of works  
This consists of realizing the parts of the bridge with well-shaped and assembled stones according to the esthetic and type of the structure (form, dimension of stones, joints, Etc…) while respecting the works of arts  
The mortar will be dosed at three hundred and fifty (350)kg of cement per m3 of sand.
The visible faces of the stone’s masonry should be regular. The minimum height of the shaped stones should not be less than fifteen (15) cm.
The finishing of the external joints will be realized with done with mortar M450

Mode of execution of works
This consists of
Mode of execution of works
These works shall be done exclusively manually (shaping of stones, humidification, elevation, bonding, pointing)

9) 309a, 309b, 309c, and 309d - Lean concrete dosed at 150Kg/m3, Mass concrete  dosed at 350Kg/m3, Reinforced concrete  dosed at 400Kg/m3, and Reinforced concrete  dosed at 350Kg/m2 for the bridge's raft

Description of works  
These works consist of the supply and put in place of concrete 150Kg/m3 for the lean concrete, at 350Kg/m3 for the mass concrete, and 400Kg/m3 for the reinforced concrete .
The concretes A.400 for the reinforced concrete must have a minimum compression resistance of 270 bars at 28 days.
This task comprised notably the:
· supply including the transport to the site of materials (cement, sand, gravel etc) and tools necessary for the precast of the slabs; 
· form works with planed planks; 
· transport and the putting in place of the stones including all contingencies; 
· Execution of all contingencies related to traffic flow and the respect of environmental prescriptions; and all other contingencies.

Formwork
  This operation consists of forming the various surfaces when necessary, before concreting. The parts of the structure requiring formwork will be approved by the Project Manager. The formwork will be of robust construction because it is called upon to support, as the case may be, the thrust of the fresh concrete or the weight of the construction until the depending on the structure.
The different parts will be assembled in a simple way to allow the formwork to be stripped without stripping the concrete. This simplicity, however, will not allow any negligence in the distribution of joints. The panels already used, will be veiled and the edges peel off.
It will be used for certain categories of formwork, greasy or plastic mold release products. These products must be approved by the Project Manager.
The construction of the formwork will also be specified as prescribed by the CCTP, depending on the category, to preserve, among other things, the homogeneous coating of the reinforcements and the final deformations of the works.
The fixings of the interior formwork to the concrete must be only those indicated on the working drawings approved by the project manager.
To maintain the reinforcements at a fixed distance from the formwork, we can use concrete wedges (or any other material approved by the Project Manager, plastic material for example) in which we will have previously embedded wire ligatures. Under no circumstances should any metal element be at a distance less than the minimum cover provided for the reinforcements.  
504b - Putting in place of metallic I beam 400 including the bracing
Description of works  
Steel beams: IPE - Metallic I beam 500 including the bracing
This work consists of laying IPE beams. Before any work begins, the project manager must define or approve the IPE beam to be installed. The new IPE beams will be directly protected against rust by a coat of anti-corrosive paint.
The steels used are merchant bars, in weldable mild steel, the grade of which is subject to the approval of the Project Manager. They must meet the requirements of Chapter III of Fascicle 4 of the French CCTG. In particular, the mechanical characteristics of these profiles must comply with the NF A 35-501 or NF A 36-201 standards. 

10) 601a and 601b - Anti-rust paint and Oil Paint
Paints
The protective paints to be applied to the metal sections brushed white beforehand are of the glycerophtalic type, and must be submitted to the prior approval of the Project Manager's Representative.

In all cases, an anti-rust undercoat of a different color will be put in place beforehand.

11) 901c - Mix guard rails (concrete pillars and metallic pipes)
Garde-corps - Mix guard rails
This operation includes the replacement or supply and installation of railings on the structure. These works will be defined when the development plans are drawn up. The elements of the railings will be placed and adjusted in alignment and altitude. It will be verified that the uprights will be vertical. The sealings of the uprights will be made of concrete dosed at 400kg/m3 and must comply with the standard plan. The sealing of uprights will only take place after verification by the Project Manager of the perfect alignment of the guardrail. The surfacing of the sealing concrete will be neat so that water cannot stay at the recess of the uprights.
Depending on their condition, and with the approval of the Project Manager, the railings may receive an anti-corrosive protective paint.

902a - Triangular signposts type A ou AB

Triangular sign - Triangular signposts type A or AB
The danger signs will be placed 150m from the point at the start of the zone to be signaled in open country and 50m in the built-up area.
Prescription signs, except for certain mandatory signs which must be installed as danger signs.
The direction signs will be placed 100m from the point at the start of the zone to be reported in the case of open country and 40m in the agglomeration.
Vertical signaling includes retro-flexing galvanized sheet metal panels for signaling, pre-signaling, location, or directional. The location of the various panels is designated by the Delegate Project Manager. The works consist in placing along the driveway on the shoulder, in the places provided by the project manager, traffic, pre-signaling, location, or directional signs.
The panels and their implementation will comply with the technical requirements.

12) 905b - Wooden post markers
[bookmark: _Toc521229388]Beacons - Wooden post markers



The turn beacons are type 2 J1 beacons with a circular section (diameter 150 mm) 80 cm high from the level of the shoulder. The beacons are made of fiber cement, enameled or galvanized sheet metal, plastic, B 300 concrete, or wood.
Among the Cameroonian wood species with these required characteristics, we can mention Doussie, Moabi, Tali, Azobé, Iroko, and Bubinga. (see § 11.13 above)
They are located on the outer shoulder of the bend, the axis one meter from the outer edge of the wearing course. The spacing between two consecutive beacons is equal to 10 meters unless waived by the Delegate Project Manager. The beacons carry a retro-reflecting device consisting of a strip 100 mm high placed 150 mm from the head of the beacon.


13) 909 - Weep holes
Barbacanes - Weep holes
This operation consists in setting up weep holes in PVC pipe φ 40 for drainage of the materials located behind the abutments or the retaining walls. The works consist in place, by the technical prescriptions and the plans of the technical file, weep holes in PVC pipe φ 40.

14) 910 - Drainage pipes
Gargouille - Drainage pipes
This operation consists in setting up drainage pipes in PVC pipe φ 100 for the evacuation of water from the deck of the bridge. The work convey the technical prescriptions and the plans of the technical file, drainage pipes in PVC pipe φ 100.


15) 1001 - Deviation- pedestrians crossing the bridge
Maintain  circulation - Deviation- pedestrians crossing of the bridge

This task is envisaged if it is necessary for the construction and maintenance of temporary works and a track for any deviation necessary to maintain traffic. 

16) SAFETY AND ENVIRONMENTAL PROTECTION
Safety measures shall be put in place to safeguard the health of the workers. They shall be 
equipped with personal protective equipment like helmets, boots, gloves, goggles, raincoats, etc. a first aid box shall be provided on the site to render first aid services in case of an accident. Before the start of each task, workers shall be reminded of the potential hazards associated with that task and the safety measures to be taken to avoid possible accidents. Working points shall be well signalized to road users using signboards placed at adequate positions that can be visible to everybody.
Every area from which soil is to be extracted shall be covered with vegetative soil at the end of the job to facilitate the growth of vegetation and to avoid erosion.
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CHAPTER 1: GENERAL PROVISIONS
These clauses are intended to assist the Project Owner and/or contractors responsible for works execution to integrate requirements aimed at optimizing the protection of the environment and the socio-economic environment.
These provisions apply to all activities likely to generate environmental and social impacts.
The Contractor shall comply with all applicable environmental laws and regulations in force in the country. In the daily organization of the works, the Contractor shall take all appropriate measures to minimize environmental impacts by applying the contract provisions and ensuring that its personnel, subcontractors, and employees also comply with and apply them.
1.1 Execution Program
The Contractor shall prepare and submit for approval by the Engineer a detailed environmental and social management program including the following:
a. Site Environmental Management Plan (PGEC)
The Contractor shall submit a Site Environmental Management Plan (PGEC) within 60 days from the notification of the contract. The PGEC shall be approved by the Engineer within 20 days and shall include at least:
· Organizational chart of environmental staff, including the project environmental officer; 
· Description of methods for mitigating biophysical and socio-economic impacts; 
· Plan for management and rehabilitation of borrow pits and quarries; 
· Water management and sanitation plan. 
b. Site Environmental Protection Plan (PPES)
The Contractor shall prepare and submit a detailed Site Environmental Protection Plan (PPES) covering site installation and material extraction areas. It shall include:
· Protection measures and execution program; 
· Site layout and location map at appropriate scale; 
· Methods for preventing pollution, fire risks, and road accidents; 
· Sanitary facilities and emergency access for local populations; 
· Environmental and safety regulations on site; 
· Post-construction site restoration plan. 
c. Waste Management and Disposal Plan (PGED)
The Contractor shall prepare a Waste Management and Disposal Plan within 60 days of notification of the contract. It shall identify all waste likely to be generated and specify collection, storage, transport, and disposal methods. It shall include:
· Methods to minimize material mixing and promote reuse; 
· Transport and disposal locations; 
· Monitoring and control procedures; 
· On-site reuse plan and management of surplus materials. 
1.2 Site Safety
The Contractor shall comply with national health and safety regulations. A medical service shall be established at the base camp according to workforce size. A safety officer shall ensure maximum safety for workers and surrounding populations.
1.3 Access to Community Infrastructure
The Contractor shall implement appropriate measures to ensure continuity of access to existing community infrastructure.
1.4 Site Logbook
The site logbook shall record all incidents or accidents with environmental or social impacts, as well as corrective actions taken.

CHAPTER 2: TECHNICAL REQUIREMENTS
2.1 Kick-off Meetings
Local authorities and communities shall be informed about the works, their scope, routes, duration, and potential impacts. Compensation procedures shall be explained where applicable. Coordination with forestry services shall be carried out to identify protected species.
2.2 Local Labour Employment
The Contractor shall prioritize local labour recruitment, ensuring gender equity where possible. External recruitment is allowed if skills are unavailable locally.
2.3 Site Selection
Sites shall be selected to minimize tree cutting, demolition of structures, and avoid sensitive areas.
2.4 Quarry Operation and Use
Quarry operations shall comply with national laws. The Contractor shall obtain required permits and bear all related costs.
Environmental protection plans shall be submitted at least one month before quarry exploitation.
Temporary quarries shall be rehabilitated after use, including:
· Soil restoration and revegetation; 
· Restoration of natural drainage; 
· Erosion control measures; 
· Site landscaping. 
Permanent quarries shall be managed to protect vegetation and drainage systems.
2.5 Hygiene, Cleanliness and Pollution Control
The Contractor shall:
· Properly manage hazardous and biomedical waste; 
· Prohibit dumping of waste on site; 
· Prevent pollution of soil and water; 
· Control dust and noise emissions; 
· Properly store hazardous substances; 
· Avoid obstruction of natural drainage. 
a. Flora and Fauna Protection
Vegetation outside the construction area shall be preserved. Damaged vegetation must be restored at the Contractor’s expense.
b. Health Measures
A site clinic shall be established. Regular medical check-ups and awareness campaigns on HIV/AIDS and STIs shall be conducted.
c. Traffic and Circulation
Speed limits shall be enforced (20–80 km/h depending on area). Sensitive areas must be protected.
d. Site Installation Plan
· Base camp must be located away from settlements and water sources; 
· Temporary roads shall be controlled; 
· Dust control measures shall be applied; 
· Proper waste management at closure of site. 
e. Awareness and Sensitization
Workers and communities shall be sensitized on environmental, social, and health risks.
f. Safety Measures
Sites shall be fenced, signposted, and access restricted.
g. Worker Protection
Workers shall be equipped with PPE appropriate to their tasks.
CHAPTER 3: REGULATIONS
The Contractor shall obtain all required permits and comply with all applicable laws.
Failure to comply may result in penalties, withholding of guarantees, or contract termination.
The Contractor shall restore the site at the end of works and remove all equipment and waste.
CHAPTER 4: MINIMUM CONTENT OF THE CODE OF CONDUCT
The Code of Conduct shall reflect risks and mitigation measures identified in:
· Environmental Impact Studies; 
· Permits and authorizations; 
· National laws and regulations; 
· Sector standards; 
· Complaint mechanisms. 
Risks include labor movement, communicable diseases, harassment, environmental damage, and misconduct.
CHAPTER 5: CODE OF CONDUCT REQUIREMENTS
The Code shall apply to all personnel and include at minimum:
1. Compliance with laws; 
2. Health and safety rules (including PPE use); 
3. Prohibition of illegal substances; 
4. Non-discrimination; 
5. Respectful community interactions; 
6. Zero tolerance for sexual harassment; 
7. Prohibition of exploitation and abuse; 
8. Child protection; 
9. Proper sanitation use; 
10. Conflict of interest prevention; 
11. Respect for work instructions; 
12. Protection of property; 
13. Obligation to report violations; 
14. Protection against retaliation. 
The Code must be written in clear language and signed by all workers confirming:
· Receipt of the Code; 
· Explanation received; 
· Understanding of contractual obligations; 
· Awareness of sanctions for violations.
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UNIT PRICE SCHEDULE FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
	N° 
	DESIGNATIONS
	Unit
	UNIT PRICE IN FIGURES 
	UNIT PRICE IN WORDS 

	
	SERIES 000 SITE INSTALLATION
	
	
	

	1
	Site installations
	Ls
	
	

	2
	Mobilisation and demobilisation of equipment
	Ls
	
	

	3
	Project information sign post
	Ls
	
	

	4
	Work execution program and as built plan
	Ls
	
	

	5
	Geotechnical studies
	Ls
	
	

	6
	Construction of temporal site office
	Ls
	
	

	
	Sub-Total : 000 Site Installation
	
	
	

	100
	Series 100: SITE PREPARATION
	
	
	

	101
	Site clearance and cutting of trees
	m²
	
	

	102
	Traffic flow (diversion of water course/road)
	Ls
	
	

	103
	Setting out of the bridge
	Ls
	
	

	104
	Hiring and installation of a batch for the construction of the central pilar of the bridge (Bartadeau)
	Ls
	
	

	
	Sub-Total : 100. Site preparation
	
	
	

	200
	Series 200: General earth works
	
	
	

	201
	Excavation of trenches 
	m³
	
	

	202
	Backfilling of excavation
	m³
	
	

	203
	Provision for demolition form the opening of the river bed downstream to construct the wing wall 
	Ls
	
	

	204
	Backfilling of the accesses of the bridge to raise the right of way 12m wide on both sides of the bridge and molding of the road to 9.50m wide
	m³
	
	

	205
	Resurfacing of the filled accesses to the bridge with laterite from borrowed pit 
	m³
	
	

	
	Sub-Total :200. General Earth works
	
	
	

	300
	Series 300-FOUNDATION-ABUTMENT-DECK-WING WALL-
	
	
	

	301
	Hard core
	m³
	
	

	302
	Stone masonry works for foundation abutment and wing walls
	m³
	
	

	303
	Lean concrete dosed at 150kg/m³
	m³
	
	

	304
	Supply and placing of ready made reinforced concrete dosed at 400kg/m³ for the foundation footings
	m³
	
	

	305
	Supply and placing of reinforced concrete dosed at 400kg/m³ for the beam seat, Deck intermediate bridge seating and kerbs
	m³
	
	

	306
	Reinforced concrete 15cm thick dosed at 350kg/m3 for the bridge’s raft
	m³
	
	

	307
	Supply and placing of traditional slab in reinforce concrete on both sides of the bridge 
	m³
	
	

	308
	IPE 300 for Cross girders (cut offs of IPE 500)
	ml
	
	

	309
	Longitudinal Girders of IPE 500 including all contingencies 
	ml
	
	

	310
	Archor of rods HA25 to a rock 
	ml
	
	

	311
	Drainage material behind the abutment 
	m³
	
	

	
	Sub-Total:300. Foundations-abutments-deck-wing wall
	
	
	

	400
	Series 400-EQUIPMENT
	
	
	

	401
	Mix Gulvanized guard rails (concrete pillars and metallic pipes)
	ml 
	
	

	402
	Weep holes in PVC
	U
	
	

	403
	Drainage pipes (PVC 100)
	ml 
	
	

	404
	Network reservation pipe 110 PVC
	ml 
	
	

	405
	Metallic sign posts (type AB)
	U
	
	

	406
	Round post markers (Balises) in treated eucalyptus well-seasoned wood
	U
	
	

	 
	Sub-Total : 400. Equipment
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BILL OF QUANTITIES AND COST ESTIMATE FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS HIGH OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
	N°
	RIVER 
	HEIGHT(ml)
	WIDTH(ml)
	SPAN(ml)
	ROAD 
	PK
	 BRIDGE  TYPE  

	 
	MEZAM
	8.00
	8m
	20.00
	 
	2+00
	 SIME DEFINED BRIDGE 

	N° 
	DESIGNATIONS
	Unit
	Q'ties
	U.P
	Total
Amount 

	 
	SERIES 000 SITE INSTALLATION
	 
	 
	 
	 

	1
	Site installations
	Ls
	1.00
	
	

	2
	Mobilisation and demobilisation of equipment
	Ls
	1.00
	
	

	3
	Project information sign post
	Ls
	1.00
	
	

	4
	Work execution program and as built plan
	Ls
	1.00
	
	

	5
	Geotechnical studies
	Ls
	1.00
	
	

	6
	Construction of temporal site office
	Ls
	1.00
	
	

	 
	Sub-Total : 000 Site Installation
	

	100
	Series 100: SITE PREPARATION

	101
	Site clearance and cutting of trees
	m²
	1779.00
	
	

	102
	Traffic flow (diversion of water course/road)
	Ls
	1.00
	
	

	103
	Setting out of the bridge
	Ls
	1.00
	
	

	104
	Hiring and installation of a batch for the construction of the central pilar of the bridge (Bartadeau)
	Ls
	1.00
	
	

	 
	Sub-Total : 100. Site preparation
	

	200
	Series 200: General earth works

	201
	Excavation of trenches 
	m³
	420.00
	
	

	202
	Backfilling of excavation
	m³
	327.09
	
	

	203
	Provision for demolition form the opening of the river bed downstream to construct the wing wall 
	Ls
	1.00
	
	

	204
	Backfilling of the accesses of the bridge to raise the right of way 12m wide on both sides of the bridge and molding of the road to 9.50m wide
	m³
	420.00
	
	

	205
	Resurfacing of the filled accesses to the bridge with laterite from borrowed pit 
	m³
	252.67
	
	

	 
	Sub-Total :200. General Earth works
	

	300
	Series 300-FOUNDATION-ABUTMENT-DECK-WING WALL-

	301
	Hard core
	m³
	185.18
	
	

	302
	Stone masonry works for foundation abutment and wing walls
	m³
	598.80
	
	

	303
	Lean concrete dosed at 150kg/m³
	m³
	5.09
	
	

	304
	Supply and placing of ready made reinforced concrete dosed at 400kg/m³ for the foundation footings
	m³
	66.19
	
	

	305
	Supply and placing of reinforced concrete dosed at 400kg/m³ for the beam seat, Deck intermediate bridge seating and kerbs
	m³
	79.78
	
	

	306
	Reinforced concrete 15cm thick dosed at 350kg/m3 for the bridge’s raft
	m³
	4.29
	
	

	307
	Supply and placing of traditional slab in reinforce concrete on both sides of the bridge 
	m³
	1.90
	
	

	308
	IPE 300 for Cross girders (cut offs of IPE 500)
	ml
	81.90
	
	

	309
	Longitudinal Girders of IPE 500 including all contingencies 
	ml
	120.00
	
	

	310
	Archor of rods HA25 to a rock 
	ml
	5.00
	
	

	311
	Drainage material behind the abutment 
	m³
	12.00
	
	

	 
	Sub-Total:300. Foundations-abutments-deck-wing wall
	

	400
	Series 400-EQUIPMENT

	401
	Mix Gulvanized guard rails (concrete pillars and metallic pipes)
	ml 
	42.70
	
	

	402
	Weep holes in PVC
	U
	48.00
	
	

	403
	Drainage pipes (PVC 100)
	ml 
	12.00
	
	

	404
	Network reservation pipe 110 PVC
	ml 
	86.00
	
	

	405
	Metallic sign posts (type AB)
	U
	2.00
	
	

	406
	Round post markers (Balises) in treated eucalyptus well-seasoned wood
	U
	12.00
	
	

	 
	Sub-Total : 400. Equipment
	      
	
	
	

	 
	SUMMARY

	0
	SITE INSTALLATION
	 
	

	100
	SITE PREPARATION
	 
	

	200
	General earth works
	 
	

	300
	FOUNDATION-ABUTMENT-DECK-WING WALL-
	 
	

	400
	EQUIPMENT
	 
	

	A
	TOTAL AMOUNT WITHOUT TAXES
	 
	

	B
	VAT (19,25%)
	 
	

	C
	AIR  (2.2%)
	 
	

	D
	AMOUNT WITH ALL TAXES INCLUSIVE
	 
	

	E
	NET AMOUNT 
	 
	



[bookmark: _Hlk237760451]This estimates has been closed at the sum of ,,,,,,,,,,,,,,,,,,,(amout in words ) FCFA ATI
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	Designation  of Works :

	N° price
	Daily output
	Total Quantity 
	Duration (days)

	
	/ day
	
	

	WORKMANSHIP
	Category
	Number
	Daily Salary
	Days paid
	Amount

	
	
	
	
	
	

	
	Site engineer
	
	
	
	

	
	Site foreman 
	
	
	
	

	
	Team chiefs 
	
	
	
	

	
	Administrative staff
	
	
	
	

	
	Driver 
	
	
	
	

	
	Specialised Technicians
	
	
	
	

	
	Labourers 
	
	
	
	

	
	Total A
	
	
	
	

	MACHINES OR EQUIPMENT
	
	
	
	
	

	
	Type
	Quantity
	Daily rate
	Days paid
	Amount

	
	
	
	
	
	

	
	
	
	
	
	

	
	Pickup for follow-up 
	
	
	
	

	
	Small equipment 
	
	
	
	

	
	
	
	
	
	

	
	Total B
	
	
	
	

	DIVERSES MATERIALS 
	
	
	
	
	

	
	Type
	Quantity
	Unit Price
	Consumption
	Amount

	
	* 
	
	
	
	

	
	Total C
	
	
	
	

	
	
	
	
	
	

	D
	TOTAL DRY PRICE A+B+C
	
	
	
	

	E
	General site expenses 
	
	X%
	D x X%
	

	F
	General head office expenses 
	
	Y%
	D x Y%
	

	G
	TOTAL COST PRICE 
	
	
	D + E + F
	

	H
	Risks + benefits 
	
	Z%
	G x Z%
	

	P
	TOTAL COST PRICE WITHOUT TAXES 
	
	G + H
	

	V
	SELLING UNIT PRICE WITHOUT TAXES
	
	P/QTE
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	REPUBLIQUE DU CAMEROUN
Paix – Travail – Patrie
-----------
	[image: SANTA COUNCIL LOGO]
	REPUBLIC OF CAMEROON
Peace – Work – Fatherland
-----------

	REGION DU NORD-OUEST
----------------
	
	NORTH WEST REGION
----------------

	DEPARTEMENT DE MEZAM     
-----------------------
	
	MEZAM DIVISION
-----------------------

	COMMUNE DE BAFUT 
----------------------------
	
	BAFUT    COUNCIL
----------------------------

	SEERVICE DE PASSATION
DES MARCHES PUBLIQUES 
-----------------------------------
	
	SERVICE OF CONTRACT AWARD
-----------------------------------





Contract  NO ……/ONIT / MINDDEVEL /NWR/ BC/BCITB/FEICOM/2026 OF THE   ….. 10/2026 AWARDED BY OPEN NATIONAL INVITATION TO TENDER
NO ……/ONIT / MINDDEVEL /NWR/ BC/BCITB/FEICOM/2026 OF THE   ….. 10/2026 FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
 (IN EMERGENCY PROCEDURE)

  HOLDER:                   ……………………………..
BP ………………………   TEL. ……………………
N°R.C. ……………………………..  
N° TAXPAYER.  …………………………….
Account N°. ………………………… at  …………………..
                                   Agency of ………………………..

SUBJECT ; THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION

PLACE:                                  BAFUT  COUNCIL

DURATION:                          eight  (08) months 

AMOUNT:                              …………………………… FCFA  TTC

	IAT
	

	EVAT
	

	VAT (19.25%)
	

	IR (2.2 %)
	

	Net to be paid
	




FINANCING:                          FEICOM /BAFUT  COUNCIL Budget 2026 Fiscal Year 

SUBSCRIBED on.….………………………………
SIGNED on……………....…………………….…
NOTIFIED on……….………………………………
REGISTERED on….………………………………

BETWEEN:  

The REPUBLIC OF CAMEROON, represented by the Mayor of BAFUT  Council, hereinafter referred to as the, “ADMINISTRATION” on the one hand,



AND
_____________ whose head office is situated at _________BP____, Tel: __________ represented by it’s Director General hereinafter referred to as the “CONTRACTOR” on the other hand.

	





		
IT IS HEREBY AGREED ON AND ORDERED AS FOLLOWS:




























SUMMARY

Part I:		Special Administrative Clause (SAC)
Part II:		Special Technical Conditions (STC)
Part III:	Schedule of Unit Prices
Part IV:	Details or Estimate































Page....and last of the Contract  NO ……/ONIT / MINDDEVEL /NWR/ BC/BCITB/FEICOM/2026 OF THE   ….. 10/2026 AWARDED BY OPEN NATIONAL INVITATION TO TENDER
NO ……/ONIT / MINDDEVEL /NWR/ BC/BCITB/FEICOM/2026 OF THE   …..10/2026 FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION
 (IN EMERGENCY PROCEDURE)



WITH The enterprise ………………………..   P.O. Box  …………………………………


[bookmark: _Hlk127507243]SUBJECT; THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION.

EXECUTION DEADLINE: ……… (………) months

AMOUNT OF CONTRACT IN FCFA:
				
	IAT
	

	EVAT
	

	VAT (19.25%)
	

	AIR (2.2 %)
	

	Net to be paid
	




	READ AND APPROVED BY THE ENTREPRENEUR









BAFUT  , the............................................
	THE MAYOR OF BAFUT    COUNCIL









BAFUT  , the........................................
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I the undersigned Mr. ……………………………………  
Taxpayer n° ………………………………….  
Acting on the name and on behalf of ETS………………. P.O. BOX ………..  

After having taken knowledge, of all relative files of the present contract document for the construction of a bridge measuring 20m long and 8 meters wide over the Mbee river in Bafut Council, Mezam Division of the North West Region.
.
.1 -. Submit and commit to execute the works in accordance with the invitation to tender file according to the prices that I have fixed after having appreciated to my point of view and under my responsibility, the nature and the benefit, which make up the sum of ..………………………………. Francs cfa all taxes included.  

Amount in figures FCFA TTC:  ………………………..   

2 - Commit to undertake from the receipt of the service order to begin works given out by the Delegated Contracting Authority, the setting up of the personnel for the works and the material as foreseen in the terms of the contract file.  

3 - Declare that this tender remains valid within ninety (90) days counting from the limit date of the submission of the bid.  

4 - Commit to respect the delays of three (03) months foreseen by the planning of execution of the works that I myself have established.  

5 - Affirm by right at the risk of termination that I have not fallen as well as the enterprise for which I act, under the influence of legal interdictions decreed in the Republic of Cameroon.  

  Done at…………… on…………………  
Signature (s



















[bookmark: _Hlk66695367]Annex No. 2: Model Bid Bond

Bank …………………………………………………….
Reference of guarantee: No. …………………………….
[bookmark: _Hlk529435023]To the Mayor of BAFUT  Council
Republic of Cameroon
Invitation to Tender No.  ……………….
BID BOND FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION.

The Contractor (5)   ……………………………………….hereby submits on ……………………. to  the Mayor of BAFUT    Council a bid relating to the construction of a bridge measuring 20m long and 8 meters wide over the Mbee river in Bafut Council, Mezam Division of the North West Region.


To this  effect, and in keeping with the conditions stated in the Tender file, the bidder shall present to the Mayor of BAFUT  Council acting in the capacity of Contracting Authority, a bid bond amounting to CFA Francs ……………………………………………………….…………… (6).
By this guarantee, we the undersigned,(7)………………………………….with our registered office in ………………………….., are committed towards the Mayor of BAFUT  Council (Contracting Authority), through the bidder for the sum of CFA Francs  ………………………(in figures)……………………………………………..
……………………………………………………………………………………….. (in full).
By this guarantee, we irrevocably commit ourselves, without any argument or delay, to pay into an account indicated by the Mayor of BAFUT  Council, the amount of the guarantee at the first written request, as soon as the latter shall inform us in writing that the bidder does not keep the commitment he took in his tender.   
The request for payment of guarantee shall be countersigned by the Mayor of BAFUT  Council. This guarantee shall be released latest thirty (30) days after the expiration of the validity of the tender or, in case the enterprise shall be the successful bidder, after presentation of the performance bond which shall be kept by the Council Internal Tenders Board.
The laws as well as the jurisdiction of application for the guarantee shall be those of the Republic of Cameroon.
Done at ……………………….., on ……………………..
Mr (Messrs)……………………………….
                                                                             Signature(s) & stamps ……..
(5) Bidder
(6) Stated in the Special regulations governing the invitation to tender
(7) Bank
[bookmark: _Hlk66695439]
Annex No. 3: Model of Performance Bond (Retention Fund)

Bank:  
Reference of bank guarantee:  
N°………………………………………………………………………  

To the Mayor of BAFUT  Council (Contracting Authority)  

The enterprise………………………………………………………………………   

SECURITY BOND FOR THE GUARANTEE OF GOOD EXECUTION OF CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION.
We, Bank…………………………………………………………… have been informed that between the Mayor of BAFUT  Council acting as the  Contracting  Authority , and…………………………………… acting as entrepreneur, a contract has been concluded for the construction of a bridge measuring 20m long and 8 meters wide over the Mbee river in Bafut Council, Mezam Division of the North West Region covering the guarantees, engagement and other liabilities being incumbent upon the entrepreneur because of the contract of an amount equal to…………………………  
We, Bank…………………………………………..engage ourselves irrevocably and without profit of discussions by thispresent, to pay in favour of the Cameroonian administration at the first written request of the Mayor of BAFUT    Council and within eight (08) weeks maximum period, up to the amount of thispresent guarantee, the sum of ………………………………………………………………..       
All that could be due the Mayor of BAFUT  Council by the entrepreneur because the entrepreneur would not fulfill one or several of his/her engagement as stipulated in his/her bid. 

A mobilisation request of thispresent guarantee will be object of a justifying recommended letter with accused receipt and copy to the entrepreneur clearly formulating completely the reasons of thisrequest.  
Thispresent banking guarantee will enter in force at the date of notification of the contract to the entrepreneur.  
The original of thispresent guarantee will be preserved in the services of the Mayor of BAFUT    Council.

Thisguarantee will be released within sixty (60) days counting from the date of the provisional reception of works.  
After thisdate, the guarantee will be without object and should be returned to us without express demand of our part.  
The law as well as the jurisdiction applicable to thisguarantee are those of the Republic of Cameroon.   

Done at…………… on…………………  
                                                                                      Signature (s)  
[bookmark: _Hlk66695508]
Annex No. 4: Declaration Form


THE MODEL UNDERTAKING BY THE BIDDER

Name of project:…………………………..Invitation to tender No. :…………………
FOR THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION.


I (We) the undersigned (8) ……………………………………………………………..
Acting in the capacity of (9) ……………in the name and on behalf of (10)…………………………………………………. at …………………….RC No. …………………by virtue of the power vested in me (us), domiciled at P.O.Box……………. (Town) ………………, telephone N° ………………………., after having studied all the documents of the tender file relating to the Invitation to Tender N° …………………………….., and after having assessed in my (our) point of view and under my (our) responsibility the nature and difficulties entailed with the execution of the job, I (we) do hereby tender and commit myself (ourselves) to carry out the construction of a bridge measuring 20m long and 8 meters wide over the Mbee river in Bafut Council, Mezam Division of the North West Region in keeping with the terms and conditions of the tender file.    

I commit myself (We commit ourselves) in case my (our) tender is retained, to execute the contract within ……………… (……………………) months as from the date of notification of award of the contract.
I hereby commit myself (We hereby commit ourselves) to maintain the amount of my (our) tender for a period of sixty (60) days with effect from the deadline for submission of bids.
Done at ……………………………. , on ………………

General Manager

Signature(s)……………………. 
Biddder(s)…………………………………. 
For companies, indicate:

The company (company or trade name, form, nationality and registered office)
« represented by the undersigned ……………………………… » (name, first name and status)

For companies without a legal status, indicate:

« We, the undersigned, ……………………………………………………………………. »
(For each person: name, first name, company name, nationality, location of the registered office)
« Constituted in a group of companies for the execution of this contract, jointly commit ourselves …….. »
(8) Name, first name, profession, residence 
(9) Position in the enterprise
(10) Company name 


[bookmark: _Hlk66695539]
Annex No. 5: Model of Start-Off Advance Bond

Bank ………………………………………………….

Reference of guarantee No.……………………………
To the Mayor of BAFUT  Council MEZAM  Division
Republic of Cameroon
Invitation to Tender No.  ……………….

BANK GUARANTEE FOR THE REFUND OF THE START-OFF ADVANCE RELATING TO THE CONSTRUCTION OF A BRIDGE MEASURING 20M LONG AND 8 METERS WIDE OVER THE MBEE RIVER IN BAFUT COUNCIL, MEZAM DIVISION OF THE NORTH WEST REGION.

We…..…………………………………… (Bank) have been informed that a contract shall be signed between the Mayor of BAFUT  Council, acting in the capacity of Contracting Authority, and…………. …………………….., acting for the construction of a bridge measuring 20m long and 8 meters wide over the Mbee river in Bafut Council, Mezam Division of the North West Region.

In compliance with the provisions of Article ………… of Contract N° ………..., the contractor shall be bound to present to the Mayor of BAFUT Council, Contracting Authority, a bank guarantee with the purpose to assure the refund of the start-off advance granted to the enterprise and amounting to CFA Francs ………………………………………  ………………………………………... 
We, …………………………………..(bank) do hereby commit ourselves, irrevocably and without arguing to pay to Mayor of BAFUT    Council, at the written request the Mayor of BAFUT    Council and within three (03) weeks the amount of this guarantee, that is to say. …………….……………………. ,  all the amounts that the contractor may owe the Contracting Authority for failing to fulfil one or more of his obligations under the contract. 
The request to partially or fully stake this guarantee shall be the subject of a registered letter of justification with confirmation of receipt and a copy to the contractor clearly stating and supplementing the reasons for his request. This letter shall be countersigned by the Mayor of BAFUT  Council .
The bank guarantee shall take effect as from the date of payment of the start-off advance. The original of this guarantee shall be kept by the Council Internal Tenders Board. The guarantee shall be released upon refund of the full amount of the advance.  After this date, the guarantee shall no longer apply and shall be returned to us without express request. 
The laws as well as the jurisdiction of application for the guarantee shall be those of the Republic of Cameroon.

Done at ……………………….., on ……………………..

Mr (Messrs)………………………………………..
Signature(s) & stamps of the bank









[bookmark: _Hlk66695601]Annex No.6: Site Visit Report


1. INTRODUCTION
TENDER Nº (withprojecttitle) …………………………………………………………………
NAME OF ENTERPRISE ……………………………………………………………………..
DATE: ……………………………………………… TIME: ……………………………………….
II) COMMENTARY:
II-1) Nature of the project site …………………………………………………….

II-2) Accessibility to the project site: ……………………………………………………

II-3) Vegetation (trees, shrubs etc) ………………………………………………………
		
II-4) Topography of the site ……………………..

III) AVAILABILITY OF SERVICES (water, electricity, etc)

IV) AVAILABILITY OF CONSTRUCTIONAL MATERIAL (stones, sand, gravel, wood etc) 


V) DIFFICULTIES: ………………………….……………………………………………….
…………………………………………………………………………………………………………………….…………………………………………………………………………………………………………………….
V) CONCLUSION …………………………………………………………………………
……………………………….…………………………………………………………………………………………………………………….


SIGNATURES:


	Visa of project owner or Representative






	Contractor’s Engineer


`
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[bookmark: _Hlk233712983]MATURITY CLEARANCE OR SUPPORTING DOCUMENTS FOR PRELIMINARY STUDIES




















annex No. 1
1. Attach the preliminary study: 
2. Indicate: 
2.1. The date the study was carried out;
2.2. The name of the public or private project manager/consultant who conducted the study;
2.3. The contract references, where the study was carried out by a private consultant;
2.4. Where applicable, indicate whether it concerns maintenance works;
2.5. Description of the studies:
(For small-scale projects, a brief presentation note may be prepared as a preliminary study, provided that it clearly outlines cost estimates and technical specifications.)
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INTEGRITY CHARTER
TITLE OF THE INVITATION TO TENDER: ________________________________
[to be specified during preparation of the bidding documents]

The “BIDDER” hereby undertakes to comply with the provisions of this Integrity Charter.
To: THE “CONTRACTING AUTHORITY”
1. Eligibility and Legal Status
We acknowledge and certify that neither we nor any member of our consortium or our subcontractors are in any of the following situations:
1.1 Being in a state of, or subject to, bankruptcy, liquidation, judicial settlement, cessation of business, or any analogous situation resulting from a similar procedure;
1.2 Being listed on financial sanctions lists adopted by the United Nations or any other Technical and Financial Partner in connection with procurement or contract execution;
1.3 Having provided false information or submitted fraudulent documents as part of this procurement process.
2. Conflict of Interest
We certify that neither we nor any member of our consortium or our subcontractors are in any of the following conflict-of-interest situations:
2.1 Being a controlling shareholder of the Contracting Authority or a subsidiary controlled by the Contracting Authority, unless such conflict has been disclosed to and resolved by the Public Procurement Authority;
2.2 Having business or family relationships with a member of the Contracting Authority’s staff involved in the procurement or contract supervision process, unless such conflict has been disclosed and resolved to the satisfaction of the Public Procurement Authority;
2.3 Controlling or being controlled by another bidder, being under common control with another bidder, receiving or granting subsidies directly or indirectly to another bidder, sharing the same legal representative, or maintaining direct or indirect contact with another bidder enabling access to confidential information or influencing the procurement process;
2.4 Being engaged in a consulting assignment that, by its nature, may be incompatible with our obligations to the Contracting Authority;
2.5 In the case of works or supply contracts:
i) Having prepared or been associated with a consultant who prepared specifications, plans, calculations, or other documents used in the procurement process;
ii) Being, or having an affiliated firm that is, recruited or expected to be recruited by the Contracting Authority to carry out supervision or control of the works under the contract.

3. Public Entities
Where we are a public entity or public enterprise, we certify that we have legal and financial autonomy, operate under private accounting rules, and are not under the authority of the Contracting Authority or Delegated Contracting Authority, unless expressly authorized by the Public Procurement Authority.
4. Obligation of Disclosure
We undertake to promptly inform the Contracting Authority, who shall in turn notify the Public Procurement Authority, of any change in our status regarding points 1 to 3 above.
5. Ethical Conduct
In the context of the procurement and execution of the Contract:
5.1 We have not engaged and shall not engage in any unfair practices (acts or omissions) intended to deliberately mislead others, conceal information, distort consent, or circumvent legal or regulatory obligations to obtain undue advantage;
5.2 We have not engaged and shall not engage in any practices contrary to legal or regulatory obligations or internal rules for the purpose of obtaining undue benefit;
5.3 We have not promised, offered, or granted, and shall not promise, offer, or grant, directly or indirectly, any undue advantage to:
(i) any public official (legislative, executive, administrative, or judicial), whether appointed or elected;
(ii) any person performing a public function, including within public bodies or enterprises;
(iii) any person defined as a public agent,
for the purpose of influencing the performance of their duties;
5.4 We have not promised, offered, or granted, and shall not promise, offer, or grant any undue advantage to any person working in the private sector to induce them to act in violation of their legal or professional obligations;
5.5 We have not offered and shall not offer any undue advantage to the Contracting Authority, its staff, or those responsible for supervising contract execution, likely to influence their objectivity;
5.6 We have not offered and shall not offer any undue advantage to the Contracting Authority, members of procurement committees or evaluation subcommittees, likely to influence the procurement process;
5.7 We undertake to refrain from any collusive or anti-competitive practices aimed at restricting or distorting competition, including artificially maintaining bid prices or limiting market access for other bidders.
6. Audit and Control
We, along with members of our consortium and subcontractors, authorize the Contracting Authority and procurement bodies to examine documents and accounting records relating to the procurement and execution of the contract, and to submit them for verification by the Public Procurement Regulatory Authority (ARMP) or any other State control body.
7. Sanctions
In the event of non-compliance with the provisions of this Charter, we acknowledge that we may be subject to the sanctions provided for under applicable laws and regulations.
Name: ___________________________
Signature: _______________________
Duly authorized to sign the bid on behalf of: _______________________
Date: ___________________________
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ENVIRONMENTAL AND SOCIAL COMMITMENT DECLARATION
TITLE OF THE INVITATION TO TENDER: ________________________________
[to be specified during preparation of the bidding documents]
The “BIDDER” hereby undertakes to comply with the provisions of this Environmental and Social Commitment Declaration.
To: THE “CONTRACTING AUTHORITY”
In the context of the procurement and execution of the Contract:
1. Compliance with Social Standards
We undertake to comply with, and ensure compliance by all members of our consortium and our subcontractors with, the social standards applicable in Cameroon, including ratified international conventions, in particular:
i) compliance with the minimum wage as provided for by the Labour Code and relevant collective agreements;
ii) prohibition of the employment of children under the age of 14;
iii) compliance with regulations governing types of work prohibited for women and pregnant women;
iv) observance of mandatory weekly rest;
v) entitlement to paid leave;
vi) compliance with regulations governing night work;
vii) adherence to hygiene and safety conditions at the workplace;
viii) mandatory use of personal protective equipment (PPE).
2. Environmental Protection Measures
Furthermore, we undertake to implement environmental risk mitigation measures as set out in the environmental impact statement provided, where applicable, by the Contracting Authority.
In all cases, we commit to complying with, and ensuring compliance by all members of our consortium and subcontractors with, guidelines promoting the use of equipment and practices that have minimal environmental impact.
3. Audit and Control
We, along with members of our consortium and our subcontractors, authorize the Contracting Authority and procurement committees to examine documents and accounting records relating to the procurement and execution of the Contract, and to submit them for verification by the Public Procurement Regulatory Authority (ARMP) or any other State oversight body.
4. Sanctions
In the event of non-compliance with the provisions of this Declaration by ourselves, any member of our consortium, or our subcontractors, we acknowledge that we may be subject to the sanctions provided for under the applicable laws and regulations.
Name: ___________________________
Signature: _______________________
Duly authorized to sign the bid for and on behalf of: _______________________
Date: ___________________________
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[bookmark: _Hlk233713083]SIGNED AND DATED CONTRACTOR’S OCCUPATIONAL HEALTH AND SAFETY CHARTER 
























TITLE OF THE INVITATION TO TENDER: ________________________________
[to be specified during preparation of the bidding documents]
1. Purpose of the Charter
This Charter sets out the basic Occupational Health and Safety (OHS) rules that every contractor must comply with during the execution of works. Its purpose is to protect workers, users, visitors, and property.
2. Essential Safety Rules to be Observed
2.1 Mandatory Use of Personal Protective Equipment (PPE)
The Contractor undertakes to ensure that all its personnel wear appropriate PPE during operations, depending on the nature of the work, including:
· Safety helmet; 
· Gloves; 
· Safety shoes; 
· Protective goggles; 
· Safety harness (for work at height). 
Personnel without proper PPE shall not be allowed to work.
2.2 Responsible Conduct on Site
The Contractor shall ensure that its personnel:
· Do not consume alcohol or drugs; 
· Adopt responsible and safe behavior; 
· Comply with instructions issued by site supervisors. 
2.3 Accident Prevention
The Contractor shall:
· Secure the work area (barriers, signage); 
· Avoid any unsafe practices or improvisation; 
· Immediately stop work in case of hazardous situations.

2.4 Cleanliness and Orderliness
The Contractor undertakes to:
· Keep the work area clean; 
· Avoid obstruction of access routes; 
· Properly dispose of all waste generated. 
2.5 Incident Management
The Contractor shall:
· Immediately report and record any accident, incident, or hazardous situation; 
· Cooperate in the analysis and resolution of such incidents. 
2.6 Competent Personnel
The Contractor undertakes to employ personnel who are:
· Qualified; 
· Physically fit; 
· Informed of the risks associated with their tasks. 
3. Contractor’s Commitment
By signing this Charter, the Contractor undertakes to:
· Comply with the above rules; 
· Inform and train its personnel accordingly; 
· Take all necessary measures to ensure safety. 
4. Consequences of Non-Compliance
The Contracting Authority reserves the right to:
· Suspend or terminate the works; 
· Deny site access to any non-compliant personnel; 
· Apply the sanctions provided for in the contract. 
5. Signatures
The Contractor
Name: .........................................................................................
Position: ......................................................................................
Signature & Stamp:

The Contracting Authority
Name: .........................................................................................
Position: ......................................................................................
Signature:
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LIST OF AUTHORIZED BANKING INSTITUTIONS AND INSURANCE COMPANIES FOR ISSUING BID SECURITIES IN PUBLIC PROCUREMENT (2026)





       






















A. BANK
1. Access Bank Cameroun B.P 6000 Yaoundé.
2.   Afriland First Bank (AFB) BP 11834 Yaoundé;
3.  Bange Bank Cameroun (BANGE CMR° BP.34.692) ;
4. 	Banque Atlantique du Cameroun (BACM) BP 2933 Douala;
5.  Banque Camerounaise des Petites et Moyennes Entreprises (BC-PME) BP 12962 Yaoundé;
6. Banque Gabonaise pour le Financement International (BGFI BANK) BP 600 Douala;
7.  Banque Internationale du Cameroun pour l’Epargne et le Crédit (BICEC) BP 1925 Douala ; 
8. Citi Bank Cameroun ( CitibankCameroon) BP 4571 Douala; 
9. Commercial Bank of Cameroon (CBC) BP 4004 Douala;
10. Crédit Communautaire d’Afrique Bank (CCA Bank) BP 30388 Yaoundé; 
11. Ecobank Cameroon (ECOBANK) BP 582 Douala; 
12. National Financial Credit Bank (NFC-BANK) BP 6578 Yaoundé; 
13. Société Commerciale de Banques-Cameroun (SCB-CAMEROUN) BP 300 Douala; 
14. Société Générale Cameroun (SGC) BP 4042 Douala ; 
15. Standard Chartered Bank Cameroon (SCBC) BP 1724 Douala; 
16. Union Bank of Cameroon (UBC) BP 15569 Douala. 
17 United Bank for Africa (UBA) BP 2088 Douala. 
18. Régionale d’Epargne et de Crédit BP 30145 Douala Cameroun ;
19. Bank Of Africa (Cameroun), BP 4593.  

B. INSURANCE COMPANIES

19.Activa Assurances BP 12970 Douala;
20.AREA Assurances S.A BP 15584 Douala ; 
21.Atlantique Assurances S.A BP 173 Douala ;
22. Chanas Assurances Cameroun S.A BP 109 Douala ; 
23. CPA /SA BP 54 Douala ;
24. NSIA Assurance S.A BP 2759 Douala.
25. PRO ASSUR BP 5963 Douala
26. Prudential Beneficial General Insurance S.A BP 2328 Douala;
27. ROYAL ONYX Insurance Cie BP 12230 Douala ;
28.SAAR S.A BP 1011 Douala ;
29. SANLAM Assurances Cameroun  BP 12125 Douala;
30.Zenith Insurance BP 1540 Douala.

ADMINISTRATIVE DOCUMENTS.
	DOC N°
	DESCRIPTION

	A.1
	Certified Copy of the Business Registration, not more than three months old.

	A.2
	Declaration of intention to tender stamped with the tariff en force (see model).

	A.3
	Certificate of non-bankruptcy established by the Court of 1st instance or the Chamber Commerce, Industry and Trade of the place of residence of the bidder, not more than three (03) months.

	A.4
	Attestation of bank account of the bidder, issued by a first rate-bank approved by the Ministry in charge of Finance or by a foreign bank the first order not more than three months. 

	A.5
	Purchase receipt of Tender File issued by BAFUT council treasury of One hundred and fifty thousand FCFA (150.000 FCFA)

	A.6
	A bid bond of THREE MILLION FIVE HUNDRED AND SEVENTY THOUSAND NINE HUNDRED AND TWENTY SEVEN FCFA (3,579,927 CFA)  issued by a first rate-bank approved by the Ministry in charge of Finance in conformity with COBAC conditions.
The said guarantee must be accompanied by a consignment receipt issued by the “Caisse Depôt et Cosignation (CDEC) in accordance with Circular letter No 0000019/L/MINMAP of 5th June 2024 relating to the constitution of deposits, retention, restitution and deconsignment of bonds on public contracts

	A.7
	An attestation of non-exclusion from Public Contracts issued by the Public Contract Regulatory Board (ARMP)

	A.8
	An Attestation of the National Social Insurance Fund stating that the bidder has met all his obligations vis a vis the Fund; the attestation should be valid within the specified time

	A.9
	A valid Certificate of Fiscal conformity stamped with the tariff en force 

	A.10
	Copy of valid taxpayers card stamped with the tariff en force 

	A 11
	location plan of the enterprise stamped with the tariff en force

	A 12
	Power of attorney if necessary

	A 13
	Group agreement if need be





The absence of or insufficient bid bond, a valid copy of a CDEC receipt, a valid certificate of categorization and the non-respect of the   48hrs given for the absence or non-conformity of any other document in the administrative file will result to the elimination of the offer.


The second Internal Envelope shall be labeled <<ENVELOPE B:  TECHNICAL DOCUMENT>> and shall contain the following: 

	Eliminatory Criteria (See evaluation of administrative files) 

	Designation
	BIDDERS

	
	A
	B
	C

	 
	a. General presentation of bids
	EVALUATION (Yes or No)

	a1
	˗ Document spirally bound 
	 
	 
	 

	a2
	˗ Table of content page
	 
	 
	 

	a3
	˗ Colour sheets separation apart from white
	
	
	

	
	-page numbering
	
	
	

	a4
	- neatness and clarity of documents
	 
	 
	 

	a5
	˗  Presentation of documents in the order given in this tender 
	 
	 
	 

	
	
	
	
	

	 
	TOTAL a
	/5
	/5
	/5

	 
	b. The company references
	EVALUATION (Yes or No)

	
	References of the company in civil construction or similar works for the past Five years 
	 
	 
	 

	b1
	At least 01 Certified copy of similar contracts equal or above 180 million (1st and last page) and PV of provisional reception for projects executed within the last five years (pluri annual projects accepted)
	 
	 
	 

	b2
	Atleast 01 Certified copy of similar contracts below 100 million and more than 50 million (1st and last page) and PV of provisional reception.
	 
	 
	 

	 
	TOTAL  b
	/2
	/2
	/2

	 
	c. Equipment
	EVALUATION (Yes or No)

	c1
	Proof of ownership or hire of a liason vehicle (Pick up 4 x 4 or van) (Hired or owned)
	 
	 
	 

	c2
	Proof of ownership or hire of a truck of at least 20 tonnes capacity
	 
	 
	 

	c3
	Proof of ownership or hire of a front head loader or similar equipment
	 
	 
	 

	c4
	Proof of ownership or hire of a bulldozer of good condition
	 
	 
	 

	c5
	Proof of ownership or hire of a theodolite
	 
	 
	 

	c6
	Proof of ownership or hire of an optical level equipment
	 
	 
	 

	c7
	 Proof of ownership or hire of a compactor in good condition
	 
	 
	 

	c8
	Prof of ownership of a survey kit
	 
	 
	 

	c9
	Prof of ownership of a carpentry kit
	 
	 
	 

	c10
	Prof of ownership of a masonry kit
	 
	 
	 

	 
	TOTA 2 
	/10
	/10
	/10

	 
	d. Personnel of the Enterprise
	EVALUATION (Yes or No)

	 
	Works Engineer: Civil Engineer or Bachelor in Civil Engineering with at least 5yrs of experience and member of the National order
	 
	 
	 

	d1
	Certified copy of valid national identity card
	 
	 
	 

	d2
	 Diploma of work Engineer certified 
	 
	 
	 

	d3
	CV signed and dated by works Engineer
	 
	 
	 

	d4
	Member of the order of civil engineers
	 
	 
	 

	d5
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	 
	Site foreman: Senior Civil Engineering technician or HND with atleast 5yrs experience
	 
	 
	 

	d6
	Certified copy of valid national identity card
	 
	 
	 

	d7
	 Certified copy of certificate of Foreman 
	 
	 
	 

	d8
	CV signed and dated by site foreman
	 
	 
	 

	d9
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	 
	Chief mason: CAP, at least 5yrs of experience
	 
	 
	 

	d10
	Certified copy of valid national identity card
	 
	 
	 

	d11
	Certified copy of diploma
	 
	 
	 

	d12
	Cv signed and dated
	 
	 
	 

	d13
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	 
	Chief surveyor; Atleast Probatoir in survey with atleast five years’ experience
	 
	 
	 

	d14
	Certified copy of diploma
	 
	 
	 

	d15
	Cv signed and dated
	 
	 
	 

	d16
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	 
	Chief carpenter: Atleast CAP in wood work/joinery atleast three years
	 
	 
	 

	d17
	Certified copy of valid national identity card
	 
	 
	 

	d18
	Certified copy of diploma
	 
	 
	 

	d19
	Cv signed and dated
	 
	 
	 

	d20
	Attestation of availability dully signed by bearer and dated
	 
	 
	 

	
	Hygiene, safety and environment manager.
(Environmentalist A/L+3 or more
	
	
	

	d21
	Certified copy of valid national identity card
	
	
	

	d22
	Certified copy of diploma
	
	
	

	d23
	Cv signed and dated
	
	
	

	d24
	Attestation of availability dully signed by bearer and dated
	
	
	

	
	
	 
	 
	 

	 
	TOTAL d
	/25
	/25
	/25

	 
	e) Technical Proposals
	EVALUATION (Yes or No)

	e1
	Attestation of site visit
	 
	 
	 

	e2
	Site visit report with pictures duely signed by presenter 
	 
	 
	 

	e3
	Detailed technical note and proposals
	 
	 
	 

	 
	TOTAL e
	/3
	/3
	/3

	 
	f) The methodology of intervention and execution of work
	EVALUATION (Yes or No)

	f1
	Site organisation in teams or options
	 
	 
	 

	f2
	Description of the socio - environment measures for site protection
	 
	 
	 

	f3
	Dispositions prevued for the securisation of personnel and and other ussers
	 
	 
	 

	f4
	Use of local manpower
	 
	 
	 

	f5
	CCTP dully initialled and dated on each page and signed on the last page
	 
	 
	 

	 
	TOTAL f
	/5
	/5
	/5

	 
	g. Planning of execution of works
	EVALUATION (Yes or No)

	g1
	Coherent planning with respect to tasks
	 
	 
	 

	g2
	Manpower deployment plan
	 
	 
	 

	g3
	Material deployment plan
	 
	 
	 

	g4
	Organisational chart of the enterprise
	 
	 
	 

	 
	TOTAL g
	/4
	/4
	/4

	
	
	
	
	

	 
	I.  Pre-financing
	EVALUATION (Yes or No)

	h1
	Attestation of credibility shall be at least 55% of the bid price
	 
	 
	 

	 
	TOTAL 
	/1
	/1
	/1

	 
	GRAND TOTAL
	/54
	/54
	/54


ENVELOPE C- FINANCIAL FILE

	No.
	DESIGNATION.

	C1
	A submission letter, signed, dated and stamped.(see ANNEX 3)

	C2
	Completed and signed frame work of unit prices. 

	C3
	Signed Bills of quantities and cost estimates indicating the total amount without taxes (HT) and with taxes (TTC) 

	C4
	Signed Sub details of unit prices



THE BIDDER SHALL MEET AT LEAST 70% OF THE ESSENTIAL CRITERIA (54 sub-criteria), which is 38“Yes” sub-criteria out of 54 TO BE ELIGIBLE FOR FINANCIAL EVALUATION

· The bidders will use for this purpose the documents and models envisaged in the Tender Documents, subject to the provisions of Article 19.2 of the RGAO concerning the other possible forms of bid bond. 
· The various parts of the same file must be separated with colour guides from the original as well as in the copies, so as to facilitate its examination
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